## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | HOOGHLY |  | Hooghly Division | RETROFITTING WORKS FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) WITHIN THE COMMAND AREA OF LAKSHMIPUR WATER SUPPLY SCHEME. | SM/07535 | Retrofitting | FHTC |  |  | VCH/000522/2021-2022 |  | 23/07/2021 | 23/07/2021 | M/S T.K.B. CONSTRUCTION | 13.44 | 0 | 0 | 0
2 | HOOGHLY |  | Hooghly Division | RETROFITTING WORKS FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) WITHIN THE COMMAND AREA OF LAKSHMIPUR WATER SUPPLY SCHEME. | SM/07535 | Retrofitting | FHTC |  |  | VCH/002631/2020-2021 |  | 19/03/2021 | 19/03/2021 | DILIP KUMAR GHOSH | 15 | 0 | 0 | 0
3 | HOOGHLY |  | Hooghly Division | RETROFITTING WORKS FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) WITHIN THE COMMAND AREA OF LAKSHMIPUR WATER SUPPLY SCHEME. | SM/07535 | Retrofitting | FHTC |  |  | VCH/000595/2021-2022 |  | 17/08/2021 | 17/08/2021 | M/S T.K.B. CONSTRUCTION | 5.51 | 0 | 0 | 0
4 | HOOGHLY |  | Hooghly Division | RETROFITTING WORKS FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) WITHIN THE COMMAND AREA OF LAKSHMIPUR WATER SUPPLY SCHEME. | SM/07535 | Retrofitting | FHTC |  |  | VCH/000524/2021-2022 |  | 23/07/2021 | 23/07/2021 | DILIP KUMAR GHOSH | 13.44 | 0 | 0 | 0
5 | HOOGHLY |  | Hooghly Division | RETROFITTING WORKS FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) WITHIN THE COMMAND AREA OF LAKSHMIPUR WATER SUPPLY SCHEME. | SM/07535 | Retrofitting | Providing 50 nos Functional Household Tap Connection (FHTC) within the command area of LAKSHMIPUR Water Supply Scheme Under Arambag Sub-Division of Hooghly Division P.H.E Dte | Assistant Engineer | Junior Engineer (Civill) | ORD/000363/2021-2022 | 124/Hug | 19/01/2022 | 03/02/2022 | SADHUKHAN ENTERPRISE | 3.79 | 3.78 | 99.99 | 100
6 | HOOGHLY |  | Hooghly Division | RETROFITTING WORKS FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) WITHIN THE COMMAND AREA OF LAKSHMIPUR WATER SUPPLY SCHEME. | SM/07535 | Retrofitting | Placement of Fund |  |  | VCH/002590/2021-2022 | 844368 | 19/01/2022 | 19/01/2022 | JAL JEEVAN MISSION WEST BENGAL ESCROW AC | 11.53 | 0 | 0 | 0
7 | HOOGHLY |  | Hooghly Division | RETROFITTING WORKS FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) WITHIN THE COMMAND AREA OF LAKSHMIPUR WATER SUPPLY SCHEME. | SM/07535 | Retrofitting | Material Requisition To Resource Division |  |  | RTOR000018/2021-2022 | 2096/15/Hug | 26/11/2021 | 26/11/2021 | Resource Division | 0.82 | 0 | 0 | 0
Total | [13 empty] | 63.54 | 3.78 | 5.96