## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | HOOGHLY |  | Hooghly Division | RETROFITTING WORKS FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) WITHIN THE COMMAND AREA OF GOBINDAPUR WATER SUPPLY SCHEME. | SM/07536 | Retrofitting | FHTC |  |  | VCH/002576/2020-2021 |  | 19/03/2021 | 19/03/2021 | M/S R.K. CHOUDHURI | 40 | 0 | 0 | 0
2 | HOOGHLY |  | Hooghly Division | RETROFITTING WORKS FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) WITHIN THE COMMAND AREA OF GOBINDAPUR WATER SUPPLY SCHEME. | SM/07536 | Retrofitting | Providing 360 nos Functional Household Tap Connection (FHTC) within the command area of Gobindapur Water Supply Scheme Under Arambagh Sub-Division of Hooghly Division P.H.E Dte | Assistant Engineer | Junior Engineer (Civill) | ORD/000272/2021-2022 | 2126/Hug | 01/12/2021 | 31/12/2021 | M/S T.K.B. CONSTRUCTION | 13.29 | 0 | 0 | 100
3 | HOOGHLY |  | Hooghly Division | RETROFITTING WORKS FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) WITHIN THE COMMAND AREA OF GOBINDAPUR WATER SUPPLY SCHEME. | SM/07536 | Retrofitting | Providing 114 nos. Functional Household Tap Connection (F.H.T.C) within Command area of Mollah Para, Malik Para Habitation of Maikhanda Village under Gobindapur Water Supply Scheme under Arambagh Sub-Division, P.H.E. Dte. [Block-Khanakul-I] [ 2nd Call] | Assistant Engineer | Junior Engineer (Civill) | ORD/000516/2021-2022 | 174/Arg | 21/03/2022 | 20/04/2022 | BAKSHI ENTERPRISE | 4.69 | 0 | 0 | 100
4 | HOOGHLY |  | Hooghly Division | RETROFITTING WORKS FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) WITHIN THE COMMAND AREA OF GOBINDAPUR WATER SUPPLY SCHEME. | SM/07536 | Retrofitting | Providing 1207 nos F.H.T.C. in Gobindapur and its Adjoining Mouzas Water Supply Scheme Under Arambagh Sub-Division of Hooghly Division P.H.E Dte. [Block-Khanakul-I] | Assistant Engineer | Junior Engineer (Civill) | ORD/000887/2020-2021 | 406/HUG | 15/02/2021 | 17/03/2021 | M/S R.K. CHOUDHURI | 62.52 | 0 | 0 | 100
5 | HOOGHLY |  | Hooghly Division | RETROFITTING WORKS FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) WITHIN THE COMMAND AREA OF GOBINDAPUR WATER SUPPLY SCHEME. | SM/07536 | Retrofitting | FHTC |  |  | VCH/002094/2021-2022 |  | 27/01/2022 | 27/01/2022 | M/S T.K.B. CONSTRUCTION | 0 | 0 | 0 | 0
6 | HOOGHLY |  | Hooghly Division | RETROFITTING WORKS FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) WITHIN THE COMMAND AREA OF GOBINDAPUR WATER SUPPLY SCHEME. | SM/07536 | Retrofitting | Operation & Maintenance of OHR, FHTC & Laying Distribution System including Street stand Post, Rising Main & other essential components of Gobindapur, Patul & Khanakul W/S Scheme for the period of 01.09.21 to 31.08.22 under Arambagh Sub- Division P.H.E Dte. SL-54 |  |  | ORD/000177/2021-2022 | 1603/Hug | 03/09/2021 | 01/09/2022 | M/S PRADYUT KUMAR HAZRA | 9.37 | 0 | 0 | 0
7 | HOOGHLY |  | Hooghly Division | RETROFITTING WORKS FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) WITHIN THE COMMAND AREA OF GOBINDAPUR WATER SUPPLY SCHEME. | SM/07536 | Retrofitting | Material Requisition To Resource Division |  |  | RTOR000026/2021-2022 | 2096/23/Hug | 26/11/2021 | 26/11/2021 | Resource Division | 0.83 | 0 | 0 | 0
Total | [13 empty] | 130.7 | 0 | 0