## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | HOOGHLY |  | Hooghly Division | RETROFITTING WORKS FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) WITHIN THE COMMAND AREA OF CHANPARAI WATER SUPPLY SCHEME. | SM/07537 | Retrofitting | FHTC |  |  | VCH/001027/2021-2022 |  | 30/09/2021 | 30/09/2021 | RAJ CONSTRUCTION | 40.07 | 0 | 0 | 0
2 | HOOGHLY |  | Central Drilling | RETROFITTING WORKS FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) WITHIN THE COMMAND AREA OF CHANPARAI WATER SUPPLY SCHEME. | SM/07537 | Retrofitting | SUPPLY & DELIVERY OF BENTONITE POWDER SODIUM BASED (RAJASTHAN VARIETY) FOR CONSTRUCTION OF TUBE WELLS ATDHARAMPUR W/S SCH TW-I (REPLACEMENT) & UDANG W/S SCG TW-I HW SITE (REPLACEMENT) UNDER CMSD-II (D), CDD, PHE DTE. |  |  | ORD/000041/2021-2022 | 236/CMSD-II (D) | 23/08/2021 | 22/09/2021 | S B S ENTERPRISE | 0.85 | 0 | 0 | 100
3 | HOOGHLY |  | Central Drilling | RETROFITTING WORKS FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) WITHIN THE COMMAND AREA OF CHANPARAI WATER SUPPLY SCHEME. | SM/07537 | Retrofitting | PROVIDING TUBE WELL MATERIALS CONFORMING TO IS: 12818:2010 WITH OTHER MATERIALS AT SITE FOR CONSTRUCTION OF TUBE WELL IN HOOGHLY DISTRICT UNDER CMSD-II (D), CDD, PHE DTE. |  |  | ORD/000016/2021-2022 | 248/CMSD-II (D) | 24/08/2021 | 23/09/2021 | S B S ENTERPRISE | 2.88 | 0 | 0 | 100
4 | HOOGHLY |  | Central Drilling | RETROFITTING WORKS FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) WITHIN THE COMMAND AREA OF CHANPARAI WATER SUPPLY SCHEME. | SM/07537 | Retrofitting | SUPPLY & DELIVERY OF PEA SIZE GRAVELS AT SITE FOR CONSTRUCTION OF TUBE WELLS AT DHARAMPUR W/S SCH TW-I (REPLACEMENT) UNDER CMSD-II (D), CDD, PHE DTE. |  |  | ORD/000039/2021-2022 | 234/CMSD-II (D) | 23/08/2021 | 22/09/2021 | S B S ENTERPRISE | 0.96 | 0 | 0 | 100
5 | HOOGHLY |  | Central Drilling | RETROFITTING WORKS FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) WITHIN THE COMMAND AREA OF CHANPARAI WATER SUPPLY SCHEME. | SM/07537 | Retrofitting | PROVIDING TUBE WELL MATERIALS (200 CM PIPE & 200 MM RMS FILTER)CONFORMING TO IS: 12818:2010 WITH OTHER MATERIALS AT SITE FOR CONSTRUCTION OF TUBE WELL IN HOOGHLY DISTRICT UNDER CMSD-II (D), CDD, PHE DTE. |  |  | ORD/000017/2021-2022 | 249/CMSD-II (D) | 24/08/2021 | 23/09/2021 | S B S ENTERPRISE | 4.85 | 0 | 0 | 100
6 | HOOGHLY |  | Central Drilling | RETROFITTING WORKS FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) WITHIN THE COMMAND AREA OF CHANPARAI WATER SUPPLY SCHEME. | SM/07537 | Retrofitting | PROVIDING DRILLING CREWS FOR CONSTRUCTION OF TUBE WELL BY DEPARTMENTAL RIG MACHINE IN HOOGHLY DISTRICT UNDER CMSD-II (D), CDD, PHE DTE. |  |  | ORD/000035/2021-2022 | 255/CMSD-II (D) | 24/08/2021 | 08/09/2021 | S B S ENTERPRISE | 4.86 | 0 | 0 | 100
7 | HOOGHLY |  | Central Drilling | RETROFITTING WORKS FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) WITHIN THE COMMAND AREA OF CHANPARAI WATER SUPPLY SCHEME. | SM/07537 | Retrofitting | PROVIDING TUBE WELL MATERIALS, CONFORMING TO IS: 12818:2010 WITH OTHER MATERIALS AT SITE FOR CONSTRUCTION OF TUBE WELL IN HOOGHLY DISTRICT UNDER CMSD-II (D), CDD, PHE DTE. |  |  | ORD/000077/2021-2022 | 351/CMSD-II (D) | 15/09/2021 | 15/10/2021 | S B S ENTERPRISE | 4.17 | 0 | 0 | 100
8 | HOOGHLY |  | Central Drilling | RETROFITTING WORKS FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) WITHIN THE COMMAND AREA OF CHANPARAI WATER SUPPLY SCHEME. | SM/07537 | Retrofitting | PROVIDING DRILLING CREWS FOR CONSTRUCTION OF TUBE WELL BY DEPARTMENTAL RIG M/C IN HOOGHLY DISTRICT UNDER CMSD-II (D), CDD, PHE DTE. |  |  | ORD/000080/2021-2022 | 350/CMSD-II (D) | 15/09/2021 | 15/10/2021 | S B S ENTERPRISE | 4.86 | 0 | 0 | 100
9 | HOOGHLY |  | Central Drilling | RETROFITTING WORKS FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) WITHIN THE COMMAND AREA OF CHANPARAI WATER SUPPLY SCHEME. | SM/07537 | Retrofitting | PROVIDING TUBE WELL MATERIALS CONFORMING TO IS:12818:2010 WITH OTHER MATERIALS AT SITE FOR CONSTRUCTION OF TUBE WELL IN HOWRAH DISTRICT UNDER CMSD-II (D), CDD, PHE DTE. |  |  | ORD/000081/2021-2022 | 352/CMSD-II (D) | 15/09/2021 | 15/10/2021 | S B S ENTERPRISE | 2.38 | 0 | 0 | 100
10 | HOOGHLY |  | Central Drilling | RETROFITTING WORKS FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) WITHIN THE COMMAND AREA OF CHANPARAI WATER SUPPLY SCHEME. | SM/07537 | Retrofitting | SUPPLY & DELIVERY OF GRAVELS & BENTONITE POWDER AT SITE FOR CONSTRUCTION OF TUBE WELL AT DHARAMPUR TW-I (REPLACEMENT TUBE WELL) HOOGHLY DISTRICT UNDER CMSD-II (D), CDD, PHE DTE. |  |  | ORD/000096/2021-2022 | 222/CMSD-II (D) | 17/08/2021 | 01/09/2021 | S B S ENTERPRISE | 0.89 | 0 | 0 | 100
11 | HOOGHLY |  | Hooghly Division | RETROFITTING WORKS FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) WITHIN THE COMMAND AREA OF CHANPARAI WATER SUPPLY SCHEME. | SM/07537 | Retrofitting | Providing 1439 nos F.H.T.C. in Chanparai and its Adjoining Mouzas Water Supply Scheme Under Chinsurah Sub-Division of Hooghly Division P.H.E Dte. [Block-Chinsurah Mogra] | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/000302/2020-2021 | 380/Hug | 15/02/2021 | 27/03/2021 | RAJ CONSTRUCTION | 74.99 | 0 | 0 | 100
12 | HOOGHLY |  | Hooghly Division | RETROFITTING WORKS FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) WITHIN THE COMMAND AREA OF CHANPARAI WATER SUPPLY SCHEME. | SM/07537 | Retrofitting | Material Requisition To Resource Division |  |  | RTOR000071/2021-2022 | 2097/11/Hug | 26/11/2021 | 26/11/2021 | Resource Division | 0.83 | 0 | 0 | 0
13 | HOOGHLY |  | Central Drilling | RETROFITTING WORKS FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) WITHIN THE COMMAND AREA OF CHANPARAI WATER SUPPLY SCHEME. | SM/07537 | Retrofitting | Fuel charges for car no. WB-25H-5187 for the month of JANUARY 2023 |  |  | BILL/00127/2022-2023 | BP-2022-23-345 | 02/03/2023 | 02/03/2023 | MIRA SERVICE STATION | 0.2 | 0 | 0 | 0
Total | [13 empty] | 142.78 | 0 | 0