## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | HOOGHLY |  | Hooghly Division | RETROFITTING WORKS FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) WITHIN THE COMMAND AREA OF ABDULPUR WATER SUPPLY SCHEME. | SM/07540 | Retrofitting | FHTC |  |  | VCH/000836/2021-2022 |  | 21/09/2021 | 21/09/2021 | MECCANO UNEMPLOYED ENGINEERS CO - OPERATIVE SOCIETY LTD. | 15.6 | 0 | 0 | 0
2 | HOOGHLY |  | Hooghly Division | RETROFITTING WORKS FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) WITHIN THE COMMAND AREA OF ABDULPUR WATER SUPPLY SCHEME. | SM/07540 | Retrofitting | FHTC |  |  | VCH/000849/2021-2022 |  | 21/09/2021 | 21/09/2021 | TAPAS ADHYA | 11.3 | 0 | 0 | 0
3 | HOOGHLY |  | Hooghly Division | RETROFITTING WORKS FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) WITHIN THE COMMAND AREA OF ABDULPUR WATER SUPPLY SCHEME. | SM/07540 | Retrofitting | Providing 446 nos F.H.T.C. in Kamardanga Village of Abdulpur and its Adjoining Mouzas Water Supply Scheme Under Chinsurah Sub-Division of Hooghly Division P.H.E Dte. [Block-Balagarh] | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/000297/2020-2021 | 375/Hug | 15/02/2021 | 17/03/2021 | MECCANO UNEMPLOYED ENGINEERS CO - OPERATIVE SOCIETY LTD. | 23.29 | 16.02 | 68.78 | 100
4 | HOOGHLY |  | Hooghly Division | RETROFITTING WORKS FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) WITHIN THE COMMAND AREA OF ABDULPUR WATER SUPPLY SCHEME. | SM/07540 | Retrofitting | Providing 569 nos F.H.T.C. in Char Sundalpur & Abdulpur Village of Abdulpur and its Adjoining Mouzas Water Supply Scheme Under Chinsurah Sub-Division of Hooghly Division P.H.E Dte. [Block-Balagarh] | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/000296/2020-2021 | 374/Hug | 15/02/2021 | 17/03/2021 | TAPAS ADHYA | 29.72 | 27.34 | 91.98 | 100
5 | HOOGHLY |  | Hooghly Division | RETROFITTING WORKS FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) WITHIN THE COMMAND AREA OF ABDULPUR WATER SUPPLY SCHEME. | SM/07540 | Retrofitting | Laying of C.I/D.I pipes & specials for Rising main Pipeline inbetween T.W No.-I & II to O.H.R. including Bypass arrangement & interconnection with distribution system for Abdulpur W/S Scheme under Chinsurah Sub - Division P.H.E. Dte. | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/000420/2021-2022 | 90/CH | 03/02/2022 | 28/02/2022 | ARUN SEAL AND CO. | 2.36 | 1.8 | 76.27 | 100
6 | HOOGHLY |  | Central Drilling | RETROFITTING WORKS FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) WITHIN THE COMMAND AREA OF ABDULPUR WATER SUPPLY SCHEME. | SM/07540 | Retrofitting | Providing Drilling crew and other allied works for construction of Tube well (300mm x 200mm x 150 mtrs. Depth) by utilising Departmental machineries for Abdulpur W/S Scheme, Balagarh block under hooghly District, CDD PHE Dte. | Driller In Charge | Junior Engineer | ORD/000482/2022-2023 | 2342/CDD | 31/03/2023 | 30/04/2023 | UNIVERSAL ENTERPRISES | 11.38 | 10.28 | 90.41 | 100
7 | HOOGHLY |  | Hooghly Division | RETROFITTING WORKS FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) WITHIN THE COMMAND AREA OF ABDULPUR WATER SUPPLY SCHEME. | SM/07540 | Retrofitting | Material Requisition To Resource Division |  |  | RTOR000063/2021-2022 | 2097/3/Hug | 26/11/2021 | 26/11/2021 | Resource Division | 0.83 | 0 | 0 | 0
Total | [13 empty] | 94.47 | 55.44 | 58.68