## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | HOOGHLY |  | Hooghly Division | RETROFITTING WORKS FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) WITHIN THE COMMAND AREA OF DEPARA WATER SUPPLY SCHEME. | SM/07542 | Retrofitting | FHTC |  |  | VCH/002287/2020-2021 |  | 15/03/2021 | 15/03/2021 | BANSBERIA CONSTRUCTION CO. | 30 | 0 | 0 | 0
2 | HOOGHLY |  | Hooghly Division | RETROFITTING WORKS FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) WITHIN THE COMMAND AREA OF DEPARA WATER SUPPLY SCHEME. | SM/07542 | Retrofitting | FHTC |  |  | VCH/000023/2021-2022 |  | 12/04/2021 | 12/04/2021 | BANSBERIA CONSTRUCTION CO. | 5.98 | 0 | 0 | 0
3 | HOOGHLY |  | Hooghly Division | RETROFITTING WORKS FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) WITHIN THE COMMAND AREA OF DEPARA WATER SUPPLY SCHEME. | SM/07542 | Retrofitting | Providing 1414 nos F.H.T.C. in Depara and its Adjoining Mouzas Water Supply Scheme Under Chinsurah Sub-Division of Hooghly Division P.H.E Dte. [Block-Pandua] | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/000308/2020-2021 | 384/Hug | 15/02/2021 | 27/03/2021 | BANBERIA CONSTRUCTION CO. | 73.86 | 35.98 | 48.72 | 100
4 | HOOGHLY |  | Hooghly Division | RETROFITTING WORKS FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) WITHIN THE COMMAND AREA OF DEPARA WATER SUPPLY SCHEME. | SM/07542 | Retrofitting | Providing 675 nos Functional Household Tap Connection (FHTC) within the command area of Chikrand Zone-II Water Supply Scheme Under Serampore Sub-Division of Hooghly Division P.H.E Dte | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/000294/2021-2022 | 2205/Hug | 14/12/2021 | 23/01/2022 | ROY ENTERPRISE | 43.29 | 0 | 0 | 100
Total | [13 empty] | 153.13 | 35.98 | 23.5