## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | HOOGHLY |  | Hooghly Division | RETROFITTING WORKS FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) WITHIN THE COMMAND AREA OF PATUL WATER SUPPLY SCHEME. | SM/07543 | Retrofitting | FHTC |  |  | VCH/000585/2021-2022 |  | 17/08/2021 | 17/08/2021 | MS CHANDIMATA CONSTRUCTION | 5.11 | 0 | 0 | 0
2 | HOOGHLY |  | Hooghly Division | RETROFITTING WORKS FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) WITHIN THE COMMAND AREA OF PATUL WATER SUPPLY SCHEME. | SM/07543 | Retrofitting | FHTC |  |  | VCH/000530/2021-2022 |  | 28/07/2021 | 28/07/2021 | MS CHANDIMATA CONSTRUCTION | 41.45 | 0 | 0 | 0
3 | HOOGHLY |  | Hooghly Division | RETROFITTING WORKS FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) WITHIN THE COMMAND AREA OF PATUL WATER SUPPLY SCHEME. | SM/07543 | Retrofitting | FHTC |  |  | VCH/000017/2021-2022 |  | 12/04/2021 | 12/04/2021 | MS CHANDIMATA CONSTRUCTION | 5.04 | 0 | 0 | 0
4 | HOOGHLY |  | Hooghly Division | RETROFITTING WORKS FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) WITHIN THE COMMAND AREA OF PATUL WATER SUPPLY SCHEME. | SM/07543 | Retrofitting | Providing 400 nos Functional Household Tap Connection (FHTC) within the left out Mouzas of PATUL Water Supply Scheme Under Arambag Sub-Division of Hooghly Division P.H.E Dte | Assistant Engineer | Junior Engineer (Civill) | ORD/000097/2022-2023 | 1089/HUG | 03/06/2022 | 03/07/2022 | K. JAGADHATRY & CO. | 23.18 | 0 | 0 | 0
Total | [13 empty] | 74.78 | 0 | 0