## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | HOOGHLY |  | Hooghly Division | RETROFITTING WORKS FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) WITHIN THE COMMAND AREA OF UTTAR RAJYADHARPUR WATER SUPPLY SCHEME. | SM/07944 | Retrofitting | FHTC |  |  | VCH/002237/2020-2021 |  | 19/03/2021 | 19/03/2021 | UNIQUE AGENCY | 20.43 | 0 | 0 | 0
2 | HOOGHLY |  | Hooghly Division | RETROFITTING WORKS FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) WITHIN THE COMMAND AREA OF UTTAR RAJYADHARPUR WATER SUPPLY SCHEME. | SM/07944 | Retrofitting | FHTC |  |  | VCH/002559/2020-2021 |  | 19/03/2021 | 19/03/2021 | UNIQUE AGENCY | 16 | 0 | 0 | 0
3 | HOOGHLY |  | Hooghly Division | RETROFITTING WORKS FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) WITHIN THE COMMAND AREA OF UTTAR RAJYADHARPUR WATER SUPPLY SCHEME. | SM/07944 | Retrofitting | FHTC |  |  | VCH/002239/2020-2021 |  | 15/03/2021 | 15/03/2021 | JAGADHATRI CONSTRUCTION | 3 | 0 | 0 | 0
4 | HOOGHLY |  | Hooghly Division | RETROFITTING WORKS FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) WITHIN THE COMMAND AREA OF UTTAR RAJYADHARPUR WATER SUPPLY SCHEME. | SM/07944 | Retrofitting | FHTC |  |  | VCH/002560/2020-2021 |  | 19/03/2021 | 19/03/2021 | MAA TARA CONSTRUCTION | 4 | 0 | 0 | 0
5 | HOOGHLY |  | Hooghly Division | RETROFITTING WORKS FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) WITHIN THE COMMAND AREA OF UTTAR RAJYADHARPUR WATER SUPPLY SCHEME. | SM/07944 | Retrofitting | FHTC |  |  | VCH/002244/2020-2021 |  | 15/03/2021 | 15/03/2021 | J B CONSTRUCTION | 2 | 0 | 0 | 0
6 | HOOGHLY |  | Hooghly Division | RETROFITTING WORKS FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) WITHIN THE COMMAND AREA OF UTTAR RAJYADHARPUR WATER SUPPLY SCHEME. | SM/07944 | Retrofitting | FHTC |  |  | VCH/002241/2020-2021 |  | 15/03/2021 | 15/03/2021 | MAA TARA CONSTRUCTION | 4 | 0 | 0 | 0
7 | HOOGHLY |  | Hooghly Division | RETROFITTING WORKS FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) WITHIN THE COMMAND AREA OF UTTAR RAJYADHARPUR WATER SUPPLY SCHEME. | SM/07944 | Retrofitting | Providing 95 nos. F.H.T.C. in Uttar Rajyadharpur village of Uttar Rajyadharpur and its Adjoining Mouzas Water Supply Scheme under Serampore Sub-Division of Hooghly Division, P.H.E. Dte.[Block-Serampore-Uttarpara] (Part-C) | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/000870/2020-2021 | 230/SER | 26/02/2021 | 28/03/2021 | H.R. CONSTRUCTION | 2.63 | 0 | 0 | 100
8 | HOOGHLY |  | Hooghly Division | RETROFITTING WORKS FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) WITHIN THE COMMAND AREA OF UTTAR RAJYADHARPUR WATER SUPPLY SCHEME. | SM/07944 | Retrofitting | Computer Works |  |  | VCH/002122/2021-2022 | 844312 | 05/10/2021 | 05/10/2021 | ARATI ENGINEERING | 0.13 | 0 | 0 | 0
9 | HOOGHLY |  | Hooghly Division | RETROFITTING WORKS FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) WITHIN THE COMMAND AREA OF UTTAR RAJYADHARPUR WATER SUPPLY SCHEME. | SM/07944 | Retrofitting | Placement of Fund |  |  | VCH/002590/2021-2022 | 844368 | 19/01/2022 | 19/01/2022 | JAL JEEVAN MISSION WEST BENGAL ESCROW AC | 11.53 | 0 | 0 | 0
10 | HOOGHLY |  | Hooghly Division | RETROFITTING WORKS FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) WITHIN THE COMMAND AREA OF UTTAR RAJYADHARPUR WATER SUPPLY SCHEME. | SM/07944 | Retrofitting | Providing 20 nos. Functional Household Tap Connection (FHTC) within Chapsara & Uttar Rajyadharpur Mouzas in Uttar Rajyadharpur W/S Scheme under Serampore Sub-Division of Hooghly Division, P.H.E. Dte. | Assistant Engineer (Civil) |  | ORD/000063/2023-2024 | 06/SER | 10/04/2023 | 30/04/2023 | SURAJIT SINGHA RAY | 0.97 | 0 | 0 | 100
11 | HOOGHLY |  | Hooghly Division | RETROFITTING WORKS FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) WITHIN THE COMMAND AREA OF UTTAR RAJYADHARPUR WATER SUPPLY SCHEME. | SM/07944 | Retrofitting | Providing balance Functional Household Tap Connection (FHTC) within Chapsara & Uttar Rajyadharpur Mouzas in Uttar Rajyadharpur W/S Scheme under Serampore Sub-Division of Hooghly Division, P.H.E. Dte. | Assistant Engineer (Civil) |  | ORD/000065/2023-2024 | 08/SER | 10/04/2023 | 30/04/2023 | SURAJIT SINGHA RAY | 0.97 | 0 | 0 | 100
12 | HOOGHLY |  | Hooghly Division | RETROFITTING WORKS FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) WITHIN THE COMMAND AREA OF UTTAR RAJYADHARPUR WATER SUPPLY SCHEME. | SM/07944 | Retrofitting | Laying Additional Pipe line for Providing Functional Household Tap Connection (FHTC) within Chapsara & Uttar Rajyadharpur Mouzas in Uttar Rajyadharpur W/S Scheme under Serampore Sub-Division of Hooghly Division, P.H.E. Dte. | Assistant Engineer (Civil) |  | ORD/000064/2023-2024 | 07/SER | 10/04/2023 | 30/04/2023 | SURAJIT SINGHA RAY | 0.97 | 0 | 0 | 100
13 | HOOGHLY |  | Hooghly Division | RETROFITTING WORKS FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) WITHIN THE COMMAND AREA OF UTTAR RAJYADHARPUR WATER SUPPLY SCHEME. | SM/07944 | Retrofitting | Providing Functional Household Tap Connection (FHTC) within various habitation of Chapsara & Uttar Rajyadharpur Mouzas in Uttar Rajyadharpur W/S Scheme under Serampore Sub-Division of Hooghly Division, P.H.E. Dte | Assistant Engineer (Civil) |  | ORD/000066/2023-2024 | 09/SER | 10/04/2023 | 30/04/2023 | SURAJIT SINGHA RAY | 0.97 | 0 | 0 | 100
14 | HOOGHLY |  | Hooghly Division | RETROFITTING WORKS FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) WITHIN THE COMMAND AREA OF UTTAR RAJYADHARPUR WATER SUPPLY SCHEME. | SM/07944 | Retrofitting | Providing Functional Household Tap Connection (FHTC) within left out habitation of Chapsara & Uttar Rajyadharpur Mouzas in Uttar Rajyadharpur W/S Scheme under Serampore Sub-Division of Hooghly Division, P.H.E. Dte. | Assistant Engineer (Civil) |  | ORD/000067/2023-2024 | 10/SER | 10/04/2023 | 30/04/2023 | SURAJIT SINGHA RAY | 0.97 | 0 | 0 | 100
15 | HOOGHLY |  | Hooghly Division | RETROFITTING WORKS FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) WITHIN THE COMMAND AREA OF UTTAR RAJYADHARPUR WATER SUPPLY SCHEME. | SM/07944 | Retrofitting | Extension of pipeline for providing FHTC Connection for Uttar Rajyadharpur Mouza of Uttar Rajyadharpur Piped Water Supply Scheme under Serampore Sub-Division of Hooghly Division, P.H.E. Dte.[ Block- Serampore-Uttarpara] | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/000238/2023-2024 | 98/SER | 19/06/2023 | 19/07/2023 | SURAJIT SINGHA RAY | 0.99 | 0 | 0 | 100
16 | HOOGHLY |  | Hooghly Division | RETROFITTING WORKS FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) WITHIN THE COMMAND AREA OF UTTAR RAJYADHARPUR WATER SUPPLY SCHEME. | SM/07944 | Retrofitting | Extension of pipeline due to providing FHTC Connection for Chapsara Mouza of Uttar Rajyadharpur Piped Water Supply Scheme under Serampore Sub-Division of Hooghly Division, P.H.E. Dte.[ Block- Serampore-Uttarpara] | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/000239/2023-2024 | 99/SER | 19/06/2023 | 19/07/2023 | SURAJIT SINGHA RAY | 1 | 0 | 0 | 100
17 | HOOGHLY |  | Hooghly Division | RETROFITTING WORKS FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) WITHIN THE COMMAND AREA OF UTTAR RAJYADHARPUR WATER SUPPLY SCHEME. | SM/07944 | Retrofitting | Material Requisition To Resource Division |  |  | RTOR000129/2021-2022 | 2198/HUG | 14/12/2021 | 14/12/2021 | Resource Division | 1.59 | 0 | 0 | 0
Total | [13 empty] | 72.16 | 0 | 0