## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | HOOGHLY |  | Hooghly Division | RETROFITTING WORKS FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) WITHIN THE COMMAND AREA OF DIHIBAYARA WATER SUPPLY SCHEME. | SM/07945 | Retrofitting | FHTC |  |  | VCH/000518/2021-2022 |  | 23/07/2021 | 23/07/2021 | DAS TRADING | 11.53 | 0 | 0 | 0
2 | HOOGHLY |  | Hooghly Division | RETROFITTING WORKS FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) WITHIN THE COMMAND AREA OF DIHIBAYARA WATER SUPPLY SCHEME. | SM/07945 | Retrofitting | FHTC |  |  | VCH/002254/2020-2021 |  | 15/03/2021 | 15/03/2021 | JAL PRAVAHIKA PVT. LTD | 32.35 | 0 | 0 | 0
3 | HOOGHLY |  | Hooghly Division | RETROFITTING WORKS FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) WITHIN THE COMMAND AREA OF DIHIBAYARA WATER SUPPLY SCHEME. | SM/07945 | Retrofitting | FHTC |  |  | VCH/001902/2020-2021 |  | 15/02/2021 | 15/02/2021 | M/S T.K.B. CONSTRUCTION | 4.8 | 0 | 0 | 0
4 | HOOGHLY |  | Hooghly Division | RETROFITTING WORKS FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) WITHIN THE COMMAND AREA OF DIHIBAYARA WATER SUPPLY SCHEME. | SM/07945 | Retrofitting | FHTC |  |  | VCH/000840/2021-2022 |  | 21/09/2021 | 21/09/2021 | DAS TRADING | 6.6 | 0 | 0 | 0
5 | HOOGHLY |  | Hooghly Division | RETROFITTING WORKS FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) WITHIN THE COMMAND AREA OF DIHIBAYARA WATER SUPPLY SCHEME. | SM/07945 | Retrofitting | Providing 50 nos Functional Household Tap Connection (FHTC) within Dihibayra & Maheshpur Village of Dihibayra Water Supply Scheme Under Arambagh Sub-Division of Hooghly Division P.H.E Dte. [Block-Arambagh] | Assistant Engineer | Junior Engineer (Civill) | ORD/000013/2022-2023 | 714/Hug | 07/04/2022 | 27/04/2022 | SAKSHI ENTERPRISE | 4.79 | 4.79 | 99.99 | 100
6 | HOOGHLY |  | Hooghly Division | RETROFITTING WORKS FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) WITHIN THE COMMAND AREA OF DIHIBAYARA WATER SUPPLY SCHEME. | SM/07945 | Retrofitting | Construction of boundary wall, Internal Pathway and allied works at 3rd TW Site of DIHI BAYARA Water Supply Scheme under Arambagh Sub-Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer (Civill) | ORD/000127/2022-2023 | 439/Arg | 22/06/2022 | 22/07/2022 | M/S TANISA ENTERPRISE | 4.43 | 0 | 0 | 100
7 | HOOGHLY |  | Hooghly Division | RETROFITTING WORKS FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) WITHIN THE COMMAND AREA OF DIHIBAYARA WATER SUPPLY SCHEME. | SM/07945 | Retrofitting | Material Requisition To Resource Division |  |  | RTOR000025/2022-2023 | 1124/6/HUG | 06/06/2022 | 06/06/2022 | Resource Division | 10.98 | 0 | 0 | 0
Total | [13 empty] | 75.48 | 4.79 | 6.34