## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | HOOGHLY |  | Hooghly Division | RETROFITTING WORKS FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) WITHIN THE COMMAND AREA OF ANTPUR WATER SUPPLY SCHEME. | SM/07946 | Retrofitting | FHTC |  |  | VCH/000837/2021-2022 |  | 21/09/2021 | 21/09/2021 | COMPAQ ENGINEER'S CO - OPERATIVE SOCIETY LTD | 30.09 | 0 | 0 | 0
2 | HOOGHLY |  | Hooghly Division | RETROFITTING WORKS FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) WITHIN THE COMMAND AREA OF ANTPUR WATER SUPPLY SCHEME. | SM/07946 | Retrofitting | Sinking of 3 nos. 300 X200 mm dia Tube Well 180 mtr. Depth by D.R. Rig method using UPVC pipe (CD) and UPVC Deep Well Screen (RDS) at 2nd Tube Well Site of JANGIPARA ZONE-II W/S Scheme, 4th Tube Well Site of ANTPUR W/S Scheme, & 4th Tube Well Site of JANGALPARA W/S Scheme under Serampore Sub-Division of Hooghly Division, P.H.E. Dte. . | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/000425/2024-2025 | 3522/HUG | 22/10/2024 | 03/09/2025 | WATER TECH | 29.57 | 0 | 0 | 45
Total | [13 empty] | 59.66 | 0 | 0