## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | HOOGHLY |  | Hooghly Division | RETROFITTING WORKS FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) WITHIN THE COMMAND AREA OF BANDIPUR WATER SUPPLY SCHEME. | SM/07948 | Retrofitting | FHTC |  |  | VCH/002298/2020-2021 |  | 15/03/2021 | 15/03/2021 | BANSBERIA CONSTRUCTION CO. | 35 | 0 | 0 | 0
2 | HOOGHLY |  | Hooghly Division | RETROFITTING WORKS FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) WITHIN THE COMMAND AREA OF BANDIPUR WATER SUPPLY SCHEME. | SM/07948 | Retrofitting | FHTC |  |  | VCH/000010/2021-2022 |  | 12/04/2021 | 12/04/2021 | BANERJEE CONSTRUCTION | 11.71 | 0 | 0 | 0
3 | HOOGHLY |  | Hooghly Division | RETROFITTING WORKS FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) WITHIN THE COMMAND AREA OF BANDIPUR WATER SUPPLY SCHEME. | SM/07948 | Retrofitting | FHTC |  |  | VCH/000004/2021-2022 |  | 06/04/2021 | 06/04/2021 | BANERJEE CONSTRUCTION | 6.85 | 0 | 0 | 0
4 | HOOGHLY |  | Hooghly Division | RETROFITTING WORKS FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) WITHIN THE COMMAND AREA OF BANDIPUR WATER SUPPLY SCHEME. | SM/07948 | Retrofitting | FHTC |  |  | VCH/001889/2020-2021 |  | 29/01/2021 | 29/01/2021 | MINTU CHAKRABORTY | 26.7 | 0 | 0 | 0
5 | HOOGHLY |  | Hooghly Division | RETROFITTING WORKS FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) WITHIN THE COMMAND AREA OF BANDIPUR WATER SUPPLY SCHEME. | SM/07948 | Retrofitting | Placement of Fund |  |  | VCH/002590/2021-2022 | 844368 | 19/01/2022 | 19/01/2022 | JAL JEEVAN MISSION WEST BENGAL ESCROW AC | 11.53 | 0 | 0 | 0
6 | HOOGHLY |  | Hooghly Division | RETROFITTING WORKS FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) WITHIN THE COMMAND AREA OF BANDIPUR WATER SUPPLY SCHEME. | SM/07948 | Retrofitting | Providing 158 nos Functional Household Tap Connection (FHTC) & extension of Laying Distribution System within the uncovered area of Bandipur and its Adjoining Mouzas Water Supply Scheme Under Chandannagar Sub-Division of Hooghly Division P.H.E Dte. [Block-Haripal] | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/000356/2020-2021 | 468/Hug | 26/02/2021 | 18/03/2021 | MINTU CHAKRABORTY | 19.87 | 0 | 0 | 100
7 | HOOGHLY |  | Hooghly Division | RETROFITTING WORKS FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) WITHIN THE COMMAND AREA OF BANDIPUR WATER SUPPLY SCHEME. | SM/07948 | Retrofitting | Providing 122 nos F.H.T.C. & extension of pipe line in left out portion of Dilalpur village of Bandipur and its Adjoining Mouzas Water Supply Scheme Under Chandannagar Sub-Division of Hooghly Division P.H.E Dte. [Block-Haripal] | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/000275/2020-2021 | 322/Hug | 11/02/2021 | 03/03/2021 | BANERJEE CONSTRUCTION | 25.9 | 15.91 | 61.45 | 100
Total | [13 empty] | 137.56 | 15.91 | 11.57