## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | HOOGHLY |  | Hooghly Division | RETROFITTING WORKS FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) WITHIN THE COMMAND AREA OF GURAP WATER SUPPLY SCHEME. | SM/07949 | Retrofitting | FHTC |  |  | VCH/000003/2021-2022 |  | 06/04/2021 | 06/04/2021 | M/S BISWAS CONSTRUCTION | 7.43 | 0 | 0 | 0
2 | HOOGHLY |  | Hooghly Division | RETROFITTING WORKS FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) WITHIN THE COMMAND AREA OF GURAP WATER SUPPLY SCHEME. | SM/07949 | Retrofitting | FHTC |  |  | VCH/000021/2021-2022 |  | 12/04/2021 | 12/04/2021 | GOBINDA MAITY | 3.29 | 0 | 0 | 0
3 | HOOGHLY |  | Hooghly Division | RETROFITTING WORKS FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) WITHIN THE COMMAND AREA OF GURAP WATER SUPPLY SCHEME. | SM/07949 | Retrofitting | FHTC |  |  | VCH/002539/2020-2021 |  | 19/03/2021 | 19/03/2021 | M/S BISWAS CONSTRUCTION | 12 | 0 | 0 | 0
4 | HOOGHLY |  | Hooghly Division | RETROFITTING WORKS FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) WITHIN THE COMMAND AREA OF GURAP WATER SUPPLY SCHEME. | SM/07949 | Retrofitting | FHTC |  |  | VCH/002291/2020-2021 |  | 15/03/2021 | 15/03/2021 | GOBINDA MAITY | 16.4 | 0 | 0 | 0
5 | HOOGHLY |  | Hooghly Division | RETROFITTING WORKS FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) WITHIN THE COMMAND AREA OF GURAP WATER SUPPLY SCHEME. | SM/07949 | Retrofitting | Providing 600 nos Functional Household Tap Connection (FHTC) within the command area of GURAP Water Supply Scheme Under Chinsurah Sub-Division of Hooghly Division P.H.E Dte | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/000354/2021-2022 | 115/Hug | 19/01/2022 | 18/02/2022 | MERCANTILE HALL | 43.98 | 44.14 | 100.37 | 100
6 | HOOGHLY |  | Hooghly Division | RETROFITTING WORKS FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) WITHIN THE COMMAND AREA OF GURAP WATER SUPPLY SCHEME. | SM/07949 | Retrofitting | Providing Functional Household Tap Connection (FHTC) within the command area (left out portion) of GURAP Water Supply Scheme Under Chinsurah Sub-Division of Hooghly Division P.H.E Dte. | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/000159/2022-2023 | 1511/HUG | 22/07/2022 | 06/08/2022 | R CONSTRUCTION | 19.73 | 17.48 | 88.59 | 100
7 | HOOGHLY |  | Hooghly Division | RETROFITTING WORKS FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) WITHIN THE COMMAND AREA OF GURAP WATER SUPPLY SCHEME. | SM/07949 | Retrofitting | Placement of Fund |  |  | VCH/002590/2021-2022 | 844368 | 19/01/2022 | 19/01/2022 | JAL JEEVAN MISSION WEST BENGAL ESCROW AC | 11.53 | 0 | 0 | 0
8 | HOOGHLY |  | Hooghly Division | RETROFITTING WORKS FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) WITHIN THE COMMAND AREA OF GURAP WATER SUPPLY SCHEME. | SM/07949 | Retrofitting | Rising Main Pipe line in between 3rd T.W By to pass arrangement and interconnection with Distribution System for Gurap Water Supply Scheme Under Chinsurah Sub-Division. | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/000481/2021-2022 | 111/CH | 10/02/2022 | 07/03/2022 | M/S S.G. CONSTRUCTION | 4.18 | 0 | 0 | 0
9 | HOOGHLY |  | Hooghly Division | RETROFITTING WORKS FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) WITHIN THE COMMAND AREA OF GURAP WATER SUPPLY SCHEME. | SM/07949 | Retrofitting | Rising Main in between 2nd T.W to O.H.R Bypass arrangement and interconnection with Distribution System for Gurap Water Supply Scheme Under Chinsurah Sub-Division. | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/000116/2022-2023 | 398/CH | 06/05/2022 | 10/06/2022 | M/S S.G. CONSTRUCTION | 2.69 | 0 | 0 | 100
10 | HOOGHLY |  | Hooghly Division | RETROFITTING WORKS FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) WITHIN THE COMMAND AREA OF GURAP WATER SUPPLY SCHEME. | SM/07949 | Retrofitting | Rising Main in between 2nd T.W to OHR Bypass arrangement and interconnection with Distribution System for Gurap Water Supply Scheme Under Chinsurah Sub-Division. | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/000679/2022-2023 | 398/CH | 06/05/2022 | 10/06/2022 | M/S S.G. CONSTRUCTION | 2.69 | 2.66 | 98.84 | 100
Total | [13 empty] | 123.92 | 64.27 | 51.87