## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | HOOGHLY |  | Hooghly Division | RETROFITTING WORKS FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) WITHIN THE COMMAND AREA OF PATNA BHAIRABPUR WATER SUPPLY SCHEME. | SM/07950 | Retrofitting | FHTC |  |  | VCH/001925/2020-2021 | null | 15/02/2021 |  | ASHOK GHOSH & BROTHERS | 20 | 0 | 0 | 0
2 | HOOGHLY |  | Hooghly Division | RETROFITTING WORKS FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) WITHIN THE COMMAND AREA OF PATNA BHAIRABPUR WATER SUPPLY SCHEME. | SM/07950 | Retrofitting | FHTC |  |  | VCH/000588/2021-2022 | null | 16/08/2021 |  | PRADIP KUMAR ADHYA | 59.27 | 0 | 0 | 0
3 | HOOGHLY |  | Hooghly Division | RETROFITTING WORKS FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) WITHIN THE COMMAND AREA OF PATNA BHAIRABPUR WATER SUPPLY SCHEME. | SM/07950 | Retrofitting | FHTC |  |  | VCH/000934/2021-2022 | null | 24/09/2021 |  | K. JAGADHATRY & CO. | 4.01 | 0 | 0 | 0
4 | HOOGHLY |  | Hooghly Division | RETROFITTING WORKS FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) WITHIN THE COMMAND AREA OF PATNA BHAIRABPUR WATER SUPPLY SCHEME. | SM/07950 | Retrofitting | FHTC |  |  | VCH/000938/2021-2022 | null | 24/09/2021 |  | YOUNG ENGINEERS CO-OPERATIVE SOCIETY LTD. | 11.55 | 0 | 0 | 0
5 | HOOGHLY |  | Hooghly Division | RETROFITTING WORKS FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) WITHIN THE COMMAND AREA OF PATNA BHAIRABPUR WATER SUPPLY SCHEME. | SM/07950 | Retrofitting | FHTC |  |  | VCH/000936/2021-2022 | null | 24/09/2021 |  | K. JAGADHATRY & CO. | 4.01 | 0 | 0 | 0
6 | HOOGHLY |  | Hooghly Division | RETROFITTING WORKS FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) WITHIN THE COMMAND AREA OF PATNA BHAIRABPUR WATER SUPPLY SCHEME. | SM/07950 | Retrofitting | FHTC |  |  | VCH/001050/2021-2022 | null | 30/09/2021 |  | RURAL CONSTRUCTION (MANIK CHANDRA ADAK) | 4.5 | 0 | 0 | 0
7 | HOOGHLY |  | Hooghly Division | RETROFITTING WORKS FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) WITHIN THE COMMAND AREA OF PATNA BHAIRABPUR WATER SUPPLY SCHEME. | SM/07950 | Retrofitting | Providing 250 nos F.H.T.C. in Kotalpur village of Patna Bhairabpur and its Adjoining Mouzas Water Supply Scheme Under Chinsurah Sub-Division of Hooghly Division P.H.E Dte. [Block-Polba-Dadpur] | Assistant Engineer (Civil) |  | ORD/000268/2020-2021 | 262/Hug | 03/02/2021 | 23/02/2021 | K JAGADHATRY & CO | 13.62 | 3.85 | 28.3 | 0
8 | HOOGHLY |  | Hooghly Division | RETROFITTING WORKS FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) WITHIN THE COMMAND AREA OF PATNA BHAIRABPUR WATER SUPPLY SCHEME. | SM/07950 | Retrofitting | Providing 200 nos F.H.T.C. in Patna Bhairabpur village of Patna Bhairabpur and its Adjoining Mouzas Water Supply Scheme Under Chinsurah Sub-Division of Hooghly Division P.H.E Dte. [Block-Polba-Dadpur] | Assistant Engineer (Civil) |  | ORD/000269/2020-2021 | 263/Hug | 03/02/2021 | 23/02/2021 | YOUNG ENGINEERS CO OPERATIVE SOCIETY LTD. | 14.3 | 11.55 | 80.79 | 85
9 | HOOGHLY |  | Hooghly Division | RETROFITTING WORKS FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) WITHIN THE COMMAND AREA OF PATNA BHAIRABPUR WATER SUPPLY SCHEME. | SM/07950 | Retrofitting | Maintenance of Laying distribution system & Rising main of Balagarh, Dumurdaha, Raghunathpur, Amodghata W/S Scheme |  |  | ORD/2011-2012/000064 | 1807/Hug | 29/12/2011 |  | PRADIP KUMAR ADHYA | 2.01 | 29.69 | 1476.64 | 0
Total | [13 empty] | 133.28 | 45.09 | 33.83