## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | HOOGHLY |  | Hooghly Division | RETROFITTING WORKS FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) WITHIN THE COMMAND AREA OF PAUNAN WATER SUPPLY SCHEME. | SM/07951 | Retrofitting | FHTC |  |  | VCH/000856/2021-2022 |  | 21/09/2021 | 21/09/2021 | M/S S.G. CONSTRUCTION | 8.61 | 0 | 0 | 0
2 | HOOGHLY |  | Hooghly Division | RETROFITTING WORKS FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) WITHIN THE COMMAND AREA OF PAUNAN WATER SUPPLY SCHEME. | SM/07951 | Retrofitting | FHTC |  |  | VCH/001911/2020-2021 |  | 15/02/2021 | 15/02/2021 | M/S S.G. CONSTRUCTION | 47 | 0 | 0 | 0
3 | HOOGHLY |  | Hooghly Division | RETROFITTING WORKS FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) WITHIN THE COMMAND AREA OF PAUNAN WATER SUPPLY SCHEME. | SM/07951 | Retrofitting | FHTC |  |  | VCH/000586/2021-2022 |  | 17/08/2021 | 17/08/2021 | TIRUPATI ENTERPRISE | 30.33 | 0 | 0 | 0
4 | HOOGHLY |  | Hooghly Division | RETROFITTING WORKS FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) WITHIN THE COMMAND AREA OF PAUNAN WATER SUPPLY SCHEME. | SM/07951 | Retrofitting | Providing 1680 nos F.H.T.C. in Amnan, Araji Jotchandi ,Banseye, Barun Napara,Kedar nagar, Ramnagar , Mirzzapur & Jatarpur village of Paunan and its Adjoining Mouzas Water Supply Scheme Under Chinsurah Sub-Division of Hooghly Division P.H.E Dte. [Block-Polba-Dadpur] | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/000882/2020-2021 | 1682HUG. | 17/12/2020 | 26/01/2021 | TIRUPATI ENTERPRISES | 11 | 0 | 0 | 100
5 | HOOGHLY |  | Hooghly Division | RETROFITTING WORKS FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) WITHIN THE COMMAND AREA OF PAUNAN WATER SUPPLY SCHEME. | SM/07951 | Retrofitting | Providing 1680 nos F.H.T.C. in Amnan, Araji Jotchandi ,Banseye, Barun Napara,Kedar nagar, Ramnagar , Mirzzapur & Jatarpur village of Paunan and its Adjoining Mouzas Water Supply Scheme Under Chinsurah Sub-Division of Hooghly Division P.H.E Dte. [Block-Polba-Dadpur] | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/000096/2020-2021 | 1682/Hug | 17/12/2020 | 17/06/2021 | TIRUPATI ENTERPRISE | 53.57 | 30.33 | 56.62 | 100
6 | HOOGHLY |  | Hooghly Division | RETROFITTING WORKS FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) WITHIN THE COMMAND AREA OF PAUNAN WATER SUPPLY SCHEME. | SM/07951 | Retrofitting | Providing 220 nos Functional Household Tap Connection (FHTC) within the command area of PAUNAN Water Supply Scheme Under Chinsurah Sub-Division of Hooghly Division P.H.E Dte | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/000447/2021-2022 | 465/Hug | 10/03/2022 | 30/03/2022 | SAMRAT CONSTRUCTION | 19.02 | 0 | 0 | 100
Total | [13 empty] | 169.53 | 30.33 | 17.89