## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | HOOGHLY |  | Hooghly Division | RETROFITTING WORKS FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) WITHIN THE COMMAND AREA OF HANRAL WATER SUPPLY SCHEME. | SM/07952 | Retrofitting | FHTC |  |  | VCH/000943/2021-2022 |  | 24/09/2021 | 24/09/2021 | LOKENIRMAN | 28.24 | 0 | 0 | 0
2 | HOOGHLY |  | Hooghly Division | RETROFITTING WORKS FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) WITHIN THE COMMAND AREA OF HANRAL WATER SUPPLY SCHEME. | SM/07952 | Retrofitting | FHTC |  |  | VCH/001048/2021-2022 |  | 30/09/2021 | 30/09/2021 | M/S S.S. ENTERPRISE | 26.38 | 0 | 0 | 0
3 | HOOGHLY |  | Hooghly Division | RETROFITTING WORKS FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) WITHIN THE COMMAND AREA OF HANRAL WATER SUPPLY SCHEME. | SM/07952 | Retrofitting | Providing 390 nos Functional Household Tap Connection (FHTC) within the command area of HANRAL & DWARBASINI Water Supply Scheme Under Chinsurah Sub-Division of Hooghly Division P.H.E Dte | Assistant Engineer (Civil) |  | ORD/000442/2021-2022 | 460/Hug | 10/03/2022 | 04/04/2022 | M/S R.M. CONSTRUCTION | 28.34 | 0 | 0 | 100
4 | HOOGHLY |  | Central Drilling | RETROFITTING WORKS FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) WITHIN THE COMMAND AREA OF HANRAL WATER SUPPLY SCHEME. | SM/07952 | Retrofitting | LOADING UNLOADING & SHIFTING OF DRILLING ACCESSORIES, SUPPORTING VEHICLES ALONG WITH RIG MACHINE JOHN/DR/1500-I FROM HANRAL (Z-II) PWSS, BLOCK - POLBA DADPUR, HOOGHLY DISTRICT TO PANCHLA STORE, HOWRAH, UNDER CDD, PHE DTE. |  |  | ORD/000212/2022-2023 | 519/CMSD-I | 21/10/2022 | 24/10/2022 | DEV ENTERPRISE | 0.32 | 0 | 0 | 100
5 | HOOGHLY |  | Central Drilling | RETROFITTING WORKS FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) WITHIN THE COMMAND AREA OF HANRAL WATER SUPPLY SCHEME. | SM/07952 | Retrofitting | LOADING UNLOADING & SHIFTING OF DRILLING ACCESSORIES, SUPPORTING VEHICLES ALONG WITH RIG MACHINE JOHN/DR/1500-I FROM HANRAL (Z-I) PWSS, BLOCK- POLBA DADPUR, HOOGHLY DISTRICT TO PANCHLA STORE, HOWRAH, UNDER CDD, PHE DTE. |  |  | ORD/000214/2022-2023 | 491/CMSD-I | 28/09/2022 | 05/10/2022 | DEV ENTERPRISE | 0.32 | 0 | 0 | 100
6 | HOOGHLY |  | Central Drilling | RETROFITTING WORKS FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) WITHIN THE COMMAND AREA OF HANRAL WATER SUPPLY SCHEME. | SM/07952 | Retrofitting | PROVIDING DRILLING CREW AND OTHER ALLIED WORKS FOR CONSTRUCTION OF TUBE WELL (250MM X 150MM X 250 MTRS DEPTH) BY UTILIZING DEPARTMENTAL MACHINERIES FOR HANRAL W/S SCH, POLBA DADPUR BLOCK UNDER HOOGHLY DISTRICT, CDD, PHE DTE. | Driller In Charge | Junior Engineer | ORD/000158/2022-2023 | 293/CDD | 27/04/2022 | 27/05/2022 | PADMA ENGINEERING & CO. | 11.23 | 0 | 0 | 100
7 | HOOGHLY |  | Central Drilling | RETROFITTING WORKS FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) WITHIN THE COMMAND AREA OF HANRAL WATER SUPPLY SCHEME. | SM/07952 | Retrofitting | PROVIDING DRILLING CREW AND OTHER ALLIED WORKS FOR CONSTRUCTION OF TUBE WELL (250MM X 150MM X 250 MTRS DEPTH) BY UTILIZING DEPARTMENTAL MACHINERIES FOR HANRAL W/S SCH, POLBA DADPUR BLOCK UNDER HOOGHLY DISTRICT, CDD, PHE DTE. |  |  | ORD/000161/2022-2023 | 292/CDD | 27/04/2022 | 27/05/2022 | PADMA ENGINEERING & CO. | 11.23 | 0 | 0 | 90
8 | HOOGHLY |  | Hooghly Division | RETROFITTING WORKS FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) WITHIN THE COMMAND AREA OF HANRAL WATER SUPPLY SCHEME. | SM/07952 | Retrofitting | Providing 1507 nos F.H.T.C. in Samsara, Hodla,Aima,Kharsat, Rasulpur,Khidirpur, Dakshin Dadpur,Maheshwarpur& Tamila Village of Hanral Zone-II and its Adjoining Mouzas Water Supply Scheme UnderChinsurah Sub-Division of Hooghly Division P.H.E Dte. [Block-Polba-Dapur] | Assistant Engineer (Civil) |  | ORD/000080/2021-2022 | 1146/Hug | 29/06/2021 | 08/08/2021 | LOKENIRMAN | 87 | 0 | 0 | 100
9 | HOOGHLY |  | Hooghly Division | RETROFITTING WORKS FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) WITHIN THE COMMAND AREA OF HANRAL WATER SUPPLY SCHEME. | SM/07952 | Retrofitting | Providing1670 nos F.H.T.C. in Sarkhola, Hanral,Mogalpur,Kantul, Anantapur,Krishnapur, Shrirampur,Kantagare & Sekendarpur Village of Hanral Zone-I and its Adjoining Mouzas Water Supply Scheme UnderChinsurah Sub-Division of Hooghly Division P.H.E Dte. [Block-Polba-Dapur] | Assistant Engineer (Civil) |  | ORD/000007/2021-2022 | 938/Hug | 06/05/2021 | 15/06/2021 | M/S S.S. ENTERPRISE | 96.09 | 0 | 0 | 100
Total | [13 empty] | 289.15 | 0 | 0