## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | HOOGHLY |  | Hooghly Division | RETROFITTING WORKS FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) WITHIN THE COMMAND AREA OF PASCHIM JOYKRISHNAPUR WATER SUPPLY | SM/07954 | Retrofitting | FHTC |  |  | VCH/001102/2021-2022 |  | 08/11/2021 | 08/11/2021 | BANSBERIA CONSTRUCTION CO. | 7.95 | 0 | 0 | 0
2 | HOOGHLY |  | Hooghly Division | RETROFITTING WORKS FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) WITHIN THE COMMAND AREA OF PASCHIM JOYKRISHNAPUR WATER SUPPLY | SM/07954 | Retrofitting | FHTC |  |  | VCH/002614/2020-2021 |  | 19/03/2021 | 19/03/2021 | BANSBERIA CONSTRUCTION CO. | 31 | 0 | 0 | 0
3 | HOOGHLY |  | Hooghly Division | RETROFITTING WORKS FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) WITHIN THE COMMAND AREA OF PASCHIM JOYKRISHNAPUR WATER SUPPLY | SM/07954 | Retrofitting | FHTC |  |  | VCH/001053/2021-2022 |  | 30/09/2021 | 30/09/2021 | UNIQUE AGENCY | 43.59 | 0 | 0 | 0
4 | HOOGHLY |  | Hooghly Division | RETROFITTING WORKS FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) WITHIN THE COMMAND AREA OF PASCHIM JOYKRISHNAPUR WATER SUPPLY | SM/07954 | Retrofitting | FHTC |  |  | VCH/001044/2021-2022 |  | 30/09/2021 | 30/09/2021 | UNIQUE AGENCY | 41.52 | 0 | 0 | 0
5 | HOOGHLY |  | Hooghly Division | RETROFITTING WORKS FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) WITHIN THE COMMAND AREA OF PASCHIM JOYKRISHNAPUR WATER SUPPLY | SM/07954 | Retrofitting | Providing1527 nos F.H.T.C. in Chaitanyapur, Chak Ananta,Kulubati Bhagabatipur & Radha Krishnapur Village of Paschim Joykrishnapur and its Adjoining Mouzas Water Supply Scheme Under Chandannagar Sub-Division of Hooghly Division P.H.E Dte. [Block-Haripal] | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/000567/2021-2022 | 944/HUG | 06/05/2021 | 15/06/2021 | PAUL CONSTRUCTION (RANJIT KUMAR PAUL) | 88.35 | 0 | 0 | 100
6 | HOOGHLY |  | Hooghly Division | RETROFITTING WORKS FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) WITHIN THE COMMAND AREA OF PASCHIM JOYKRISHNAPUR WATER SUPPLY | SM/07954 | Retrofitting | Placement of Fund |  |  | VCH/002590/2021-2022 | 844368 | 19/01/2022 | 19/01/2022 | JAL JEEVAN MISSION WEST BENGAL ESCROW AC | 11.53 | 0 | 0 | 0
7 | HOOGHLY |  | Hooghly Division | RETROFITTING WORKS FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) WITHIN THE COMMAND AREA OF PASCHIM JOYKRISHNAPUR WATER SUPPLY | SM/07954 | Retrofitting | Construction of 3.6 m X 3.0 m Switch Room with Sanitary and Water Supply arrangement, Boundary Wall in Proposed T.W Site, Laying rising main pipe for inter connection between T.W & Distribution For Source Augmentation of PASCHIM JAYKRISHNAPUR Piped Water Supply Scheme under Chandannagar Sub-Division of Hooghly Division P.HE Dte. within HARIPAL Block. | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/000131/2023-2024 | 1474/HUG | 19/05/2023 | 18/06/2023 | S.B. ENTERPRISE | 11.8 | 0 | 0 | 80
8 | HOOGHLY |  | Hooghly Division | RETROFITTING WORKS FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) WITHIN THE COMMAND AREA OF PASCHIM JOYKRISHNAPUR WATER SUPPLY | SM/07954 | Retrofitting | Designing making and erection of Display Board using logo and tag line of Jal Jeevan Mission to the placed at different work sites and HGJ villages for awareness generation among the people in the district of Hooghly under Chandannagar Sub Division under Hooghly Division PHE Dte.(Paschim Jaykrishnapur PWSS, Kaikala PWSS, Bandipur PWSS, Bamonjol PWSS, Binagram PWSS, Rambati PWSS). | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/000979/2023-2024 | 307/Chan | 15/03/2024 | 22/03/2024 | AMBIAN INFRASTRUCTURE | 0.95 | 0 | 0 | 100
9 | HOOGHLY |  | Hooghly Division | RETROFITTING WORKS FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) WITHIN THE COMMAND AREA OF PASCHIM JOYKRISHNAPUR WATER SUPPLY | SM/07954 | Retrofitting | Reparing of Damage Pipeline at Paschim Jaykrishnapur Water Supply Scheme Under chandannagar Sub-Division under Hooghly Division,P.H.E Dte . | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/000951/2023-2024 | 289/Chan | 15/03/2024 | 30/03/2024 | AMBIAN INFRASTRUCTURE | 0.57 | 0 | 0 | 100
10 | HOOGHLY |  | Hooghly Division | RETROFITTING WORKS FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) WITHIN THE COMMAND AREA OF PASCHIM JOYKRISHNAPUR WATER SUPPLY | SM/07954 | Retrofitting | Making of 2 nos 1.8m X 1.45m X 2.1m KIOSK at Gouribati 3rd T/W site & Paschim Joykrishnapur (Zone-1) 3rd T/W Site under Chandannagar Sub-Division PHE Dte. | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/000935/2023-2024 | 280/Chan | 15/03/2024 | 30/03/2024 | SUDIPTA SINHA | 0.88 | 0 | 0 | 100
11 | HOOGHLY |  | Hooghly Division | RETROFITTING WORKS FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) WITHIN THE COMMAND AREA OF PASCHIM JOYKRISHNAPUR WATER SUPPLY | SM/07954 | Retrofitting | Providing F.H.T.C in leftout portion of Dignagar and adjacent areas of Paschim Joykrishnapur water supply scheme under Chandannagar Sub-Division P.H.E. Dte. | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/001548/2024-2025 | 321/HUG | 05/02/2025 | 07/03/2025 | WELFARE ENGINEER'S CO - OPERATIVE SOCIETY LTD | 11.38 | 0 | 0 | 100
Total | [13 empty] | 249.52 | 0 | 0