## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | HOOGHLY |  | Hooghly Division | RETROFITTING WORKS FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) WITHIN THE COMMAND AREA OF EKTARPUR WATER SUPPLY SCHEME. | SM/07955 | Retrofitting | FHTC |  |  | VCH/001049/2021-2022 |  | 30/09/2021 | 30/09/2021 | BISHALAXMI ENTERPRISE (DIPAK SINGHA ROY) | 27.03 | 0 | 0 | 0
2 | HOOGHLY |  | Hooghly Division | RETROFITTING WORKS FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) WITHIN THE COMMAND AREA OF EKTARPUR WATER SUPPLY SCHEME. | SM/07955 | Retrofitting | Providing 310 nos Functional Household Tap Connection (FHTC) within the command area of EKTARPUR Water Supply Scheme Under Chinsurah Sub-Division of Hooghly Division P.H.E Dte | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/000357/2021-2022 | 118/Hug | 19/01/2022 | 08/02/2022 | YOUNG ENGINEERS CO-OPERATIVE SOCIETY LTD. | 22.53 | 0 | 0 | 100
3 | HOOGHLY |  | Hooghly Division | RETROFITTING WORKS FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) WITHIN THE COMMAND AREA OF EKTARPUR WATER SUPPLY SCHEME. | SM/07955 | Retrofitting | Providing 1338 nos F.H.T.C. in Dwarpara, Beleswar& Basna Village of Ektarpur and its Adjoining Mouzas Water Supply Scheme Under Chinsurah Sub-Division of Hooghly Division P.H.E Dte. [Block-Balagarh] | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/000006/2021-2022 | 937/Hug | 06/05/2021 | 15/06/2021 | BISHALAXMI ENTERPRISE (DIPAK SINGHA ROY) | 77.59 | 0 | 0 | 100
4 | HOOGHLY |  | Hooghly Division | RETROFITTING WORKS FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) WITHIN THE COMMAND AREA OF EKTARPUR WATER SUPPLY SCHEME. | SM/07955 | Retrofitting | Providing 780 nos Functional Household Tap Connection (FHTC) within the command area of EKTARPUR Water Supply Scheme Under Chinsurah Sub-Division of Hooghly Division P.H.E Dte | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/000440/2021-2022 | 458/Hug | 10/03/2022 | 19/04/2022 | MAA TARA CONSTRUCTION | 52.71 | 0 | 0 | 100
5 | HOOGHLY |  | Hooghly Division | RETROFITTING WORKS FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) WITHIN THE COMMAND AREA OF EKTARPUR WATER SUPPLY SCHEME. | SM/07955 | Retrofitting | Material Requisition To Resource Division |  |  | RTOR000061/2021-2022 | 2097/1/Hug | 26/11/2021 | 26/11/2021 | Resource Division | 0.83 | 0 | 0 | 0
Total | [13 empty] | 180.69 | 0 | 0