## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | HOOGHLY |  | Hooghly Division | RETROFITTING WORKS FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) WITHIN THE COMMAND AREA OF KULTEGHARI WATER SUPPLY SCHEME. | SM/07956 | Retrofitting | FHTC |  |  | VCH/000848/2021-2022 |  | 21/09/2021 | 21/09/2021 | M/S RAJKUMAR KHAN | 23.52 | 0 | 0 | 0
2 | HOOGHLY |  | Hooghly Division | RETROFITTING WORKS FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) WITHIN THE COMMAND AREA OF KULTEGHARI WATER SUPPLY SCHEME. | SM/07956 | Retrofitting | FHTC |  |  | VCH/001042/2021-2022 |  | 30/09/2021 | 30/09/2021 | M/S S.G. CONSTRUCTION | 18.9 | 0 | 0 | 0
3 | HOOGHLY |  | Hooghly Division | RETROFITTING WORKS FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) WITHIN THE COMMAND AREA OF KULTEGHARI WATER SUPPLY SCHEME. | SM/07956 | Retrofitting | FHTC |  |  | VCH/000534/2021-2022 |  | 23/07/2021 | 23/07/2021 | M/S RAJKUMAR KHAN | 32.53 | 0 | 0 | 0
4 | HOOGHLY |  | Hooghly Division | RETROFITTING WORKS FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) WITHIN THE COMMAND AREA OF KULTEGHARI WATER SUPPLY SCHEME. | SM/07956 | Retrofitting | FHTC |  |  | VCH/000593/2021-2022 |  | 17/08/2021 | 17/08/2021 | M/S S.G. CONSTRUCTION | 34.67 | 0 | 0 | 0
5 | HOOGHLY |  | Hooghly Division | RETROFITTING WORKS FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) WITHIN THE COMMAND AREA OF KULTEGHARI WATER SUPPLY SCHEME. | SM/07956 | Retrofitting | FHTC |  |  | VCH/000519/2021-2022 |  | 23/07/2021 | 23/07/2021 | M/S RAJKUMAR KHAN | 32.53 | 0 | 0 | 0
6 | HOOGHLY |  | Hooghly Division | RETROFITTING WORKS FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) WITHIN THE COMMAND AREA OF KULTEGHARI WATER SUPPLY SCHEME. | SM/07956 | Retrofitting | Material Requisition To Resource Division |  |  | RTOR000134/2022-2023 | 2686/1/Hug | 01/12/2022 | 01/12/2022 | Resource Division | 0.34 | 0 | 0 | 0
7 | HOOGHLY |  | Hooghly Division | RETROFITTING WORKS FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) WITHIN THE COMMAND AREA OF KULTEGHARI WATER SUPPLY SCHEME. | SM/07956 | Retrofitting | FHTC |  |  | VCH/002111/2021-2022 |  | 28/01/2022 | 28/01/2022 | M/S S.G. CONSTRUCTION | 20 | 0 | 0 | 0
8 | HOOGHLY |  | Hooghly Division | RETROFITTING WORKS FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) WITHIN THE COMMAND AREA OF KULTEGHARI WATER SUPPLY SCHEME. | SM/07956 | Retrofitting | Providing Functional Household Tap Connection (FHTC) under JJM within left out portion of Tullyan, Keshabchak, Kulteghari, Mohanbati Mouza in KULTEGHORI PWSS, Block Tarakeswar under Chandannagar Sub-Division of Hooghly Division P.H.E Dte. | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/000593/2022-2023 | 2852/HUG | 16/12/2022 | 15/01/2023 | S K ENTERPRISE | 14.97 | 14.45 | 96.52 | 100
9 | HOOGHLY |  | Hooghly Division | RETROFITTING WORKS FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) WITHIN THE COMMAND AREA OF KULTEGHARI WATER SUPPLY SCHEME. | SM/07956 | Retrofitting | Material Requisition To Resource Division |  |  | RTOR000037/2021-2022 | 2098/1/Hug | 26/11/2021 | 26/11/2021 | Resource Division | 0.83 | 0 | 0 | 0
10 | HOOGHLY |  | Hooghly Division | RETROFITTING WORKS FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) WITHIN THE COMMAND AREA OF KULTEGHARI WATER SUPPLY SCHEME. | SM/07956 | Retrofitting | Repairing of boundary wall at old 1st tubewell site of Kulteghari PWSS Scheme under Chandannagar Sub-Division, PHE Dte. | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/000271/2025-2026 | 917/CHAN | 21/07/2025 | 10/08/2025 | M/S RAJKUMAR KHAN | 4.17 | 0 | 0 | 0
11 | HOOGHLY |  | Hooghly Division | RETROFITTING WORKS FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) WITHIN THE COMMAND AREA OF KULTEGHARI WATER SUPPLY SCHEME. | SM/07956 | Retrofitting | Road restoration at Kultegori water supply scheme under Chandannagar Sub-Division P.H.E. Dte. (Part B) | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/000217/2025-2026 | 865/CHAN | 21/07/2025 | 10/08/2025 | R.K. TRADERS | 4.79 | 0 | 0 | 90
12 | HOOGHLY |  | Hooghly Division | RETROFITTING WORKS FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) WITHIN THE COMMAND AREA OF KULTEGHARI WATER SUPPLY SCHEME. | SM/07956 | Retrofitting | Road restoration at Kultegori water supply scheme under Chandannagar Sub-Division P.H.E. Dte. (Part C) | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/000218/2025-2026 | 866/CHAN | 21/07/2025 | 10/08/2025 | JOY GURU ENTERPRISE | 4.89 | 0 | 0 | 50
13 | HOOGHLY |  | Hooghly Division | RETROFITTING WORKS FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) WITHIN THE COMMAND AREA OF KULTEGHARI WATER SUPPLY SCHEME. | SM/07956 | Retrofitting | Road restoration at Kultegori water supply scheme under Chandannagar Sub-Division P.H.E. Dte. (Part A) | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/000216/2025-2026 | 864/CHAN | 22/07/2025 | 11/08/2025 | TOTON MONDAL | 4.88 | 0 | 0 | 50
14 | HOOGHLY |  | Hooghly Division | RETROFITTING WORKS FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) WITHIN THE COMMAND AREA OF KULTEGHARI WATER SUPPLY SCHEME. | SM/07956 | Retrofitting | Special repairing of Laying Distribution System including Rising main, FHTC & other essential components of Kulteghari W/S Scheme under Chandannagar Sub-Division P.H.E.Dte. | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/000239/2025-2026 | 890/CHAN | 21/07/2025 | 10/08/2025 | M/S RAJKUMAR KHAN | 4.97 | 0 | 0 | 100
15 | HOOGHLY |  | Hooghly Division | RETROFITTING WORKS FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) WITHIN THE COMMAND AREA OF KULTEGHARI WATER SUPPLY SCHEME. | SM/07956 | Retrofitting | Repairing of pump house at 1St and 2nd TW site of Kulteghari PWSS under Chandannagar Sub-Division, PHE Dte. | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/000289/2025-2026 | 922/CHAN | 21/07/2025 | 10/08/2025 | MAHABIR CONSTRUCTION | 4.39 | 0 | 0 | 100
Total | [13 empty] | 206.38 | 14.45 | 7