## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | HOOGHLY |  | Hooghly Division | RETROFITTING WORKS FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) WITHIN THE COMMAND AREA OF BAHADURPUR WATER SUPPLY SCHEME. | SM/07958 | Retrofitting | Providing 1599 nos F.H.T.C. in Bahadurpur, Belmuri,Manikpur, Radha Ballabhpur & Uttar Mogalpur Village of Bahadurpur and its Adjoining Mouzas Water Supply Scheme UnderChinsurah Sub-Division of Hooghly Division P.H.E Dte. [Block-Dhaniakhali] | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/000002/2021-2022 | 933/Hug | 06/05/2021 | 15/06/2021 | ORIENT CONSTRUCTION | 92.76 | 69.85 | 75.3 | 100
2 | HOOGHLY |  | Hooghly Division | RETROFITTING WORKS FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) WITHIN THE COMMAND AREA OF BAHADURPUR WATER SUPPLY SCHEME. | SM/07958 | Retrofitting | Material Requisition To Resource Division |  |  | RTOR000080/2021-2022 | 2097/20/Hug | 26/11/2021 | 26/11/2021 | Resource Division | 0.83 | 0 | 0 | 0
3 | HOOGHLY |  | Hooghly Division | RETROFITTING WORKS FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) WITHIN THE COMMAND AREA OF BAHADURPUR WATER SUPPLY SCHEME. | SM/07958 | Retrofitting | Providing Functional Household Tap Connection (FHTC) under JJM within left out Mouzas / Habitations of different PWSS under DHANIAKHALI Block of CHINSURAH Sub-Division of Hooghly Division P.H.E Dte. | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/000340/2023-2024 | 2430/HUG | 11/08/2023 | 10/09/2023 | MUKHERJEE AND CO | 39.91 | 39.29 | 98.46 | 98
Total | [13 empty] | 133.49 | 109.14 | 81.75