## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | HOOGHLY |  | Hooghly Division | RETROFITTING WORKS FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) WITHIN THE COMMAND AREA OF SAOTA WATER SUPPLY SCHEME. | SM/08737 | Retrofitting | FHTC |  |  | VCH/000942/2021-2022 |  | 24/09/2021 | 24/09/2021 | SOUMYADIP DE | 44.16 | 0 | 0 | 0
2 | HOOGHLY |  | Hooghly Division | RETROFITTING WORKS FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) WITHIN THE COMMAND AREA OF SAOTA WATER SUPPLY SCHEME. | SM/08737 | Retrofitting | Providing 550 nos Functional Household Tap Connection (FHTC) within the left out Mouzas of SAOTA Water Supply Scheme Under Arambag Sub-Division of Hooghly Division P.H.E Dte | Assistant Engineer | Junior Engineer (Civill) | ORD/000098/2022-2023 | 1090/Hug | 03/06/2022 | 03/07/2022 | MESSRS FREEDOM CONSTRUCTION | 30.73 | 0 | 0 | 100
Total | [13 empty] | 74.89 | 0 | 0