## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | HOOGHLY |  | Hooghly Division | RETROFITTING WORKS FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) WITHIN THE COMMAND AREA OF BAIKUNTHAPUR WATER SUPPLY SCHEME. | SM/08738 | Retrofitting | Survey & Collection of Data through mobile app regarding availability of drinking water sanitation & others prarameters in primary schools, anganwari Centers. | Assistant Engineer | Junior Engineer (Civill) | ORD/000487/2021-2022 | 564/CH | 02/12/2021 | 14/12/2021 | R.K. TRADERS | 3.64 | 0 | 0 | 100
2 | HOOGHLY |  | Hooghly Division | RETROFITTING WORKS FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) WITHIN THE COMMAND AREA OF BAIKUNTHAPUR WATER SUPPLY SCHEME. | SM/08738 | Retrofitting | Providing 111 nos. Functional Household Tap Connection (F.H.T.C) with extention of pipeline at Adak Para, Dulepara & Bagpara Habitation of Baikunthapur Mouza of BAIKUNTHAPUR Water Supply Scheme under Arambagh Sub-Division of Hooghly Division P.H.E. Dte. [Block-Pursurah]. | Assistant Engineer | Junior Engineer (Civill) | ORD/000357/2022-2023 | 615/Arg | 30/08/2022 | 19/09/2022 | TANISA ENTERPRISE | 4.47 | 0 | 0 | 100
3 | HOOGHLY |  | Hooghly Division | RETROFITTING WORKS FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) WITHIN THE COMMAND AREA OF BAIKUNTHAPUR WATER SUPPLY SCHEME. | SM/08738 | Retrofitting | Providing 112 nos. Functional Household Tap Connection (F.H.T.C) with extention of pipeline at Mallickpara, Palpara & Janapara Habitation of Baikunthapur Mouza of BAIKUNTHAPUR Water Supply Scheme under Arambagh Sub-Division of Hooghly Division P.H.E. Dte. [Block-Pursurah]. | Assistant Engineer | Junior Engineer (Civill) | ORD/000358/2022-2023 | 616/Arg | 31/08/2022 | 20/09/2022 | TANISA ENTERPRISE | 4.5 | 0 | 0 | 100
4 | HOOGHLY |  | Hooghly Division | RETROFITTING WORKS FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) WITHIN THE COMMAND AREA OF BAIKUNTHAPUR WATER SUPPLY SCHEME. | SM/08738 | Retrofitting | Providing 111 nos. Functional Household Tap Connection (F.H.T.C) with extention of pipeline at Adak Para, Dulepara & Bagpara Habitation of Baikunthapur Mouza of BAIKUNTHAPUR Water Supply Scheme under Arambagh Sub-Division of Hooghly Division P.H.E. Dte. [Block-Pursurah]. | Assistant Engineer | Junior Engineer (Civill) | ORD/000360/2022-2023 | 615/Arg | 31/08/2022 | 20/09/2022 | TANISA ENTERPRISE | 4.47 | 0 | 0 | 100
5 | HOOGHLY |  | Hooghly Division | RETROFITTING WORKS FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) WITHIN THE COMMAND AREA OF BAIKUNTHAPUR WATER SUPPLY SCHEME. | SM/08738 | Retrofitting | Providing 1950 nos F.H.T.C. in Baikunthapur Village of Baikunthapur and its Adjoining Mouzas Water Supply Scheme Under Arambagh Sub-Division of Hooghly Division P.H.E Dte. [Block-Pursurah] | Assistant Engineer | Junior Engineer (Civill) | ORD/000004/2021-2022 | 935/Hug | 06/05/2021 | 15/06/2021 | PRADIP KUMAR ADHYA | 96.28 | 0 | 0 | 100
6 | HOOGHLY |  | Hooghly Division | RETROFITTING WORKS FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) WITHIN THE COMMAND AREA OF BAIKUNTHAPUR WATER SUPPLY SCHEME. | SM/08738 | Retrofitting | Providing 325 nos Functional Household Tap Connection (FHTC) with extension of pipeline at Baikunthapur Water Supply Scheme Under Arambagh Sub-Division of Hooghly Division P.H.E Dte. [Block-Pursurah] | Assistant Engineer | Junior Engineer (Civill) | ORD/000075/2023-2024 | 1309/HUG | 10/05/2023 | 09/06/2023 | TANISA ENTERPRISE | 20.47 | 0 | 0 | 100
Total | [13 empty] | 133.84 | 0 | 0