## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | HOOGHLY |  | Hooghly Division | RETROFITTING WORKS FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) WITHIN THE COMMAND AREA OF PALASPAI WATER SUPPLY SCHEME. | SM/08739 | Retrofitting | FHTC |  |  | VCH/001030/2021-2022 |  | 30/09/2021 | 30/09/2021 | KARALI MOHAN KHAMRUI | 42.88 | 0 | 0 | 0
2 | HOOGHLY |  | Hooghly Division | RETROFITTING WORKS FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) WITHIN THE COMMAND AREA OF PALASPAI WATER SUPPLY SCHEME. | SM/08739 | Retrofitting | Providing 1102 nos F.H.T.C. in Daulat chak, Khune chak & Chanpanagari Village of Palaspai and its Adjoining Mouzas Water Supply Scheme Under Arambagh Sub-Division of Hooghly Division P.H.E Dte. [Block-Khanakul-II] | Assistant Engineer | Junior Engineer (Civill) | ORD/000012/2021-2022 | 943/Hug | 06/05/2021 | 15/06/2021 | DILIP KUMAR GHOSH | 63.84 | 23.44 | 36.71 | 100
3 | HOOGHLY |  | Hooghly Division | RETROFITTING WORKS FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) WITHIN THE COMMAND AREA OF PALASPAI WATER SUPPLY SCHEME. | SM/08739 | Retrofitting | Providing 1670 nos F.H.T.C. in Narendapur & Palaspai Village of Palapai and its Adjoining Mouzas Water Supply Scheme Under Arambagh Sub-Division of Hooghly Division P.H.E Dte. [Block-Khanakul-II] | Assistant Engineer | Junior Engineer (Civill) | ORD/000083/2021-2022 | 1149/Hug | 29/06/2021 | 08/08/2021 | KARALI MOHAN KHAMRUI | 81.69 | 78.4 | 95.97 | 100
4 | HOOGHLY |  | Hooghly Division | RETROFITTING WORKS FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) WITHIN THE COMMAND AREA OF PALASPAI WATER SUPPLY SCHEME. | SM/08739 | Retrofitting | Repair and Renovation Works of R.C.C. Elevated Reservoir, Boundary Wall, Switch Room & Construction of Internal Pathway of PALASPAI PWSS under Arambagh Sub-Division of Hooghly Division, P.H.E. Dte. |  |  | ORD/000452/2024-2025 | 4079/HUG | 19/12/2024 | 19/03/2025 | TAPAS ADHYA | 26.94 | 0 | 0 | 0
5 | HOOGHLY |  | Hooghly Division | RETROFITTING WORKS FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) WITHIN THE COMMAND AREA OF PALASPAI WATER SUPPLY SCHEME. | SM/08739 | Retrofitting | Designing making and erection of Display Board using logo and tag line of Jal Jeevan Mission to the placed at different work sites and HGJ villages for awareness generation among the people in the district of Hooghly under ARAMBAGH Sub-Division under Hooghly Division PHE Dte. (i) PALASPAI PWSS (ii) SABALSINGHAPUR PWSS (iii) CHINGRA (ZONE- I) PWSS (iv) CHINGRA (ZONE- II) PWSS (v) HAYATPUR PWSS (vi) PRATAPNAGAR PWSS | Assistant Engineer | Junior Engineer (Civill) | ORD/000441/2024-2025 | 802/Arg | 23/08/2024 | 30/08/2024 | LIMRA SOCIAL WELFARE SOCIETY | 0.95 | 0 | 0 | 100
6 | HOOGHLY |  | Hooghly Division | RETROFITTING WORKS FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) WITHIN THE COMMAND AREA OF PALASPAI WATER SUPPLY SCHEME. | SM/08739 | Retrofitting | Preparation of DPR for Augmentation of Palaspai Piped Water Supply Scheme under Arambagh Sub - Division of Hooghly Division, P.H.E. Dte. | Assistant Engineer |  | ORD/001294/2025-2026 | 680/Arg | 31/07/2025 | 31/08/2025 | APEX ENGINEERING | 0.78 | 0 | 0 | 0
7 | HOOGHLY |  | Hooghly Division | RETROFITTING WORKS FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) WITHIN THE COMMAND AREA OF PALASPAI WATER SUPPLY SCHEME. | SM/08739 | Retrofitting | Preparation of CAD-GIS Drawing and Pipe Network Design for Augmentation of Palaspai Piped Water Supply Scheme under Arambagh Sub - Division of Hooghly Division, P.H.E. Dte. | Assistant Engineer |  | ORD/001293/2025-2026 | 679/Arg | 31/07/2025 | 31/08/2025 | APEX ENGINEERING | 0.84 | 0 | 0 | 0
8 | HOOGHLY |  | Hooghly Division | RETROFITTING WORKS FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) WITHIN THE COMMAND AREA OF PALASPAI WATER SUPPLY SCHEME. | SM/08739 | Retrofitting | Route Survey for Augmentation of Palaspai Piped Water Supply Scheme under Arambagh Sub - Division of Hooghly Division, P.H.E. Dte. (Part-A) | Assistant Engineer |  | ORD/001295/2025-2026 | 681/Arg | 31/07/2025 | 31/08/2025 | APEX ENGINEERING | 0.73 | 0 | 0 | 0
9 | HOOGHLY |  | Hooghly Division | RETROFITTING WORKS FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) WITHIN THE COMMAND AREA OF PALASPAI WATER SUPPLY SCHEME. | SM/08739 | Retrofitting | Route Survey for Augmentation of Palaspai Piped Water Supply Scheme under Arambagh Sub - Division of Hooghly Division, P.H.E. Dte. (Part-B) | Assistant Engineer |  | ORD/001296/2025-2026 | 682/Arg | 31/07/2025 | 31/08/2025 | APEX ENGINEERING | 0.95 | 0 | 0 | 0
10 | HOOGHLY |  | Hooghly Division | RETROFITTING WORKS FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) WITHIN THE COMMAND AREA OF PALASPAI WATER SUPPLY SCHEME. | SM/08739 | Retrofitting | Route Survey for Augmentation of Palaspai Piped Water Supply Scheme under Arambagh Sub - Division of Hooghly Division, P.H.E. Dte. (Part-C) | Assistant Engineer |  | ORD/001297/2025-2026 | 683/Arg | 31/07/2025 | 31/08/2025 | APEX ENGINEERING | 0.95 | 0 | 0 | 0
Total | [13 empty] | 220.55 | 101.84 | 46.17