## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | HOOGHLY |  | Hooghly Division | RETROFITTING WORKS FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) WITHIN THE COMMAND AREA OF PALASPAI WATER SUPPLY SCHEME. | SM/08739 | Retrofitting | FHTC |  |  | VCH/001030/2021-2022 |  | 30/09/2021 | 30/09/2021 | KARALI MOHAN KHAMRUI | 42.88 | 0 | 0 | 0
2 | HOOGHLY |  | Hooghly Division | RETROFITTING WORKS FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) WITHIN THE COMMAND AREA OF PALASPAI WATER SUPPLY SCHEME. | SM/08739 | Retrofitting | Providing 1102 nos F.H.T.C. in Daulat chak, Khune chak & Chanpanagari Village of Palaspai and its Adjoining Mouzas Water Supply Scheme Under Arambagh Sub-Division of Hooghly Division P.H.E Dte. [Block-Khanakul-II] | Assistant Engineer | Junior Engineer (Civill) | ORD/000012/2021-2022 | 943/Hug | 06/05/2021 | 15/06/2021 | DILIP KUMAR GHOSH | 63.84 | 23.44 | 36.71 | 100
3 | HOOGHLY |  | Hooghly Division | RETROFITTING WORKS FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) WITHIN THE COMMAND AREA OF PALASPAI WATER SUPPLY SCHEME. | SM/08739 | Retrofitting | Providing 1670 nos F.H.T.C. in Narendapur & Palaspai Village of Palapai and its Adjoining Mouzas Water Supply Scheme Under Arambagh Sub-Division of Hooghly Division P.H.E Dte. [Block-Khanakul-II] | Assistant Engineer | Junior Engineer (Civill) | ORD/000083/2021-2022 | 1149/Hug | 29/06/2021 | 08/08/2021 | KARALI MOHAN KHAMRUI | 81.69 | 78.4 | 95.97 | 100
4 | HOOGHLY |  | Hooghly Division | RETROFITTING WORKS FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) WITHIN THE COMMAND AREA OF PALASPAI WATER SUPPLY SCHEME. | SM/08739 | Retrofitting | Repair and Renovation Works of R.C.C. Elevated Reservoir, Boundary Wall, Switch Room & Construction of Internal Pathway of PALASPAI PWSS under Arambagh Sub-Division of Hooghly Division, P.H.E. Dte. |  |  | ORD/000452/2024-2025 | 4079/HUG | 19/12/2024 | 19/03/2025 | TAPAS ADHYA | 26.94 | 0 | 0 | 0
Total | [13 empty] | 215.35 | 101.84 | 47.29