## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | HOOGHLY |  | Hooghly Division | RETROFITTING WORKS FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) WITHIN THE COMMAND AREA OF KAIKALA WATER SUPPLY SCHEME. | SM/08740 | Retrofitting | FHTC |  |  | VCH/000852/2021-2022 |  | 21/09/2021 | 21/09/2021 | SATYA NARAYAN BISWAS | 20.9 | 0 | 0 | 0
2 | HOOGHLY |  | Hooghly Division | RETROFITTING WORKS FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) WITHIN THE COMMAND AREA OF KAIKALA WATER SUPPLY SCHEME. | SM/08740 | Retrofitting | FHTC |  |  | VCH/001040/2021-2022 |  | 30/09/2021 | 30/09/2021 | SIKHA ENTERPRISE | 4.58 | 0 | 0 | 0
3 | HOOGHLY |  | Hooghly Division | RETROFITTING WORKS FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) WITHIN THE COMMAND AREA OF KAIKALA WATER SUPPLY SCHEME. | SM/08740 | Retrofitting | FHTC |  |  | VCH/001041/2021-2022 |  | 30/09/2021 | 30/09/2021 | BRISTI CONSTRUCTION | 4.58 | 0 | 0 | 0
4 | HOOGHLY |  | Hooghly Division | RETROFITTING WORKS FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) WITHIN THE COMMAND AREA OF KAIKALA WATER SUPPLY SCHEME. | SM/08740 | Retrofitting | FHTC |  |  | VCH/001039/2021-2022 |  | 30/09/2021 | 30/09/2021 | SURAJIT SINGHA RAY | 5.04 | 0 | 0 | 0
5 | HOOGHLY |  | Hooghly Division | RETROFITTING WORKS FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) WITHIN THE COMMAND AREA OF KAIKALA WATER SUPPLY SCHEME. | SM/08740 | Retrofitting | FHTC |  |  | VCH/001037/2021-2022 |  | 30/09/2021 | 30/09/2021 | SATYA NARAYAN BISWAS | 9.09 | 0 | 0 | 0
6 | HOOGHLY |  | Hooghly Division | RETROFITTING WORKS FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) WITHIN THE COMMAND AREA OF KAIKALA WATER SUPPLY SCHEME. | SM/08740 | Retrofitting | Providing 1634 nos F.H.T.C. in Baladbandha ,Basudebpur, Kaikala & Baramba Village of Kaikala Zone-II and its Adjoining Mouzas Water Supply Scheme Under Chandannagar Sub-Division of Hooghly Division P.H.E Dte. [Block-Haripal] | Assistant Engineer (Civil) |  | ORD/000561/2021-2022 | 1147/HUG | 29/06/2021 | 08/08/2021 | SATYA NARAYAN BISWAS | 72.55 | 0 | 0 | 100
7 | HOOGHLY |  | Hooghly Division | RETROFITTING WORKS FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) WITHIN THE COMMAND AREA OF KAIKALA WATER SUPPLY SCHEME. | SM/08740 | Retrofitting | FHTC |  |  | VCH/002110/2021-2022 |  | 28/01/2022 | 28/01/2022 | SWASTIK ENTERPRISE | 5.1 | 0 | 0 | 0
8 | HOOGHLY |  | Hooghly Division | RETROFITTING WORKS FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) WITHIN THE COMMAND AREA OF KAIKALA WATER SUPPLY SCHEME. | SM/08740 | Retrofitting | Providing 1634 nos F.H.T.C. in Baladbandha ,Basudebpur, Kaikala & Baramba Village of Kaikala Zone-II and its Adjoining Mouzas Water Supply Scheme Under Chandannagar Sub-Division of Hooghly Division P.H.E Dte. [Block-Haripal] | Assistant Engineer (Civil) |  | ORD/000081/2021-2022 | 1147/Hug | 29/06/2021 | 08/08/2021 | SATYA NARAYAN BISWAS | 72.55 | 0 | 0 | 100
9 | HOOGHLY |  | Hooghly Division | RETROFITTING WORKS FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) WITHIN THE COMMAND AREA OF KAIKALA WATER SUPPLY SCHEME. | SM/08740 | Retrofitting | Providing 91 nos. tap connection at Ichapur mouza of Kaikala water supply scheme under Chandannagar Sub-Division, P.H.E. Dte. to make it "SWAJAL VILLAGE" | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/000353/2021-2022 | 14/chan | 05/01/2022 | 25/01/2022 | SWASTIK ENTERPRISE | 5 | 0 | 0 | 100
10 | HOOGHLY |  | Hooghly Division | RETROFITTING WORKS FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) WITHIN THE COMMAND AREA OF KAIKALA WATER SUPPLY SCHEME. | SM/08740 | Retrofitting | Providing balance 81 nos F.H.T.C. in Baladbandh village of kaikala Zone-1 and its adjoining mouzas water supply scheme under Chandannagar Sub-Division, P.H.E. Dte. | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/000123/2021-2022 | 354/chan | 16/08/2021 | 05/09/2021 | MGM ENTERPRISE | 4.93 | 0 | 0 | 100
11 | HOOGHLY |  | Hooghly Division | RETROFITTING WORKS FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) WITHIN THE COMMAND AREA OF KAIKALA WATER SUPPLY SCHEME. | SM/08740 | Retrofitting | Construction of Boundary Wall and Laying of rising main at 3rd Tubewell site of KAIKALA Water Supply Scheme under Hooghly Division, PHE Dte. | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/000079/2022-2023 | 210/chan | 13/04/2022 | 13/05/2022 | SWASTIK ENTERPRISE | 5 | 0 | 0 | 0
12 | HOOGHLY |  | Hooghly Division | RETROFITTING WORKS FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) WITHIN THE COMMAND AREA OF KAIKALA WATER SUPPLY SCHEME. | SM/08740 | Retrofitting | Providing F.H.T.C in leftout portion of Choutara, Basudebpur, Baladbandh, Baramba, Ichapur, Kaikala village of Kaikala Zone-II and its adjoining mouzas water supply scheme under Chandannagar Sub-Division P.H.E. Dte. [Block-Haripal] of Hooghly Division P.H.E Dte. | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/000386/2022-2023 | 2139/HUG | 26/09/2022 | 10/11/2022 | MALLIKA ENTERPRISE | 63.68 | 0 | 0 | 100
Total | [13 empty] | 272.99 | 0 | 0