## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | HOOGHLY |  | Hooghly Division | RETROFITTING WORKS FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) WITHIN THE COMMAND AREA OF GOURHATI WATER SUPPLY SCHEME. | SM/08742 | Retrofitting | Providing 350 nos Functional Household Tap Connection (FHTC) within the command area of Gourhati Water Supply Scheme Under Arambagh Sub-Division of Hooghly Division P.H.E Dte. [Block-Arambagh] | Assistant Engineer | Junior Engineer (Civill) | ORD/000014/2022-2023 | 715/Hug | 07/04/2022 | 07/05/2022 | TULIP ENGINEERS CO-OPERATIVE SOCIETY LTD. | 16.57 | 12.35 | 74.56 | 100
2 | HOOGHLY |  | Hooghly Division | RETROFITTING WORKS FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) WITHIN THE COMMAND AREA OF GOURHATI WATER SUPPLY SCHEME. | SM/08742 | Retrofitting | Providing 300 nos Functional Household Tap Connection (FHTC) within the command area of GOURHATI Water Supply Scheme Under Arambag Sub-Division of Hooghly Division P.H.E Dte | Assistant Engineer | Junior Engineer (Civill) | ORD/000445/2021-2022 | 463/Hug | 10/03/2022 | 30/03/2022 | ZENITH CONSTRUCTION | 18.73 | 16.44 | 87.75 | 40
3 | HOOGHLY |  | Hooghly Division | RETROFITTING WORKS FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) WITHIN THE COMMAND AREA OF GOURHATI WATER SUPPLY SCHEME. | SM/08742 | Retrofitting | Providing 1050 nos Functional Household Tap Connection (FHTC) within the command area (left out portion) of Gourhati Water Supply Scheme Under Arambagh Sub-Division of Hooghly Division P.H.E Dte | Assistant Engineer | Junior Engineer (Civill) | ORD/000273/2021-2022 | 2127/Hug | 01/12/2021 | 10/01/2022 | DILIP KUMAR GHOSH | 36.01 | 43.58 | 121 | 100
4 | HOOGHLY |  | Hooghly Division | RETROFITTING WORKS FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) WITHIN THE COMMAND AREA OF GOURHATI WATER SUPPLY SCHEME. | SM/08742 | Retrofitting | Material Requisition To Resource Division |  |  | RTOR000166/2021-2022 | 427/2-2/Hug | 07/03/2022 | 07/03/2022 | Resource Division | 10.43 | 0 | 0 | 0
Total | [13 empty] | 81.74 | 72.36 | 88.53