## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | HOOGHLY |  | Hooghly Division | RETROFITTING WORKS FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) WITHIN THE COMMAND AREA OF BAIDYAPUR WATER SUPPLY SCHEME. | SM/08743 | Retrofitting | FHTC |  |  | VCH/002108/2021-2022 |  | 28/01/2022 | 28/01/2022 | SARKAR CONSTRUCTION | 7.5 | 0 | 0 | 0
2 | HOOGHLY |  | Hooghly Division | RETROFITTING WORKS FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) WITHIN THE COMMAND AREA OF BAIDYAPUR WATER SUPPLY SCHEME. | SM/08743 | Retrofitting | Providing 224 nos Functional Household Tap Connection (FHTC) within the command area of Baidyapur Water Supply Scheme at Basudebpur Mouza Under Chandannagar Sub-Division of Hooghly Division P.H.E Dte | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/000126/2021-2022 | 1444/Hug | 23/08/2021 | 22/09/2021 | SARKAR CONSTRUCTION | 22.35 | 7.43 | 33.26 | 100
3 | HOOGHLY |  | Hooghly Division | RETROFITTING WORKS FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) WITHIN THE COMMAND AREA OF BAIDYAPUR WATER SUPPLY SCHEME. | SM/08743 | Retrofitting | PROVIDING 94 NOS. FHTC IN MIRZAPUR VILLAGE OF BAIDYAPUR AND ITS ADJ MOUZAS PWSS | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/000461/2020-2021 | 89/CHAN | 15/02/2021 | 17/03/2021 | TAPAS ADHYA | 4.62 | 1.55 | 33.55 | 100
4 | HOOGHLY |  | Hooghly Division | RETROFITTING WORKS FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) WITHIN THE COMMAND AREA OF BAIDYAPUR WATER SUPPLY SCHEME. | SM/08743 | Retrofitting | Repair and Renovation Works of R.C.C. Elevated Reservoir of BAIDYAPUR PWSS under Chandannagar Sub-Division of Hooghly Division, P.H.E. Dte. |  |  | ORD/000456/2024-2025 | 4075/HUG | 19/12/2024 | 19/03/2025 | BIMAL KUMAR HALDER | 9.23 | 0 | 0 | 0
5 | HOOGHLY |  | Hooghly Division | RETROFITTING WORKS FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) WITHIN THE COMMAND AREA OF BAIDYAPUR WATER SUPPLY SCHEME. | SM/08743 | Retrofitting | Designing making and erection of Display Board using logo and tag line of Jal Jeevan Mission to the placed at different work sites and HGJ villages for awareness generation among the people in the district of Hooghly under Chandannagar Sub Division under Hooghly Division PHE Dte.(Baidyapur PWSS,Madpur PWSS,Ghosha PWSS). | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/000981/2023-2024 | 309/chan | 15/03/2024 | 22/03/2024 | AMBIAN INFRASTRUCTURE | 0.48 | 0.48 | 100 | 100
6 | HOOGHLY |  | Hooghly Division | RETROFITTING WORKS FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) WITHIN THE COMMAND AREA OF BAIDYAPUR WATER SUPPLY SCHEME. | SM/08743 | Retrofitting | Providing F.H.T.C in leftout portion and construction of boundary wall at head work site and 3rd tubewell site, laying pumping main at 3rd tubewell site of Baidyapur water supply scheme under Chandannagar Sub-Division of Hooghly Division P.H.E Dte | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/000221/2024-2025 | 3430/HUG | 03/10/2024 | 03/08/2025 | BAPPADITYA BANERJEE | 65.68 | 0 | 0 | 50
7 | HOOGHLY |  | Hooghly Division | RETROFITTING WORKS FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) WITHIN THE COMMAND AREA OF BAIDYAPUR WATER SUPPLY SCHEME. | SM/08743 | Retrofitting | Special repairing of Laying Distribution System including Rising main, FHTC & other essential components of Baidyapur W/S Scheme under Chandannagar Sub-Division P.H.E.Dte. | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/000238/2025-2026 | 889/CHAN | 21/07/2025 | 10/08/2025 | SWASTIK ENTERPRISE | 4.97 | 0 | 0 | 100
8 | HOOGHLY |  | Hooghly Division | RETROFITTING WORKS FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) WITHIN THE COMMAND AREA OF BAIDYAPUR WATER SUPPLY SCHEME. | SM/08743 | Retrofitting | QUOTATION BILL FOR THE BAIDYAPUR W/S/SCH |  |  | BILL/01005/2023-2024 | BP-2023-24-699 | 29/12/2023 | 29/12/2023 | EXECUTIVE ENGINEER, ELECTRICAL DIVISION, PHE DTE | 30.35 | 0 | 0 | 0
Total | [13 empty] | 145.17 | 9.46 | 6.52