## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | HOOGHLY |  | Hooghly Division | Drinking water sample collection & testing through Filed Test Kits (FTKs) & uploading charges for the same related to Water Quality Monitoring & Surveillance Programme. | SM/08967 | Support-WQMSP | Supply and Delivery Chemicals of 09 nos. Water Testing Laboratories under Hooghly District under Hooghly Division, P.H.E. Dte. | Assistant Engineer(HQ) |  | ORD/000629/2022-2023 | 304/HQ/HUG | 30/12/2022 | 09/01/2023 | LAB SOLUTION | 0.86 | 0.86 | 100 | 0
2 | HOOGHLY |  | Hooghly Division | Drinking water sample collection & testing through Filed Test Kits (FTKs) & uploading charges for the same related to Water Quality Monitoring & Surveillance Programme. | SM/08967 | Support-WQMSP | Supply and Delivery Chemicals of 09 nos. Water Testing Laboratories under Hooghly District under Hooghly Division, P.H.E. Dte. | Assistant Engineer(HQ) |  | ORD/000628/2022-2023 | 305/HQ/HUG | 30/12/2022 | 09/01/2023 | LAB SOLUTION | 0.86 | 0.86 | 100 | 0
3 | HOOGHLY |  | Hooghly Division | Drinking water sample collection & testing through Filed Test Kits (FTKs) & uploading charges for the same related to Water Quality Monitoring & Surveillance Programme. | SM/08967 | Support-WQMSP | Supply and Delivery Chemicals of 09 nos. Water Testing Laboratories under Hooghly District under Hooghly Division, P.H.E. Dte. | Assistant Engineer(HQ) |  | ORD/000630/2022-2023 | 306/HQ/HUG | 30/12/2022 | 09/01/2023 | LAB SOLUTION | 0.86 | 0.86 | 100 | 0
Total | [13 empty] | 2.58 | 2.58 | 100