## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | HOOGHLY | Haripal | Central Drilling | Chandanpur Piped Water Supply Scheme. | SM/08995 | New | SINKING OF TUBE WELL (250MM X 150MM X 250 MTRS DEPTH) BY DEPARTMENTAL RIG MACHINE FOR CHANDANPUR W/S SCHEME TARAKESWAR BLOCK, UNDER HOOGHLY DISTRICT, CDD, PHE DTE. |  |  | ORD/000215/2021-2022 | 1295/CDD | 17/02/2022 | 19/03/2022 | C.M. ENTERPRISE | 11.21 | 10.17 | 90.79 | 100
2 | HOOGHLY | Haripal | Central Drilling | Chandanpur Piped Water Supply Scheme. | SM/08995 | New | PROVIDING DRILLING CREW AND OTHER ALLIED WORKS FOR CONSTRUCTION OF TUBE WELL (300MM X 200MM X 210 MTRS DEPTH) BY UTILIZING DEPARTMENTAL MACHINERIES FOR BANDIPUR W/S SCHEME (TW-II), HARIPAL BLOCK UNDER HOOGHLY DISTRICT, CDD, PHE DTE. | Driller In Charge | Junior Engineer | ORD/000143/2022-2023 | 300/CDD | 27/04/2022 | 27/05/2022 | PADMA ENGINEERING & CO. | 12.84 | 11.6 | 90.32 | 100
3 | HOOGHLY | Haripal | Central Drilling | Chandanpur Piped Water Supply Scheme. | SM/08995 | New | SINKING OF TUBE WELL (250MM X 150MM X 250 MTRS DEPTH) BY UTILIZING RIG MACHINE FOR CHANDANPUR W/S SCHEME UNDER HOOGHLY DISTRICT, CDD, PHE DTE. |  |  | ORD/000257/2021-2022 | 1294/CDD | 17/02/2022 | 19/03/2022 | C.M. ENTERPRISE | 11.21 | 9.2 | 82.09 | 90
4 | HOOGHLY | Haripal | Hooghly Division | Chandanpur Piped Water Supply Scheme. | SM/08995 | New | QUOTATION BILL ON ACCOUNT OF WBSEDCL FOR THE CHANDANPUR W/S/S |  |  | BILL/00057/2022-2023 |  | 12/12/2022 | 12/12/2022 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 1.64 | 0 | 0 | 0
5 | HOOGHLY | Haripal | Hooghly Division | Chandanpur Piped Water Supply Scheme. | SM/08995 | New | WBSEDCL PAYMENT FROM ELECTRICAL DIVISION,PHE DTE. |  |  | VCH/001031/2022-2023 | C092248441540 | 27/09/2022 | 27/09/2022 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 9.43 | 0 | 0 | 0
6 | HOOGHLY | Haripal | Electrical | Chandanpur Piped Water Supply Scheme. | SM/08995 | New | Supply, delivery & installation of submersible pumping machinery and other electrical / mechanical equipments etc. including allied works for Chandanpur water supply scheme, T.W. No. I, Block: Haripal, District - Hooghly under Electrical Division, PHE Dte. |  |  | ORD/000242/2022-2023 | 2044/ED | 01/12/2022 | 01/03/2023 | R.N.S. TRADING | 10.29 | 0 | 0 | 0
7 | HOOGHLY | Haripal | Hooghly Division | Chandanpur Piped Water Supply Scheme. | SM/08995 | New | Baseline household survey work including collection of House Hold Details at Prescribed Format through Mobile App/Hard Copy for yearly data updation in JJM portal at HARIPAL Block under Chandannagar Sub-Division, P.H.E. Dte. | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/000088/2022-2023 | 220/chan | 13/04/2022 | 03/05/2022 | M/S S.G. CONSTRUCTION | 4.98 | 0 | 0 | 100
8 | HOOGHLY | Haripal | Central Drilling | Chandanpur Piped Water Supply Scheme. | SM/08995 | New | PROVIDING DRILLING CREWS FOR CONSTRUCTION OF TUBEWELL BY DEPARTMENTAL RIG MACHINE AT AMODGHATA W/S SCH TW-II, POLBA DADPUR BLOCK, HOOGHLY DISTRICT UNDER CMSD-II (D), CDD, PHE DTE. | Driller In Charge | Junior Engineer | ORD/000367/2022-2023 | 377/CMSD-II | 01/08/2022 | 16/08/2022 | C.M. ENTERPRISE | 2.93 | 2.63 | 89.7 | 0
9 | HOOGHLY | Haripal | Hooghly Division | Chandanpur Piped Water Supply Scheme. | SM/08995 | New | Jack pushing / Horizontal direct drilling along Railway land and below Railway track for laying 600 mm dia M.S Casing Pipe,150 mm dia M.S Carrier Pipe through in between Mast no 40/1057-40/29 & 49/29A-40/30A on HWH-BWN (Chord) Section Chandanpur to Porabazar Station for Chandanpur Piped Water Supply Scheme Under Chandannagar Sub-Division of Hooghly Division P.H.E Dte. | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/000343/2023-2024 | 2432/HUG | 11/08/2023 | 10/10/2023 | WELFARE ENGINEER'S CO - OPERATIVE SOCIETY LTD | 37.98 | 37.82 | 99.57 | 98
10 | HOOGHLY | Haripal | Hooghly Division | Chandanpur Piped Water Supply Scheme. | SM/08995 | New | Material Requisition To Resource Division |  |  | RTOR000041/2022-2023 | 1370/4/Hug | 06/07/2022 | 06/07/2022 | Resource Division | 24.77 | 0 | 0 | 0
11 | HOOGHLY | Haripal | Hooghly Division | Chandanpur Piped Water Supply Scheme. | SM/08995 | New | Material Requisition To Resource Division |  |  | RTOR000234/2022-2023 | 109/ 17/Hug | 10/01/2023 | 10/01/2023 | Resource Division | 23.6 | 0 | 0 | 0
12 | HOOGHLY | Haripal | Hooghly Division | Chandanpur Piped Water Supply Scheme. | SM/08995 | New | Material Requisition To Resource Division |  |  | RTOR000271/2023-2024 | 1383/23/Hug | 15/05/2023 | 15/05/2023 | Resource Division | 3.45 | 0 | 0 | 0
13 | HOOGHLY | Haripal | Hooghly Division | Chandanpur Piped Water Supply Scheme. | SM/08995 | New | PAYMENT FOR QUOTATION BILL TO WBSEDCL FOR CHANDANPUR WATER SUPPLY SCHEME UNDER CHANDANNAGORE SUB-DIVISION, PHE DTE. BILL WAS ALREADY SUBMITTED BY THE EXECUTIVE ENGINEER, HOOGHLY DIVISION, PHE DTE. |  |  | BILL/00140/2022-2023 | BP-2022-23-471 | 18/01/2023 | 18/01/2023 | EXECUTIVE ENGINEER, ELECTRICAL DIVISION, PHE DTE | 2.4 | 0 | 0 | 0
14 | HOOGHLY | Haripal | Hooghly Division | Chandanpur Piped Water Supply Scheme. | SM/08995 | New | Way leave Facility Charges |  |  | BILL/00199/2022-2023 | BP-2022-23-529 | 02/02/2023 | 02/02/2023 | EASTERN RAILWAY HOWRAH DIVISION | 6.78 | 0 | 0 | 0
15 | HOOGHLY | Haripal | Hooghly Division | Chandanpur Piped Water Supply Scheme. | SM/08995 | New | PAYMENT IN RESPECT OF WBSEDCL TO THE ELECTRICAL DIVISION, PHE DTE. FOR THE CHANDANPUR W/S/SCH |  |  | BILL/00122/2023-2024 | BP-2023-24-98 | 26/05/2023 | 26/05/2023 | EXECUTIVE ENGINEER, ELECTRICAL DIVISION, PHE DTE | 19.19 | 0 | 0 | 0
16 | HOOGHLY | Haripal | Hooghly Division | Chandanpur Piped Water Supply Scheme. | SM/08995 | New | WBSEDCL |  |  | BILL/00029/2022-2023 | BP-2022-23-414 | 20/12/2022 | 20/12/2022 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 1.64 | 0 | 0 | 0
17 | HOOGHLY | Haripal | Hooghly Division | Chandanpur Piped Water Supply Scheme. | SM/08995 | New | HIRE CHARGES BILL FOR THE ASSISTANT ENGINEER, CHANDANNAGORE SUB-DIVISION, PHE DTE. |  |  | BILL/00258/2022-2023 | BP-2022-23-570 | 03/03/2023 | 03/03/2023 | GOUR KUMAR DAS | 1.29 | 0 | 0 | 0
18 | HOOGHLY | Haripal | Electrical | Chandanpur Piped Water Supply Scheme. | SM/08995 | New | Supply, delivery & installation of submersible pumping machinery and other electrical / mechanical equipments etc. including allied works for Chandanpur water supply scheme, T.W. No. II, Block: Haripal, District- Hooghly under Electrical Division, PHE Dte. | Assistant Engineer Howrah mechanical Sub Division | Junior Engineer4 | ORD/001223/2022-2023 | 1319/ED | 17/08/2022 | 15/11/2022 | ANJAN ENTERPRISE | 9.78 | 0 | 0 | 100
19 | HOOGHLY | Haripal | Hooghly Division | Chandanpur Piped Water Supply Scheme. | SM/08995 | New | Laying Extra D.I Pipe for Interconnection Between OHR, Head work T.W &, 2nd t.w & allied works for Chandandanpur W/S Scheme under Chandannagar Sub - Division, PHE Dte. | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/000349/2023-2024 | 2441/HUG | 12/08/2023 | 30/10/2024 | WELFARE ENGINEER'S CO - OPERATIVE SOCIETY LTD | 56.42 | 25.62 | 45.41 | 52
20 | HOOGHLY | Haripal | Hooghly Division | Chandanpur Piped Water Supply Scheme. | SM/08995 | New | Construction of 1 no. 250 CUM capacity R.C.C. Elevated Reservoir with 20 m staging height Over R.C.C Bored Pile Foundation/Raft Foundation as per Departmental Type Drawing Design and Specification including pipeline connection and cost of pipes, specials, and Soil Investigation works for construction of OHR and Laying Distribution System, Laying CI/D.I pipes & specials for Rising Main pipe line in between T.W NO.-I & II to OHR and interconnection with distribution system including allied work, Construction of 1 No 5.9 M X 4.1 M Switch Room with Sanitary and Water Supply Arrangements, Construction of 1 no 4.10M x 3.5M Switch Room without Sanitary & Water Supply arrangement at 2nd T/W Site including Providing 1105 nos, FHTC in Chandanpur Water Supply Scheme of HARIPAL BLOCK under CHANDANNAGAR Sub-Division of Hooghly Division, P.H.E. Dte., Dist. Hooghly. | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/000186/2022-2023 | 1606/Hug | 05/08/2022 | 04/10/2024 | WELFARE ENGINEER'S CO - OPERATIVE SOCIETY LTD | 278.64 | 234.7 | 84.23 | 70
Total | [13 empty] | 530.46 | 331.74 | 62.54