## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | HOOGHLY |  | Hooghly Division | Repairing damages caused by Cyclonic Storm AMPHAN to various Piped Water Supply Scheme under Hooghly Division, PHE Dte. | SM/09025 | Disaster | Repairing of Office Floor, Roof, main gate, painting of Boundary Wall, pump room etc. of Serampore Sub Division Office cum Head Work Site under Serampore Sub Division PHE Dte. (PHASE-II) | Assistant Engineer (Civil) |  | ORD/000486/2021-2022 | 129/SER | 10/09/2021 | 10/10/2021 | DHIRENDRA ENGINEERING & CONSTRUCTION | 3.62 | 0 | 0 | 0
2 | HOOGHLY |  | Hooghly Division | Repairing damages caused by Cyclonic Storm AMPHAN to various Piped Water Supply Scheme under Hooghly Division, PHE Dte. | SM/09025 | Disaster | LAYING OF PIPELINE |  |  | VCH/002095/2021-2022 |  | 28/01/2022 | 28/01/2022 | P.B. ENTERPRISE (PINTU BHADURI) | 6.42 | 0 | 0 | 0
3 | HOOGHLY |  | Hooghly Division | Repairing damages caused by Cyclonic Storm AMPHAN to various Piped Water Supply Scheme under Hooghly Division, PHE Dte. | SM/09025 | Disaster | Transportation charge for carriage and distribution of 300 ml. drinking Water Pouch packet from MTU placed at Arambagh, Khanakul to flood affected zone of Arambagh, Khanakul-I, Khanakul-II, Goghat-I & Pursurah Block during flood including loading, unloading and distribution considering flood like situation (August-2021). | Assistant Engineer |  | ORD/000393/2021-2022 | 326/Arg | 02/08/2021 | 05/08/2021 | M/S TANISA ENTERPRISE | 11.14 | 0 | 0 | 0
4 | HOOGHLY |  | Hooghly Division | Repairing damages caused by Cyclonic Storm AMPHAN to various Piped Water Supply Scheme under Hooghly Division, PHE Dte. | SM/09025 | Disaster | Repairing Work of O.H.R, Switch Room, Boundary Wall of Head Work & Spiral Stair Case of O.H.R. at Furfura water supply scheme under Serampore Sub-Division, P.H.E. Dte. (Damaged during AMPHAN) | Assistant Engineer (Civil) |  | ORD/000418/2021-2022 | 308/SER | 24/02/2022 | 26/03/2022 | COMPAQ ENGINEER'S CO - OPERATIVE SOCIETY LTD | 4.3 | 0 | 0 | 0
5 | HOOGHLY |  | Hooghly Division | Repairing damages caused by Cyclonic Storm AMPHAN to various Piped Water Supply Scheme under Hooghly Division, PHE Dte. | SM/09025 | Disaster | Disinfection of spot sources of 36 nos. DWP / Mark-II and 164 nos. Ordinary tube well for flood situation at Khanakul-II Blocks under RWS Hooghly Sub-Divison under Hooghly Division, P.H.E. Dte. | Assistant Engineer (Civil) |  | ORD/000580/2021-2022 | 911/RWS | 07/08/2021 | 12/08/2021 | TANISA ENTERPRISE | 0.48 | 0 | 0 | 0
6 | HOOGHLY |  | Hooghly Division | Repairing damages caused by Cyclonic Storm AMPHAN to various Piped Water Supply Scheme under Hooghly Division, PHE Dte. | SM/09025 | Disaster | DISINFECTION OF SPOT SOURCES OF 36NOS. DWP/ MARK - II AND 164 NOS. ORDINARY TUBE WELL FOR FLOOD SITUATION AT KHANAKUL-II BLOCKS UNDER RWS HOOGHLY SUB-DIVISION, P.H.E DTE. (PHASE - II) | Assistant Engineer (Civil) |  | ORD/000581/2021-2022 | 1000/hug | 01/10/2021 | 06/10/2021 | TANISA ENTERPRISE | 0.47 | 0 | 0 | 0
7 | HOOGHLY |  | Hooghly Division | Repairing damages caused by Cyclonic Storm AMPHAN to various Piped Water Supply Scheme under Hooghly Division, PHE Dte. | SM/09025 | Disaster | DISINFECTION OF SPOT SOURCES OF 28NOS. DWP/ MARK - II AND 134 NOS. QRDINARY TUBE WELL FOR FLOOD SITUATION AT ARAMBAGH , GOGHAT - I & II AND KHANAKUL I & II BLOCKS UNDER RWS HOOGHLY SUB-DIVISION, P.H.E DTE. (PHASE - II) | Assistant Engineer (Civil) |  | ORD/000627/2022-2023 | 314/D/HUG | 07/01/2023 | 12/01/2023 | ROY ENTERPRISE | 3.92 | 0 | 0 | 0
8 | HOOGHLY |  | Hooghly Division | Repairing damages caused by Cyclonic Storm AMPHAN to various Piped Water Supply Scheme under Hooghly Division, PHE Dte. | SM/09025 | Disaster | Repairing work of O.H.R. and allied works of Boundary Wall, Gate, Pump room etc. at PURBATAJPUR water supply scheme due to damages caused by Super Cyclone "AMPHAN" Under Serampore Sub-Division of Hooghly Division, P.H.E. Dte. | Assistant Engineer (Civil) |  | ORD/000234/2021-2022 | 1919/Hug | 27/10/2021 | 26/11/2021 | A.M. ENTERPRISE | 6.79 | 0 | 0 | 0
9 | HOOGHLY |  | Hooghly Division | Repairing damages caused by Cyclonic Storm AMPHAN to various Piped Water Supply Scheme under Hooghly Division, PHE Dte. | SM/09025 | Disaster | Distribution of Water Pouch at flood affected areas of Khanakul-I, Khanakul-II, Pursurah, Arambagh, and Goghat-I Block under Arambagh Sub-Division of Hooghly Division PHE Dte., Dist. Hooghly. (Aug-2021) | Assistant Engineer |  | ORD/000434/2021-2022 | 336/Arg | 06/08/2021 | 09/08/2021 | M/S TANISA ENTERPRISE | 4.07 | 0 | 0 | 0
10 | HOOGHLY |  | Hooghly Division | Repairing damages caused by Cyclonic Storm AMPHAN to various Piped Water Supply Scheme under Hooghly Division, PHE Dte. | SM/09025 | Disaster | Relaying of UPVC pipes & specials damaged during AMPHAN with construction of 12 nos. Street Standpost for Chanditala W/S Scheme under Serampore Sub - Division P.H.E. Dte. | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/000416/2021-2022 | 306/SER | 24/02/2022 | 16/03/2022 | M/S SHIVAM UDYOG | 1.7 | 0 | 0 | 0
11 | HOOGHLY |  | Hooghly Division | Repairing damages caused by Cyclonic Storm AMPHAN to various Piped Water Supply Scheme under Hooghly Division, PHE Dte. | SM/09025 | Disaster | Restoration of Flood damaged portion of KAKNAN Water Supply Scheme under Arambagh Sub-Division, P.H.E. Dte., Dist. Hooghly. [ Block-Khanakul-II] | Assistant Engineer | Junior Engineer (Civill) | ORD/000393/2022-2023 | 620/Arg | 01/09/2022 | 16/09/2022 | TITAS CONSTRUCTION | 4.98 | 0 | 0 | 0
12 | HOOGHLY |  | Hooghly Division | Repairing damages caused by Cyclonic Storm AMPHAN to various Piped Water Supply Scheme under Hooghly Division, PHE Dte. | SM/09025 | Disaster | Restoration of Flood damaged portion of LAKSHMIPUR & BALI Water Supply Scheme under Arambagh Sub-Division, P.H.E. Dte., Dist. Hooghly. [ Block-Goghat-I] | Assistant Engineer | Junior Engineer (Civill) | ORD/000426/2022-2023 | 727/Arg | 29/09/2022 | 14/10/2022 | DHIRENDRA ENGINEERING & CONSTRUCTION | 2.23 | 0 | 0 | 0
13 | HOOGHLY |  | Hooghly Division | Repairing damages caused by Cyclonic Storm AMPHAN to various Piped Water Supply Scheme under Hooghly Division, PHE Dte. | SM/09025 | Disaster | Restoration of Flood damaged portion of KISHORPUR Water Supply Scheme under Arambagh Sub-Division, P.H.E. Dte., Dist. Hooghly. [ Block-Khanakul-I] | Assistant Engineer |  | ORD/000392/2022-2023 | 617/Arg | 01/09/2022 | 16/09/2022 | TITAS CONSTRUCTION | 4.84 | 0 | 0 | 0
14 | HOOGHLY |  | Hooghly Division | Repairing damages caused by Cyclonic Storm AMPHAN to various Piped Water Supply Scheme under Hooghly Division, PHE Dte. | SM/09025 | Disaster | Connection of Over Flow to the Discharge for the Pratapnagar, Gobindapur & Purbaraypur W/S Scheme under Arambagh Sub-Division P.H.E. Dte. | Assistant Engineer | Junior Engineer (Civill) | ORD/000396/2022-2023 | 622/Arg | 01/09/2022 | 16/09/2022 | TITAS CONSTRUCTION | 3.73 | 0 | 0 | 0
15 | HOOGHLY |  | Hooghly Division | Repairing damages caused by Cyclonic Storm AMPHAN to various Piped Water Supply Scheme under Hooghly Division, PHE Dte. | SM/09025 | Disaster | Restoration of Flood damaged portion of GHORADAHA Water Supply Scheme under Arambagh Sub-Division, P.H.E. Dte., Dist. Hooghly. [ Block-Khanakul-II] PART-B | Assistant Engineer | Junior Engineer (Civill) | ORD/000398/2022-2023 | 619/Arg | 01/09/2022 | 16/09/2022 | TITAS CONSTRUCTION | 4.92 | 0 | 0 | 0
16 | HOOGHLY |  | Hooghly Division | Repairing damages caused by Cyclonic Storm AMPHAN to various Piped Water Supply Scheme under Hooghly Division, PHE Dte. | SM/09025 | Disaster | DISINFECTION OF SPOT SOURCES OF 28NOS. DWP/ MARK - II AND 134 NOS. QRDINARY TUBE WELL FOR FLOOD SITUATION AT ARAMBAGH , GOGHAT - I & II AND KHANAKUL I & II BLOCKS UNDER RWS HOOGHLY SUB-DIVISION, P.H.E DTE. (PHASE - II) | Assistant Engineer (Civil) |  | ORD/000579/2021-2022 | 1823/HUG | 01/10/2021 | 06/10/2021 | ROY ENTERPRISE | 3.92 | 0 | 0 | 0
17 | HOOGHLY |  | Hooghly Division | Repairing damages caused by Cyclonic Storm AMPHAN to various Piped Water Supply Scheme under Hooghly Division, PHE Dte. | SM/09025 | Disaster | DISINFECTION OF SPOT SOURCES OF 243 NOS. DWP/ MARK - II AND 1107 NOS. QRDINARY TUBE WELL FOR FLOOD SITUATION AT KHANAKUL-I & II BLOCKS UNDER RWS HOOGHLY SUB-DIVISION, P.H.E DTE. (PHASE - I) | Assistant Engineer (Civil) |  | ORD/000582/2021-2022 | 1817/HUG | 01/10/2021 | 06/10/2021 | HAZRA CONSTRUCTION | 3.2 | 0 | 0 | 0
18 | HOOGHLY |  | Hooghly Division | Repairing damages caused by Cyclonic Storm AMPHAN to various Piped Water Supply Scheme under Hooghly Division, PHE Dte. | SM/09025 | Disaster | Connection of Over Flow to the Discharge for the Arandi & Kishorpur W/S Scheme under Arambagh Sub-Division P.H.E. Dte. | Assistant Engineer | Junior Engineer (Civill) | ORD/000394/2022-2023 | 621/Arg | 01/09/2022 | 16/09/2022 | TITAS CONSTRUCTION | 3.85 | 0 | 0 | 0
19 | HOOGHLY |  | Hooghly Division | Repairing damages caused by Cyclonic Storm AMPHAN to various Piped Water Supply Scheme under Hooghly Division, PHE Dte. | SM/09025 | Disaster | Restoration of Flood damaged portion of GHORADAHA Water Supply Scheme under Arambagh Sub-Division, P.H.E. Dte., Dist. Hooghly. [ Block-Khanakul-II] PART-A | Assistant Engineer | Junior Engineer (Civill) | ORD/000397/2022-2023 | 618/Arg | 01/09/2022 | 16/09/2022 | TITAS CONSTRUCTION | 2.73 | 0 | 0 | 0
20 | HOOGHLY |  | Hooghly Division | Repairing damages caused by Cyclonic Storm AMPHAN to various Piped Water Supply Scheme under Hooghly Division, PHE Dte. | SM/09025 | Disaster | DISINFECTION OF SPOT SOURCES OF 28NOS. DWP/ MARK - II AND 134 NOS. QRDINARY TUBE WELL FOR FLOOD SITUATION AT JANGIPARA, ARAMBAGH & RARAKESWAR BLOCKS UNDER RWS HOOGHLY SUB-DIVISION, P.H.E DTE. (PHASE - I) | Assistant Engineer (Civil) |  | ORD/000576/2021-2022 | 1358/HUG | 07/08/2021 | 12/08/2021 | ARUN SEAL AND CO. | 0.38 | 0 | 0 | 0
21 | HOOGHLY |  | Hooghly Division | Repairing damages caused by Cyclonic Storm AMPHAN to various Piped Water Supply Scheme under Hooghly Division, PHE Dte. | SM/09025 | Disaster | DISINFECTION OF SPOT SOURCES OF 28NOS. DWP/ MARK - II AND 134 NOS. QRDINARY TUBE WELL FOR FLOOD SITUATION AT KHANAKUL - I & II BLOCKS UNDER RWS HOOGHLY SUB-DIVISION, P.H.E DTE. (PHASE - II) | Assistant Engineer (Civil) |  | ORD/000577/2021-2022 | 1824/HUG | 01/10/2021 | 06/10/2021 | M/S RAJKUMAR KHAN | 2.5 | 0 | 0 | 0
22 | HOOGHLY |  | Hooghly Division | Repairing damages caused by Cyclonic Storm AMPHAN to various Piped Water Supply Scheme under Hooghly Division, PHE Dte. | SM/09025 | Disaster | DISINFECTION OF SPOT SOURCES OF 28NOS. DWP/ MARK - II AND 134 NOS. QRDINARY TUBE WELL FOR FLOOD SITUATION AT GOGHAT - I & II, KHANAKUL - I & II, BLOCKS UNDER RWS HOOGHLY SUB-DIVISION, P.H.E DTE. (PHASE - I) | Assistant Engineer (Civil) |  | ORD/000578/2021-2022 | 1359/HUG | 07/08/2021 | 12/08/2021 | TITAS CONSTRUCTION | 3.8 | 0 | 0 | 0
23 | HOOGHLY |  | Hooghly Division | Repairing damages caused by Cyclonic Storm AMPHAN to various Piped Water Supply Scheme under Hooghly Division, PHE Dte. | SM/09025 | Disaster | DISINFECTION OF SPOT SOURCES OF 216 NOS. DWP/ MARK - II AND 983 NOS. QRDINARY TUBE WELL FOR FLOOD SITUATION AT KHANAKUL - I & II BLOCKS UNDER RWS HOOGHLY SUB-DIVISION, P.H.E DTE. (PHASE - II) | Assistant Engineer (Civil) |  | ORD/000583/2021-2022 | 1816/HUG | 01/10/2021 | 06/10/2021 | M/S PRADYUT KUMAR HAZRA | 2.84 | 0 | 0 | 0
24 | HOOGHLY |  | Hooghly Division | Repairing damages caused by Cyclonic Storm AMPHAN to various Piped Water Supply Scheme under Hooghly Division, PHE Dte. | SM/09025 | Disaster | Disinfection of spot sources of 36 nos. DWP / Mark-II and 164 nos. Ordinary tube well for flood situation at Khanakul-II Blocks under RWS Hooghly Sub-Divison under Hooghly Division, P.H.E. Dte. | Assistant Engineer (Civil) |  | ORD/000584/2021-2022 | 1370/HUG | 07/08/2021 | 12/08/2021 | TANISA ENTERPRISE | 0.48 | 0 | 0 | 0
25 | HOOGHLY |  | Hooghly Division | Repairing damages caused by Cyclonic Storm AMPHAN to various Piped Water Supply Scheme under Hooghly Division, PHE Dte. | SM/09025 | Disaster | Disinfection of spot sources of 112 nos. DWP / Mark-II and 507 nos. Ordinary tubewell for flood situation at Khanakul-II Blocks under RWS Hooghly Sub-Division under Hooghly Division, P.H.E. Dte. | Assistant Engineer (Civil) |  | ORD/000586/2021-2022 | 1369/HUG | 09/08/2021 | 16/08/2021 | DILIP KUMAR GHOSH | 1.47 | 0 | 0 | 0
26 | HOOGHLY |  | Hooghly Division | Repairing damages caused by Cyclonic Storm AMPHAN to various Piped Water Supply Scheme under Hooghly Division, PHE Dte. | SM/09025 | Disaster | Disinfection of spot sources of 124 nos. DWP / Mark-II and 563 nos. Ordinary tubewell for flood situation at Khanakul-II Blocks under RWS Hooghly Sub-Division under Hooghly Division, P.H.E. Dte. [Phase - II] | Assistant Engineer (Civil) |  | ORD/000587/2021-2022 | 1838/HUG | 04/10/2021 | 09/10/2021 | GLOBAL CONSTRUCTION | 1.63 | 0 | 0 | 0
27 | HOOGHLY |  | Hooghly Division | Repairing damages caused by Cyclonic Storm AMPHAN to various Piped Water Supply Scheme under Hooghly Division, PHE Dte. | SM/09025 | Disaster | DISINFECTION OF SPOT SOURCES OF 36NOS. DWP/ MARK - II AND 164 NOS. ORDINARY TUBE WELL FOR FLOOD SITUATION AT KHANAKUL-II BLOCKS UNDER RWS HOOGHLY SUB-DIVISION, P.H.E DTE. (PHASE - II) | Assistant Engineer (Civil) |  | ORD/000585/2021-2022 | 1815/hug | 01/10/2021 | 06/10/2021 | TANISA ENTERPRISE | 0.47 | 0 | 0 | 0
Total | [13 empty] | 90.91 | 0 | 0