## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | HOOGHLY |  | Hooghly Division | Retrofitting works for providing Functional Household Tap Connection within the command area of BACHHANARI W/S Scheme | SM/09066 | Retrofitting | Providing 145 nos Functional Household Tap Connection (FHTC) within the command area of BACHHANARI Water Supply Scheme Under ARAMBAG Sub-Division of Hooghly Division P.H.E Dte. | Assistant Engineer | Junior Engineer (Civill) | ORD/000337/2021-2022 | 14/Hug | 04/01/2022 | 24/01/2022 | ROY ENTERPRISE | 6.02 | 6.02 | 100.04 | 100
2 | HOOGHLY |  | Hooghly Division | Retrofitting works for providing Functional Household Tap Connection within the command area of BACHHANARI W/S Scheme | SM/09066 | Retrofitting | Construction of 3.6 m X 3.00 m Switch Room with Additional Plinth Height, without Sanitary and Water Supply arrangement at 3rd TW Site of BACHHANARI W/S Scheme under Arambagh Sub-Division P.H.E. Dte. | Assistant Engineer | Junior Engineer (Civill) | ORD/000414/2021-2022 | 52/Arg | 31/01/2022 | 17/03/2022 | S. B. CONSTRUCTION | 3.43 | 2.75 | 80.36 | 100
3 | HOOGHLY |  | Hooghly Division | Retrofitting works for providing Functional Household Tap Connection within the command area of BACHHANARI W/S Scheme | SM/09066 | Retrofitting | Hiring of well maintained Diesel Motor Cab for the office of the Executive Engineer, Hooghly Division PHE Dte. | Assistant Engineer,Assistant Engineer(HQ) | Junior Engineer (Civill) | ORD/000556/2021-2022 | 148/HQHUG | 30/12/2021 | 30/12/2022 | PRADIP KUMAR ADHYA | 1.25 | 1.25 | 100 | 100
4 | HOOGHLY |  | Hooghly Division | Retrofitting works for providing Functional Household Tap Connection within the command area of BACHHANARI W/S Scheme | SM/09066 | Retrofitting | Construction of approach road at 3rd Tube Well site of Bachhanari Piped Water Supply Scheme under Arambagh Sub-Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer (Civill) | ORD/000570/2021-2022 | 215/ARG | 31/03/2022 | 07/04/2022 | KARALI MOHAN KHAMRUI | 1.32 | 1.3 | 98.03 | 100
5 | HOOGHLY |  | Central Drilling | Retrofitting works for providing Functional Household Tap Connection within the command area of BACHHANARI W/S Scheme | SM/09066 | Retrofitting | SUPPLY AND DELIVERY OF COTTON WASTE AND OTHER MATERIALS FOR DRILLING WORK AT BACHHANARI PWSS DISTRICT HOOGHLY AND OTHER PWSS UNDER CDD, PHE DTE. |  |  | ORD/000191/2022-2023 | 256/CMSD-I | 23/06/2022 | 08/07/2022 | M/S PRACHI ENGINEERING | 1.92 | 0 | 0 | 100
6 | HOOGHLY |  | Central Drilling | Retrofitting works for providing Functional Household Tap Connection within the command area of BACHHANARI W/S Scheme | SM/09066 | Retrofitting | PROVIDING DRILLING CREWS INCLUDING ALLIED MATERIALS FOR CONSTRUCTION OF TUBE WELL (250MM X 150MM) BY KORES RIG MACHINE UNDER CMSD-II, CDD, PHE DTE. |  |  | ORD/000195/2021-2022 | 644/ CDD | 28/09/2021 | 28/10/2021 | PADMA ENGINEERING & CO. | 11.2 | 8.36 | 74.63 | 100
7 | HOOGHLY |  | Hooghly Division | Retrofitting works for providing Functional Household Tap Connection within the command area of BACHHANARI W/S Scheme | SM/09066 | Retrofitting | FHTC |  |  | VCH/002104/2021-2022 |  | 28/01/2022 | 28/01/2022 | M/S SHIVAM UDYOG | 19.5 | 0 | 0 | 0
8 | HOOGHLY |  | Hooghly Division | Retrofitting works for providing Functional Household Tap Connection within the command area of BACHHANARI W/S Scheme | SM/09066 | Retrofitting | Providing 450 nos F.H.T.C. in Bachhanari and its Adjoining Mouzas Water Supply Scheme Under Arambagh Sub-Division of Hooghly Division P.H.E Dte.[Block-Arambagh] | Assistant Engineer | Junior Engineer (Civill) | ORD/000248/2020-2021 | 250/Hug | 03/02/2021 | 05/03/2021 | PRADIP KUMAR ADHYA | 30.31 | 5.22 | 17.23 | 100
9 | HOOGHLY |  | Hooghly Division | Retrofitting works for providing Functional Household Tap Connection within the command area of BACHHANARI W/S Scheme | SM/09066 | Retrofitting | Providing 145 nos Functional Household Tap Connection (FHTC) within the command area of Bachhanari Water Supply Scheme Under Arambagh Sub-Division of Hooghly Division P.H.E Dte | Assistant Engineer | Junior Engineer (Civill) | ORD/000231/2021-2022 | 1916/Hug | 27/10/2021 | 16/11/2021 | ROY ENTERPRISE | 8.38 | 8.28 | 98.8 | 100
10 | HOOGHLY |  | Central Drilling | Retrofitting works for providing Functional Household Tap Connection within the command area of BACHHANARI W/S Scheme | SM/09066 | Retrofitting | Supply & delivery of Cotton Waste and other materials for drilling work at Bachanari PWSS, District Hooghly and other PWSS under Central Drilling Division, PHE Dte. | Driller In Charge | Junior Engineer | ORD/000148/2023-2024 | 256/CMSD-I | 23/06/2023 | 08/07/2023 | DEV ENTERPRISE | 1.46 | 0 | 0 | 0
11 | HOOGHLY |  | Central Drilling | Retrofitting works for providing Functional Household Tap Connection within the command area of BACHHANARI W/S Scheme | SM/09066 | Retrofitting | PROVIDING TUBE WELL MATERIALS (150MM DIA CD), CONFORMING TO IS12:42 PM 12818:2010 WITH OTHER MATERIALS AT SITE FOR CONSTRUCTION OF TUBE WELL AT BACHHANARI, IN HOWRAH DISTRICT UNDER CMSD-I (D), CDD, PHE DTE. |  |  | ORD/000362/2022-2023 | 113/CMSD-I | 06/05/2022 | 21/05/2022 | ASHUTOSH DAS & CO | 3.11 | 3.11 | 100 | 0
12 | HOOGHLY |  | Central Drilling | Retrofitting works for providing Functional Household Tap Connection within the command area of BACHHANARI W/S Scheme | SM/09066 | Retrofitting | SUPPLY & DELIVERY OF CONSUMBLES AND OTHERS WORKS AT SITE FOR CONSTRUCTION OF TUBE WELL AT AMODGHATA W/S SCH, TW-II, HOOGHLY DISTRICT,UNDER CDD. PHE DTE. | Driller In Charge | Junior Engineer | ORD/000364/2022-2023 | 379/CMSD-II | 01/08/2022 | 16/08/2022 | C.M. ENTERPRISE | 3.44 | 0.02 | 0.67 | 0
13 | HOOGHLY |  | Central Drilling | Retrofitting works for providing Functional Household Tap Connection within the command area of BACHHANARI W/S Scheme | SM/09066 | Retrofitting | Providing Drilling crew and other allied works for construction of Tube well (300mm x 200mm x 210 mtrs. Depth) by utilising Departmental machineries for baidyapur W/S Scheme, Tarakeswar block under hooghly District, CDD PHE Dte. | Driller In Charge | Junior Engineer | ORD/000433/2022-2023 | 1724/CDD | 29/12/2022 | 28/01/2023 | DEY ENTERPRISE | 13.83 | 0.01 | 0.08 | 0
Total | [13 empty] | 105.17 | 36.32 | 34.53