## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | HOOGHLY |  | Hooghly Division | RETROFITTING WORKS FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) WITHIN THE COMMAND AREA OF KAPSIT WATER SUPPLY SCHEME | SM/09067 | Retrofitting | Providing 280 Nos FHTC TAP Connection For Kapsit PWSS | Assistant Engineer | Junior Engineer (Civill) | ORD/000507/2021-2022 | 1917/Hug. | 27/10/2021 | 26/11/2021 | M/S S & P CONSTRUCTION | 16.74 | 16.74 | 100 | 100
2 | HOOGHLY |  | Hooghly Division | RETROFITTING WORKS FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) WITHIN THE COMMAND AREA OF KAPSIT WATER SUPPLY SCHEME | SM/09067 | Retrofitting | Providing 550 nos Functional Household Tap Connection (FHTC) within the left out Mouzas of KAPSIT Water Supply Scheme Under Arambag Sub-Division of Hooghly Division P.H.E Dte | Assistant Engineer | Junior Engineer (Civill) | ORD/000099/2022-2023 | 1088/HUG | 03/06/2022 | 03/07/2022 | BRISTI CONSTRUCTION | 30.74 | 23.5 | 76.46 | 100
3 | HOOGHLY |  | Hooghly Division | RETROFITTING WORKS FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) WITHIN THE COMMAND AREA OF KAPSIT WATER SUPPLY SCHEME | SM/09067 | Retrofitting | Providing 250 nos Functional Household Tap Connection (FHTC) within the command area of KAPSIT Water Supply Scheme Under Arambag Sub-Division of Hooghly Division P.H.E Dte | Assistant Engineer | Junior Engineer (Civill) | ORD/000446/2021-2022 | 464/Hug | 10/03/2022 | 30/03/2022 | KOUSIK MONDAL | 12.26 | 12.14 | 99.06 | 30
4 | HOOGHLY |  | Hooghly Division | RETROFITTING WORKS FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) WITHIN THE COMMAND AREA OF KAPSIT WATER SUPPLY SCHEME | SM/09067 | Retrofitting | FHTC |  |  | VCH/002097/2021-2022 |  | 28/01/2022 | 28/01/2022 | S AND P CONSTRUCTION | 16.74 | 0 | 0 | 0
5 | HOOGHLY |  | Hooghly Division | RETROFITTING WORKS FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) WITHIN THE COMMAND AREA OF KAPSIT WATER SUPPLY SCHEME | SM/09067 | Retrofitting | Providing 280 nos Functional Household Tap Connection (FHTC) within the command area of Kapsit Water Supply Scheme Under Arambagh Sub-Division of Hooghly Division P.H.E Dte | Assistant Engineer | Junior Engineer (Civill) | ORD/000232/2021-2022 | 1917/Hug | 27/10/2021 | 26/11/2021 | S AND P CONSTRUCTION | 16.75 | 0 | 0 | 100
6 | HOOGHLY |  | Hooghly Division | RETROFITTING WORKS FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) WITHIN THE COMMAND AREA OF KAPSIT WATER SUPPLY SCHEME | SM/09067 | Retrofitting | Construction of Boundary wall, Pathway & Land development at the Head Work site of Kapsit W/S Scheme under Arambagh Sub - Division of Hooghly Division, P.H.E. Dte | Assistant Engineer | Junior Engineer (Civill) | ORD/000933/2020-2021 | 1536/HUG | 24/11/2020 | 14/11/2024 | KAPTON | 13.57 | 0 | 0 | 100
Total | [13 empty] | 106.81 | 52.39 | 49.05