## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | HOOGHLY |  | Hooghly Division | RETROFITTING WORKS FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) WITHIN THE COMMAND AREA OF KANPUR WATER SUPPLY SCHEME. | SM/09068 | Retrofitting | FHTC |  |  | VCH/002099/2021-2022 |  | 28/01/2022 | 28/01/2022 | MANISHIKA CONSTRUCTION | 14.88 | 0 | 0 | 0
2 | HOOGHLY |  | Hooghly Division | RETROFITTING WORKS FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) WITHIN THE COMMAND AREA OF KANPUR WATER SUPPLY SCHEME. | SM/09068 | Retrofitting | Providing 280 nos Functional Household Tap Connection (FHTC) within the command area of Kanpur Water Supply Scheme Under Arambagh Sub-Division of Hooghly Division P.H.E Dte. | Assistant Engineer | Junior Engineer (Civill) | ORD/000245/2021-2022 | 1996/Hug | 12/11/2021 | 12/12/2021 | MANISHIKA CONSTRUCTION | 14.98 | 0 | 0 | 100
3 | HOOGHLY |  | Hooghly Division | RETROFITTING WORKS FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) WITHIN THE COMMAND AREA OF KANPUR WATER SUPPLY SCHEME. | SM/09068 | Retrofitting | Providing 280 nos Functional Household Tap Connection (FHTC) within the command area of KANPUR Water Supply Scheme Under ARAMBAG Sub-Division of Hooghly Division P.H.E Dte. | Assistant Engineer | Junior Engineer (Civill) | ORD/000345/2021-2022 | 46/Hug | 07/01/2022 | 06/02/2022 | ASIT KUMAR KHANRUI | 7.34 | 0 | 0 | 100
Total | [13 empty] | 37.19 | 0 | 0