## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | HOOGHLY |  | Central Drilling | RETROFITTING WORKS FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) WITHIN THE COMMAND AREA OF AKNA WATER SUPPLY SCHEME. | SM/09069 | Retrofitting | PROVIDING DRILLING CREW AND OTHER AIILIED WORKS FOR CONSTRUCTION OF TUBE WELL (250MM X 150MM X 250 MTRS DEPTH) BY UTILIZING DEPARTMENTAL MACHINERIES FOR AKNA W/S SCHEME (Z-I), POLBA DADPUR BLOCK UNDER HOOGHLY DISTRICT, CDD, PHE DTE. | Driller In Charge | Junior Engineer | ORD/000195/2022-2023 | 292/ CDD | 27/04/2022 | 27/05/2022 | PADMA ENGINEERING & CO. | 4.21 | 0 | 0 | 100
2 | HOOGHLY |  | Central Drilling | RETROFITTING WORKS FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) WITHIN THE COMMAND AREA OF AKNA WATER SUPPLY SCHEME. | SM/09069 | Retrofitting | PROVIDING DRILLING CREW AND OTHER ALLIED WORKS FOR CONSTRUCTION OF TUBE WELL (250MM X 150MM X 250 MTRS DEPTH) BY UTILIZING DEPARTMENTAL MACHINERIES FOR HANRAL W/S SCH, POLBA DADPUR BLOCK UNDER HOOGHLY DISTRICT, CDD, PHE DTE. |  |  | ORD/000161/2022-2023 | 292/CDD | 27/04/2022 | 27/05/2022 | PADMA ENGINEERING & CO. | 11.23 | 4.21 | 37.47 | 90
Total | [13 empty] | 15.44 | 4.21 | 27.26