## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | HOOGHLY |  | Hooghly Division | RETROFITTING WORKS FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) WITHIN THE COMMAND AREA OF SAPTAGRAM WATER SUPPLY SCHEME. | SM/09070 | Retrofitting | Providing 1600 nos Functional Household Tap Connection (FHTC) within the command area of Saptagram Water Supply Scheme Under Chinsurah Sub-Division of Hooghly Division P.H.E Dte | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/000547/2021-2022 | 1674/HUG | 13/09/2021 | 23/10/2021 | MIXED ENGINEER'S CO - OPERATIVE SOCIETY LTD | 73.56 | 0 | 0 | 100
2 | HOOGHLY |  | Central Drilling | RETROFITTING WORKS FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) WITHIN THE COMMAND AREA OF SAPTAGRAM WATER SUPPLY SCHEME. | SM/09070 | Retrofitting | PROVIDING DRILLING CREWS FOR CONSTRUCTION OF TUBE WELL BY DEPARTMENTAL RIG MACHINE AT SAPTAGRAM PWSS, CHINSURAH MOGRA BLOCK, HOOGHLY DISTRICT UNDER CMSD-I (D), CDD, PHE DTE. |  |  | ORD/000030/2022-2023 | 178/CMSD-I (D) | 10/06/2022 | 25/06/2022 | S B S ENTERPRISE | 3.88 | 0 | 0 | 100
3 | HOOGHLY |  | Central Drilling | RETROFITTING WORKS FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) WITHIN THE COMMAND AREA OF SAPTAGRAM WATER SUPPLY SCHEME. | SM/09070 | Retrofitting | SUPPLY & DELIVERY OF CONSUMBLES AT SITE FOR CONSTRUCTION OF TUBE WELL AT SAPTAGRAM PWSS, CHINSURAH MOGRA BLOCK, HOOGHLY DISTRICT UNDER CDD, PHE DTE. |  |  | ORD/000034/2022-2023 | 181/CMSD-I (D) | 20/06/2022 | 05/07/2022 | M/S PRACHI ENGINEERING | 1.88 | 0 | 0 | 100
4 | HOOGHLY |  | Central Drilling | RETROFITTING WORKS FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) WITHIN THE COMMAND AREA OF SAPTAGRAM WATER SUPPLY SCHEME. | SM/09070 | Retrofitting | PROVIDING TUBE WELL MATERIALS, CONFORMING TO IS: 12818:2010 WITH OTHER MATERIALS AT SITE FOR CONSTRUCTION OF TUBE WELL AT SAPTAGRAM PWSS, CHINSURAH MOGRA BLOCK, HOOGHLY DISTRICT UNDER CDD, PHE DTE. |  |  | ORD/000031/2022-2023 | 176/CMSD-I (D) | 10/06/2022 | 25/06/2022 | S B S ENTERPRISE | 4.85 | 0 | 0 | 100
5 | HOOGHLY |  | Central Drilling | RETROFITTING WORKS FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) WITHIN THE COMMAND AREA OF SAPTAGRAM WATER SUPPLY SCHEME. | SM/09070 | Retrofitting | SUPPLY & DELIVERY OF PEA SIZE GRAVELS AT SITE FOR CONSTRUCTION OF TUBE WELLS AT HARIPAL (Z-I) PWSS, HARIPAL BLOCK, HOOGHLY DISTRICT UNDER CMSD-I (D), CDD, PHE DTE. |  |  | ORD/000404/2022-2023 | 574/CMSD-I (D) (P-II) | 30/11/2022 | 07/12/2022 | C.M. ENTERPRISE | 0.7 | 0 | 0 | 0
6 | HOOGHLY |  | Hooghly Division | RETROFITTING WORKS FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) WITHIN THE COMMAND AREA OF SAPTAGRAM WATER SUPPLY SCHEME. | SM/09070 | Retrofitting | Construction of 3.60 m X 3.00 m Switch Room with Sanitary and Water Supply & Sanitation arrangement at 4th T/W Site of SAPTAGRAM W/S Scheme under Chinsurah Sub-Division P.H.E. Dte. | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/000269/2022-2023 | 724/CH | 23/08/2022 | 07/10/2022 | SRI KRISHNA ENTERPRISE | 4.97 | 0 | 0 | 100
7 | HOOGHLY |  | Hooghly Division | RETROFITTING WORKS FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) WITHIN THE COMMAND AREA OF SAPTAGRAM WATER SUPPLY SCHEME. | SM/09070 | Retrofitting | Providing Functional Household Tap Connection (FHTC) within the command area (left out portion) of SAPTAGRAM Water Supply Scheme Under Chinsurah Sub-Division of Hooghly Division P.H.E Dte. | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/000616/2022-2023 | 2936/HUG | 28/12/2022 | 16/02/2023 | STP ENTERPRISE | 48.34 | 0 | 0 | 90
8 | HOOGHLY |  | Central Drilling | RETROFITTING WORKS FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) WITHIN THE COMMAND AREA OF SAPTAGRAM WATER SUPPLY SCHEME. | SM/09070 | Retrofitting | ADDITIONAL WORK FOR CONSTRUCTION OF TUBEWELL AT IIEST TW-I, SHIBPUR, HOWRAH DISTRICT BY UTILISING SKIILLED DEPARTMENTAL CREW AND DEPARTMENTAL MACHINERIES OF CDD, PHE DTE. |  |  | ORD/000365/2022-2023 | 111/CMSD-I | 29/04/2022 | 14/05/2022 | ASHUTOSH DAS & CO | 0.93 | 0 | 0 | 0
9 | HOOGHLY |  | Central Drilling | RETROFITTING WORKS FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) WITHIN THE COMMAND AREA OF SAPTAGRAM WATER SUPPLY SCHEME. | SM/09070 | Retrofitting | Providing Drilling crew and other allied works for construction of Tube well (300mm x 200mm x 210 mtrs. Depth) by utilising Departmental machineries for baidyapur W/S Scheme, Tarakeswar block under hooghly District, CDD PHE Dte. | Driller In Charge | Junior Engineer | ORD/000433/2022-2023 | 1724/CDD | 29/12/2022 | 28/01/2023 | DEY ENTERPRISE | 13.83 | 0 | 0 | 0
Total | [13 empty] | 152.93 | 0 | 0