## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | HOOGHLY |  | Hooghly Division | Augmentation of DEBANANDAPUR Piped Water Supply Scheme by installing ( 01 ) no. Tube well including Connection with Distribution, Switch Room and other allied work to meet up the water demand, hampered due to execution of FHTC. | SM/09207 | Augmentation | Providing of 87 nos Functional House Hold Tap Connection Within Debanandapur Mouza of Debanandapur Water Supply Scheme Under Chinsurah Sub-Division of Hooghly Division P.H.E Dte. | Assistant Engineer (Civil) |  | ORD/000419/2021-2022 | 91/CH | 03/02/2022 | 28/02/2022 | BIMAL KUMAR HALDER | 4.99 | 0 | 0 | 100
2 | HOOGHLY |  | Hooghly Division | Augmentation of DEBANANDAPUR Piped Water Supply Scheme by installing ( 01 ) no. Tube well including Connection with Distribution, Switch Room and other allied work to meet up the water demand, hampered due to execution of FHTC. | SM/09207 | Augmentation | Providing 70 nos. Functional House Hold Connection (FHTC) within the Command area of DEBANANDAPUR (Z-II) Water Supply Scheme Under Chinsurah Sub-Division. (Block: Chinsurah-Magra) | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/000275/2022-2023 | 730/CH | 26/08/2022 | 10/09/2022 | BIMAL KUMAR HALDER | 4.96 | 0 | 0 | 100
3 | HOOGHLY |  | Hooghly Division | Augmentation of DEBANANDAPUR Piped Water Supply Scheme by installing ( 01 ) no. Tube well including Connection with Distribution, Switch Room and other allied work to meet up the water demand, hampered due to execution of FHTC. | SM/09207 | Augmentation | Providing 80 nos. Functional House Hold Connection (FHTC) within the Command area of DEBANANDAPUR (Z-I) Water Supply Scheme Under Chinsurah Sub-Division. (Block: Chinsurah-Magra) | Assistant Engineer (Civil) |  | ORD/000720/2022-2023 | 756/Ch | 05/09/2022 | 20/09/2022 | BIMAL KUMAR HALDER | 4.97 | 0 | 0 | 100
4 | HOOGHLY |  | Hooghly Division | Augmentation of DEBANANDAPUR Piped Water Supply Scheme by installing ( 01 ) no. Tube well including Connection with Distribution, Switch Room and other allied work to meet up the water demand, hampered due to execution of FHTC. | SM/09207 | Augmentation | Providing Functional Household Tap Connection (FHTC) under JJM within left out portion of DEBANANDAPUR PWSS under Chinsurah Sub-Division of Hooghly Division P.H.E Dte. | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/000030/2023-2024 | 1130/HUG | 19/04/2023 | 03/06/2023 | BAKSHI ENTERPRISE | 40.32 | 0 | 0 | 30
Total | [13 empty] | 55.23 | 0 | 0