## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | HOOGHLY |  | Hooghly Division | Augmentation of NALDANGA Piped Water Supply Scheme by Tube well Connection with Distribution, Switch Room and other allied work to meet up the water demand, hampered due to execution of FHTC. | SM/09208 | Augmentation | WBSEDCL PAYMENT FROM ELECTRICAL DIVISION,PHE DTE. |  |  | VCH/001030/2022-2023 |  | 20/09/2022 | 20/09/2022 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 3.2 | 0 | 0 | 0
2 | HOOGHLY |  | Hooghly Division | Augmentation of NALDANGA Piped Water Supply Scheme by Tube well Connection with Distribution, Switch Room and other allied work to meet up the water demand, hampered due to execution of FHTC. | SM/09208 | Augmentation | Laying of C.I/D.I pipes & specials for connection of T.W No. -III with distribution system at 4TH TW Site of Naldanga W/S Scheme under Chinsurah Sub - Division P.H.E. Dte. | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/000590/2021-2022 | 598/CH | 14/12/2021 | 08/01/2022 | R.K. TRADERS | 4.05 | 1.31 | 32.29 | 100
3 | HOOGHLY |  | Hooghly Division | Augmentation of NALDANGA Piped Water Supply Scheme by Tube well Connection with Distribution, Switch Room and other allied work to meet up the water demand, hampered due to execution of FHTC. | SM/09208 | Augmentation | Providing Functional Household Tap Connection at Subhaspally of Kadalia-2 Gram Panchyet under Naldanga W/S scheme under Chinsurah Sub- Division, PHE Dte. | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/000306/2023-2024 | 693/CH | 27/07/2023 | 11/08/2023 | S.D ENTERPRISE (SAMIR KR. DAS) | 0.97 | 0.97 | 100 | 100
4 | HOOGHLY |  | Hooghly Division | Augmentation of NALDANGA Piped Water Supply Scheme by Tube well Connection with Distribution, Switch Room and other allied work to meet up the water demand, hampered due to execution of FHTC. | SM/09208 | Augmentation | Providing Functional Household Tap Connection at Natunpara Talpukur of Kadalia-2 Gram Panchyet under Naldanga W/S scheme under Chinsurah Sub- Division, PHE Dte. | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/000307/2023-2024 | 694/CH | 27/07/2023 | 11/08/2023 | S.D ENTERPRISE (SAMIR KR. DAS) | 0.97 | 0.97 | 100 | 100
5 | HOOGHLY |  | Hooghly Division | Augmentation of NALDANGA Piped Water Supply Scheme by Tube well Connection with Distribution, Switch Room and other allied work to meet up the water demand, hampered due to execution of FHTC. | SM/09208 | Augmentation | Connecting Rising main From Newly Bored Tube Well at Jatileswer Tala to the Existing distribution system and allied works of Naldanga water supply scheme under Chinsurah Sub Division undre Hooghly Division PHE Dte. | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/000510/2023-2024 | 817/CH | 31/08/2023 | 15/09/2023 | R.K. TRADERS | 0.98 | 0.96 | 97.88 | 80
6 | HOOGHLY |  | Hooghly Division | Augmentation of NALDANGA Piped Water Supply Scheme by Tube well Connection with Distribution, Switch Room and other allied work to meet up the water demand, hampered due to execution of FHTC. | SM/09208 | Augmentation | Connecting Rising main with Existing distribution system and allied works at Simla Village of Naldanga water supply scheme under Chinsurah Sub Divusion undre Hooghly Division PHE Dte. | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/000513/2023-2024 | 821/CH | 31/08/2023 | 15/09/2023 | R.K. TRADERS | 1 | 1 | 100 | 80
7 | HOOGHLY |  | Hooghly Division | Augmentation of NALDANGA Piped Water Supply Scheme by Tube well Connection with Distribution, Switch Room and other allied work to meet up the water demand, hampered due to execution of FHTC. | SM/09208 | Augmentation | Laying distribution of Pipeline and allied works at Jatileswar Tala, Natun Para, Simla Village of Naldanga water supply scheme under Chinsurah Sub Divusion under Hooghly Division PHE Dte. | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/000511/2023-2024 | 818/CH | 31/08/2023 | 15/09/2023 | R.K. TRADERS | 0.96 | 0.96 | 100.68 | 80
8 | HOOGHLY |  | Hooghly Division | Augmentation of NALDANGA Piped Water Supply Scheme by Tube well Connection with Distribution, Switch Room and other allied work to meet up the water demand, hampered due to execution of FHTC. | SM/09208 | Augmentation | Repairing & Renovation of switch room including boundary wall at different TW sites of Naldanga water supply scheme and Dharampur water supply scheme under Chinsurah mogra block of Chinsurah Sub-division under Hooghly Division, P.H.E Dte. | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/001562/2024-2025 | 326/HUG | 05/02/2025 | 06/04/2025 | SOUMYADIP DE | 21.24 | 0 | 0 | 50
Total | [13 empty] | 33.34 | 6.15 | 18.46