## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | HOOGHLY |  | Central Drilling | SOURCE AUGMENTATION OF ANTPUR PIPED WATER SUPPLY SCHEME. | SM/09423 | Augmentation | PROVIDING TUBE WELL MATERIALS, CONFORMING TO IS: 12818:2010 WITH OTHER MATERIALS AT SITE FOR CONSTRUCTION OF TUBE WELL AT ANTPUR PWSS, JAIGIPARA BLOCK, HOOGHLY DISTRICT UNDER CDD, PHE DTE. |  |  | ORD/000032/2022-2023 | 177/CMSD-I (D) | 10/06/2022 | 25/06/2022 | M/S S.K.GHOSH & CO. | 4.38 | 3.91 | 89.18 | 90
2 | HOOGHLY |  | Central Drilling | SOURCE AUGMENTATION OF ANTPUR PIPED WATER SUPPLY SCHEME. | SM/09423 | Augmentation | Supply & Delivery of consumables at site for construction of TW at ANTPUR PWSS under CDD, PHE Dte. |  |  | ORD/000027/2022-2023 | 179/CMSD-I(D) | 10/06/2022 | 25/06/2022 | S B S ENTERPRISE | 1.5 | 1.45 | 96.69 | 100
3 | HOOGHLY |  | Central Drilling | SOURCE AUGMENTATION OF ANTPUR PIPED WATER SUPPLY SCHEME. | SM/09423 | Augmentation | PROVIDING DRILLING CREWS FOR CONSTRUCTION OF TUBE WELL BY DEPARTMENTAL RIG MACHINE AT ANTPUR PWSS, JANGIPARA BLOCK, HOOGHLY DISTRICT UNDER CDD, PHE DTE. |  |  | ORD/000033/2022-2023 | 180/CMSD-I(D) | 10/06/2022 | 25/06/2022 | M/S S.K.GHOSH & CO. | 2.9 | 2.75 | 94.91 | 100
4 | HOOGHLY |  | Hooghly Division | SOURCE AUGMENTATION OF ANTPUR PIPED WATER SUPPLY SCHEME. | SM/09423 | Augmentation | Construction of One No. 3.60 m X 3.00 m Switch Room without Sanitary and Water Supply arrangement at 3rd T/W Site for ANTPUR W/S Scheme under Serampore Sub-Division of Hooghly Division,P.H.E. Dte. | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/000350/2022-2023 | 537/SER | 08/09/2022 | 07/11/2022 | BAKSHI ENTERPRISE | 2.65 | 2.53 | 95.58 | 0
5 | HOOGHLY |  | Central Drilling | SOURCE AUGMENTATION OF ANTPUR PIPED WATER SUPPLY SCHEME. | SM/09423 | Augmentation | PROVIDING DRILLING CREWS FOR CONSTRUCTION OF TUBEWELL BY DEPARTMENTAL RIG MACHINE AT AMODGHATA W/S SCH TW-II, POLBA DADPUR BLOCK, HOOGHLY DISTRICT UNDER CMSD-II (D), CDD, PHE DTE. | Driller In Charge | Junior Engineer | ORD/000367/2022-2023 | 377/CMSD-II | 01/08/2022 | 16/08/2022 | C.M. ENTERPRISE | 2.93 | 0.11 | 3.68 | 0
6 | HOOGHLY |  | Central Drilling | SOURCE AUGMENTATION OF ANTPUR PIPED WATER SUPPLY SCHEME. | SM/09423 | Augmentation | PROVIDING TUBE WELL MATERIALS (250MM DIA CD) CONFORMING TO IS12:42 PM 12818:2010 WITH OTHER MATERIALS AT SITE FOR CONSTRUCTION OF TUBEWELL ANTPUR, UNDER CMSD-I (D), CDD, PHE DTE. |  |  | ORD/000363/2022-2023 | 114/CMSD-I | 06/05/2022 | 21/05/2022 | ASHUTOSH DAS & CO | 3.87 | 3.78 | 97.81 | 0
7 | HOOGHLY |  | Electrical | SOURCE AUGMENTATION OF ANTPUR PIPED WATER SUPPLY SCHEME. | SM/09423 | Augmentation | Supply, delivery & installation of submersible pumping machinery and other electrical / mechanical equipments etc. including allied works for ANTPUR PIPED W/S SCHEME, T.W. No. IV, District - Hooghly under JJM Program under Electrical Division PHE Dte. | Assistant Engineer 1,Assistant Engineer Howrah mechanical Sub Division | Junior Engineer2 | ORD/002583/2023-2024 | 458/ED | 05/03/2024 | 03/06/2024 | D. K. ELECTRIC | 9.7 | 0 | 0 | 65
8 | HOOGHLY |  | Hooghly Division | SOURCE AUGMENTATION OF ANTPUR PIPED WATER SUPPLY SCHEME. | SM/09423 | Augmentation | Repairing of Switch Room & Boundary Wall at Existing TW sites of ANTPUR PWSS under Serampore Sub-Division of Hooghly Division P.H.E. Dte. | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/000930/2023-2024 | 986/HUG | 16/03/2024 | 15/04/2024 | SUNITI MAIRA | 6.18 | 0 | 0 | 0
9 | HOOGHLY |  | Hooghly Division | SOURCE AUGMENTATION OF ANTPUR PIPED WATER SUPPLY SCHEME. | SM/09423 | Augmentation | Construction of Boundary Wall in Proposed T.W Site, Laying rising main pipe for inter connection between T.W & Distribution For Source Augmentation of ANTPUR Piped Water Supply Scheme under Hooghly Division P.HE Dte. within Jangipara Block, Serampore Sub Division of Hooghly Division, PHE Dte. | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/000641/2022-2023 | 98/HUG | 10/01/2023 | 09/06/2023 | SHREEOM ENTERPRISE | 4.59 | 4.2 | 91.44 | 99
10 | HOOGHLY |  | Electrical | SOURCE AUGMENTATION OF ANTPUR PIPED WATER SUPPLY SCHEME. | SM/09423 | Augmentation | Quotation bill for new service connection charges at Antpur PWSS P.H. No.-IV, Hooghly. Application No. 5004065652 Ref ID: 503592944 |  |  | BILL/00120/2024-2025 | 42 | 09/04/2024 | 09/04/2024 | WBSEDCL | 5.37 | 0 | 0 | 0
11 | HOOGHLY |  | Hooghly Division | SOURCE AUGMENTATION OF ANTPUR PIPED WATER SUPPLY SCHEME. | SM/09423 | Augmentation | Quotation money deposition for new service connection at Antpur w/s scheme, T.W. No.-V, Dist.-Hooghly under PHE Dte. Application No- 5004622560 Reference ID- 503902562 SM Code- 09423 |  |  | BILL/00783/2025-2026 |  | 28/08/2025 | 28/08/2025 | WBSEDCL | 6.23 | 0 | 0 | 0
12 | HOOGHLY |  | Electrical | SOURCE AUGMENTATION OF ANTPUR PIPED WATER SUPPLY SCHEME. | SM/09423 | Augmentation | Supply, delivery & installation of submersible pumping machinery and other electrical/ mechanical equipments etc. including allied works for Antpur (Aug) water supply scheme, T.W. No. III, Block: Jangipara, District- Hooghly under Electrical Division, PHE Dte. | Assistant Engineer 1 | Junior Engineer2 | ORD/002564/2022-2023 | 1321/ED | 17/08/2022 | 01/06/2026 | M/S, GHOSH ENTERPRISE | 10.28 | 9.91 | 96.42 | 75
Total | [13 empty] | 60.57 | 28.63 | 47.28