## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | HOOGHLY |  | Hooghly Division | Augmentation of RAJHAT ZONE 2 Piped Water Supply Scheme by installing ( 01 ) no. Tube well including Connection with Distribution, Switch Room and other allied work to meet up the water demand, hampered due to execution of FHTC. | SM/09517 | Augmentation | Construction of 3.6 m X 3.00 m Switch Room without Sanitary and Water Supply arrangement at 3rd T/W Site for Rajhat (Z-II) W/S Scheme under Chinsurah Sub-Division P.H.E. Dte. | Assistant Engineer (Civil) |  | ORD/000468/2021-2022 | 622/CH | 20/12/2021 | 29/01/2022 | SURAJ ENTERPRISE | 2.44 | 2.44 | 99.98 | 100
2 | HOOGHLY |  | Electrical | Augmentation of RAJHAT ZONE 2 Piped Water Supply Scheme by installing ( 01 ) no. Tube well including Connection with Distribution, Switch Room and other allied work to meet up the water demand, hampered due to execution of FHTC. | SM/09517 | Augmentation | Supply, Delivery & Installation of S/P/M & other Electrical/Mechanical equipment etc. including allied works for Rajhat W/S. Sch. Z-II, TW-III | Assistant Engineer Howrah mechanical Sub Division | Junior Engineer4 | ORD/000026/2022-2023 | 1036/ED | 28/06/2022 | 05/10/2022 | INDIA ENTERPRISE | 9.21 | 9.21 | 100 | 100
3 | HOOGHLY |  | Electrical | Augmentation of RAJHAT ZONE 2 Piped Water Supply Scheme by installing ( 01 ) no. Tube well including Connection with Distribution, Switch Room and other allied work to meet up the water demand, hampered due to execution of FHTC. | SM/09517 | Augmentation | Electric Supply |  |  | VCH/001993/2022-2023 | 14 | 07/07/2022 | 07/07/2022 | WBSEDCL | 4.53 | 0 | 0 | 0
4 | HOOGHLY |  | Hooghly Division | Augmentation of RAJHAT ZONE 2 Piped Water Supply Scheme by installing ( 01 ) no. Tube well including Connection with Distribution, Switch Room and other allied work to meet up the water demand, hampered due to execution of FHTC. | SM/09517 | Augmentation | Laying of C.I/D.I pipes & specials for connection of T.W No. -III with distribution system & Protection work at 3rd TW Site of Rajhat (Z-II) W/S Scheme under Chinsurah Sub - Division P.H.E. Dte. | Assistant Engineer (Civil) |  | ORD/000467/2021-2022 | 621/CH | 20/12/2021 | 14/01/2022 | BIMAL KUMAR HALDER | 4.16 | 0.86 | 20.78 | 100
5 | HOOGHLY |  | Hooghly Division | Augmentation of RAJHAT ZONE 2 Piped Water Supply Scheme by installing ( 01 ) no. Tube well including Connection with Distribution, Switch Room and other allied work to meet up the water demand, hampered due to execution of FHTC. | SM/09517 | Augmentation | Construction of Boundary Wall & Pathway Development of RAJHAT (Z-II) at 3rd T/W Site W/S Scheme under Chinsurah Sub-Division P.H.E. Dte | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/000276/2022-2023 | 731/CH | 26/08/2022 | 25/09/2022 | SURAJ ENTERPRISE | 4.85 | 4.42 | 91.19 | 100
6 | HOOGHLY |  | Electrical | Augmentation of RAJHAT ZONE 2 Piped Water Supply Scheme by installing ( 01 ) no. Tube well including Connection with Distribution, Switch Room and other allied work to meet up the water demand, hampered due to execution of FHTC. | SM/09517 | Augmentation | Supply & installation of LED board at Zone-II, P.H. No.-I & II of Rajhat water supply scheme, Dist.- Hooghly under Electrical Division, PHE Dte. | Assistant Engineer Howrah mechanical Sub Division | Junior Engineer4 | ORD/000600/2022-2023 | 2348/HMSD | 20/12/2022 | 30/12/2022 | SUDHIKSHA CONSTRUCTION | 0.79 | 0.79 | 100 | 0
7 | HOOGHLY |  | Electrical | Augmentation of RAJHAT ZONE 2 Piped Water Supply Scheme by installing ( 01 ) no. Tube well including Connection with Distribution, Switch Room and other allied work to meet up the water demand, hampered due to execution of FHTC. | SM/09517 | Augmentation | 'Hire Charges Bill of V.No.- WB07J-317301.03.23 to 14.05.23' with fuel bill |  |  | ORD/002176/2022-2023 | 215//AE-II/ED | 24/03/2023 | 23/04/2023 | INDRANI ENTERPRISE | 0.63 | 0.63 | 100 | 1
8 | HOOGHLY |  | Electrical | Augmentation of RAJHAT ZONE 2 Piped Water Supply Scheme by installing ( 01 ) no. Tube well including Connection with Distribution, Switch Room and other allied work to meet up the water demand, hampered due to execution of FHTC. | SM/09517 | Augmentation | Supply, delivery & installation of submersible pumping machinery and other electrical/ mechanical equipments etc. including allied works for Rajhat water supply scheme, Zone-II, T.W. No.- IV, Block: Polba Dadpur, District- Hooghly under Electrical Division, PHE Dte. | Assistant Engineer Howrah mechanical Sub Division | Junior Engineer4 | ORD/000235/2022-2023 | 866/ED | 14/02/2023 | 15/05/2023 | KUSHANI ENTERPRISE | 10.17 | 10.17 | 99.95 | 100
9 | HOOGHLY |  | Electrical | Augmentation of RAJHAT ZONE 2 Piped Water Supply Scheme by installing ( 01 ) no. Tube well including Connection with Distribution, Switch Room and other allied work to meet up the water demand, hampered due to execution of FHTC. | SM/09517 | Augmentation | "Hire Charges Bill of V.No.- WB07J-3173 01.03.23 to 14.05.23" with fuel bill |  |  | ORD/002170/2022-2023 | 215//AE-II/ED | 24/03/2023 | 23/04/2023 | INDRANI ENTERPRISE | 0.62 | 0 | 0 | 1
10 | HOOGHLY |  | Hooghly Division | Augmentation of RAJHAT ZONE 2 Piped Water Supply Scheme by installing ( 01 ) no. Tube well including Connection with Distribution, Switch Room and other allied work to meet up the water demand, hampered due to execution of FHTC. | SM/09517 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000348/2023-2024 | 3004/10/Hug | 05/10/2023 | 05/10/2023 | Resource Division | 2.86 | 0 | 0 | 0
Total | [13 empty] | 40.25 | 28.53 | 70.86