## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | HOOGHLY |  | Central Drilling | Augmentation of PANDUA ZONE 1 Piped Water Supply Scheme by installing ( 01 ) no. Tube well including Connection with Distribution, Switch Room and other allied work to meet up the water demand, hampered due to execution of FHTC. | SM/09604 | Augmentation | PROVIDING PEA SIZE GRAVELS AT SITE FOR CONSTRUCTION OF TUBE WELL AT PANDUA BLOCK UNDER CDD, PHE DTE. |  |  | ORD/000177/2022-2023 | 328/CMSD-I | 15/07/2022 | 25/07/2022 | INDRANI ENTERPRISE | 0.93 | 0 | 0 | 100
2 | HOOGHLY |  | Central Drilling | Augmentation of PANDUA ZONE 1 Piped Water Supply Scheme by installing ( 01 ) no. Tube well including Connection with Distribution, Switch Room and other allied work to meet up the water demand, hampered due to execution of FHTC. | SM/09604 | Augmentation | PROVIDING DRILLING CREWS FOR CONSTRUCTION OF TUBE WELL BY DEPARTMENTAL RIG MACHINE IN PANDUA, SUTAHATA BLOCK UNDER CMSD-I (D), CDD, PHE DTE. |  |  | ORD/000178/2022-2023 | 223/CMSD-I | 20/06/2022 | 05/07/2022 | INDRANI ENTERPRISE | 4.98 | 0 | 0 | 100
3 | HOOGHLY |  | Central Drilling | Augmentation of PANDUA ZONE 1 Piped Water Supply Scheme by installing ( 01 ) no. Tube well including Connection with Distribution, Switch Room and other allied work to meet up the water demand, hampered due to execution of FHTC. | SM/09604 | Augmentation | SINKING OF 200 MM X 100 MM DIA TUBE WELL WITH OTHER WOORKS AT SITE IN PANDUA, GHATAL BLOCK UNDER CDD, PHE DTE. |  |  | ORD/000180/2022-2023 | 396/CMSD-I | 05/08/2022 | 20/08/2022 | INDRANI ENTERPRISE | 5 | 0 | 0 | 100
4 | HOOGHLY |  | Central Drilling | Augmentation of PANDUA ZONE 1 Piped Water Supply Scheme by installing ( 01 ) no. Tube well including Connection with Distribution, Switch Room and other allied work to meet up the water demand, hampered due to execution of FHTC. | SM/09604 | Augmentation | PROVIDING BENTONITE POWDER SODIUM BASED WITH OTHER MATERIALS & WORKS AT SITE FOR CONSTRUCTION OF TUBE WELL AT PANDUA BLOCK UNDER CDD, PHE DTE. |  |  | ORD/000179/2022-2023 | 329/CMSD-I | 15/07/2022 | 25/07/2022 | INDRANI ENTERPRISE | 0.97 | 0 | 0 | 100
5 | HOOGHLY |  | Electrical | Augmentation of PANDUA ZONE 1 Piped Water Supply Scheme by installing ( 01 ) no. Tube well including Connection with Distribution, Switch Room and other allied work to meet up the water demand, hampered due to execution of FHTC. | SM/09604 | Augmentation | Replacement of some electrical accessories, voltage correcting device and other allied works for Pandua water supply scheme, Zone-III, P.H. No. I, District- Hooghly under Electrical Division, PHE Dte. |  |  | ORD/000317/2022-2023 | 493/HMSD | 02/03/2023 | 01/04/2023 | KARUNAMOY ENGINEERING | 3.06 | 0 | 0 | 0
Total | [13 empty] | 14.93 | 0 | 0