## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | HOOGHLY |  | Hooghly Division | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR KAKNAN BLOCK: KHANKUL-II | SM/09688 | Augmentation | Preparation of DPR for Augmentation of KAKNAN Piped Water Supply Scheme Under Arambagh Sub-Division of Hooghly Division P.H.E Dte. [Block-Khanakul-II]. | Assistant Engineer | Junior Engineer (Civill) | ORD/000381/2021-2022 | 612/Arg | 31/12/2021 | 30/01/2022 | SRIJAN ECOLOGICAL UPLIFTMENT PVT. LTD. | 3.17 | 3.16 | 99.58 | 100
2 | HOOGHLY |  | Hooghly Division | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR KAKNAN BLOCK: KHANKUL-II | SM/09688 | Augmentation | Augmentation of KAKNAN (ZONE-I) Water Supply Scheme with Laying Distribution System & Functional Household Tap Connection, of Switch room, Boundary wall, existing OHR at KHANAKUL-II Block under Arambag Sub-Division, PHE Dte. | Assistant Engineer | Junior Engineer (Civill) | ORD/000192/2022-2023 | 963//Hug | 17/05/2022 | 16/07/2022 | UNIQUE AGENCY | 166.37 | 165.74 | 99.62 | 100
3 | HOOGHLY |  | Hooghly Division | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR KAKNAN BLOCK: KHANKUL-II | SM/09688 | Augmentation | Sinking of One No Big Dia Tube Well (300 mm X 200 mm) with supply of uPVC pipes & Strainer having depth upto 180 Mtr at KAKNAN (ZONE-II) PWSS of Arambag Sub-Division under Hooghly Division, PHE Dte. SL NO - 10 | Assistant Engineer | Junior Engineer (Civill) | ORD/000345/2022-2023 | 1958/HUG | 07/09/2022 | 07/10/2022 | OSMAN SEKH | 11.32 | 10.41 | 91.99 | 100
4 | HOOGHLY |  | Hooghly Division | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR KAKNAN BLOCK: KHANKUL-II | SM/09688 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000163/2021-2022 | 424/4/Hug | 07/03/2022 | 07/03/2022 | Resource Division | 36.05 | 0 | 0 | 0
5 | HOOGHLY |  | Hooghly Division | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR KAKNAN BLOCK: KHANKUL-II | SM/09688 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000023/2022-2023 | 1124/4/HUG | 06/06/2022 | 06/06/2022 | Resource Division | 12.32 | 0 | 0 | 0
6 | HOOGHLY |  | Hooghly Division | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR KAKNAN BLOCK: KHANKUL-II | SM/09688 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000106/2022-2023 | 1773/40/Hug | 29/08/2022 | 29/08/2022 | Resource Division | 1.38 | 0 | 0 | 0
7 | HOOGHLY |  | Hooghly Division | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR KAKNAN BLOCK: KHANKUL-II | SM/09688 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000047/2022-2023 | 1590/2/Hug | 03/08/2022 | 03/08/2022 | Resource Division | 6.15 | 0 | 0 | 0
8 | HOOGHLY |  | Hooghly Division | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR KAKNAN BLOCK: KHANKUL-II | SM/09688 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000143/2023-2024 | 1385/13/Hug | 15/05/2023 | 15/05/2023 | Resource Division | 1.79 | 0 | 0 | 0
9 | HOOGHLY |  | Electrical | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR KAKNAN BLOCK: KHANKUL-II | SM/09688 | Augmentation | Quotation Bill for New Service Connection at Aug. of Kaknan W/S. Sch. TW-III Hooghly |  |  | BILL/00938/2022-2023 |  | 13/03/2023 | 13/03/2023 | WBSEDCL | 3.65 | 0 | 0 | 0
10 | HOOGHLY |  | Hooghly Division | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR KAKNAN BLOCK: KHANKUL-II | SM/09688 | Augmentation | SUBMISSION OF QUOTATION BILL FOR THE WBSEDCL BILL RAISED BY THE EXECUTIVE ENGINEER, ELECTRICAL DIVISION, PHE DTE. |  |  | BILL/00368/2022-2023 | BP-2022-23-644 | 25/03/2023 | 25/03/2023 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 3.65 | 0 | 0 | 0
11 | HOOGHLY |  | Hooghly Division | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR KAKNAN BLOCK: KHANKUL-II | SM/09688 | Augmentation | Augmentation of KAKNAN (ZONE-II) Water Supply Scheme with Laying Distribution System & Functional Household Tap Connection, Construction of Switch Room & Boundary Wall of 3rd T.W Site at KHANAKUL-II Block under Arambag Sub-Division, PHE Dte. | Assistant Engineer | Junior Engineer (Civill) | ORD/000095/2022-2023 | 1086/Hug | 02/06/2022 | 02/07/2022 | SWASTIK ENTERPRISE | 66.2 | 49.6 | 74.92 | 50
12 | HOOGHLY |  | Hooghly Division | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR KAKNAN BLOCK: KHANKUL-II | SM/09688 | Augmentation | Construction of Drain, Internal Road & Land Development works at Head Work site of Kaknan W/S Scheme under Arambagh Sub - Division P.H.E. Dte. | Assistant Engineer | Junior Engineer (Civill) | ORD/000437/2022-2023 | 728/Arg | 29/09/2022 | 12/04/2025 | UNIQUE AGENCY | 3.81 | 0 | 0 | 100
13 | HOOGHLY |  | Electrical | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR KAKNAN BLOCK: KHANKUL-II | SM/09688 | Augmentation | Supply, delivery & installation of submersible pumping machinery and other electrical/ mechanical equipments etc. including allied works for Augmentation of Kaknan water supply scheme, T.W. No.- I, Block: Khanakul-II, District- Hooghly under Electrical Division, PHE Dte. | Assistant Engineer 2 | Junior Engineer4 | ORD/000287/2022-2023 | 937/ED | 22/02/2023 | 01/09/2025 | OSMAN SEKH | 10.75 | 10.38 | 96.61 | 83
Total | [13 empty] | 326.62 | 239.29 | 73.26