## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | HOOGHLY |  | Hooghly Division | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR ANIYA. | SM/09690 | Augmentation | Preparation of DPR for Augmentation of Aniya Water Supply Scheme under Serampore Sub-Division of Hooghly Division, P.H.E. Dte. [Block-Chanditala-I] | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/000395/2021-2022 | 288/SER | 18/02/2022 | 10/03/2022 | SRIJAN ECHOLOGICAL UPLIFTMENT PVT. LTD. | 3.22 | 0 | 0 | 100
2 | HOOGHLY |  | Hooghly Division | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR ANIYA. | SM/09690 | Augmentation | Augmentation of ANIYA Water Supply Scheme with Laying Distribution System within ANIYA Mouza (Part), Shyamsundarpur & Kalyanbati Mouza, Repairing of existing OHR, Switch Rooms (H/W & 2ND T.W Site) & Construction of Boundary wall at H/W Site and FHTC Work under Chanditala-I Block of Serampore Sub-Division, Hooghly Division, PHE Dte | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/000044/2022-2023 | 828/Hug | 20/04/2022 | 19/06/2022 | ARUN SEAL AND CO. | 155.99 | 0 | 0 | 30
3 | HOOGHLY |  | Hooghly Division | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR ANIYA. | SM/09690 | Augmentation | Augmentation of ANIYA Water Supply Scheme with Laying Distribution System within ANIYA Mouza (Part), Construction of boundary wall at 2nd TW site and FHTC Work under Chanditala-I Block of Serampore Sub-Division, Hooghly Division, PHE Dte. | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/000045/2022-2023 | 829/Hug | 20/04/2022 | 20/05/2022 | DAS ENTERPRISE (SAMIR DAS) | 84.14 | 0 | 0 | 30
4 | HOOGHLY |  | Hooghly Division | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR ANIYA. | SM/09690 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000159/2021-2022 | 422/4/Hug | 07/03/2022 | 07/03/2022 | Resource Division | 39.63 | 0 | 0 | 0
5 | HOOGHLY |  | Hooghly Division | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR ANIYA. | SM/09690 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000003/2022-2023 | 1122/HUG | 06/06/2022 | 06/06/2022 | Resource Division | 12.32 | 0 | 0 | 0
6 | HOOGHLY |  | Hooghly Division | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR ANIYA. | SM/09690 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000063/2022-2023 | 1689/HUG | 22/08/2022 | 22/08/2022 | Resource Division | 0.87 | 0 | 0 | 0
7 | HOOGHLY |  | Hooghly Division | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR ANIYA. | SM/09690 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000121/2022-2023 | 2210/Hug | 30/09/2022 | 30/09/2022 | Resource Division | 0.05 | 0 | 0 | 0
8 | HOOGHLY |  | Hooghly Division | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR ANIYA. | SM/09690 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000036/2022-2023 | 1291/Hug | 24/06/2022 | 24/06/2022 | Resource Division | 6.16 | 0 | 0 | 0
9 | HOOGHLY |  | Hooghly Division | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR ANIYA. | SM/09690 | Augmentation | Designing making and erection of Display Board using logo and tag line of Jal Jeevan Mission to be placed at different work sites and HGJ villages for awareness generation among the people in the district of Hooghly under Serampore Sub Division under Hooghly Division PHE Dte. 1. Seakhala PWSS 2. Aniya PWSS 3. Dudhkalmi PWSS 4. Nababpur PWSS 5. Gangadharpur PWSS 6. Kumirmora PWSS | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/000939/2023-2024 | 109/SER | 23/02/2024 | 01/03/2024 | AMBIAN INFRASTRUCTURE | 0.95 | 0 | 0 | 80
Total | [13 empty] | 303.33 | 0 | 0