## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | HOOGHLY |  | Hooghly Division | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPLY SCHEME FOR ATGHARA. | SM/09692 | Augmentation | Preparation of DPR for Augmentation of ATGHARA Piped Water Supply Scheme Under Arambagh Sub-Division of Hooghly Division P.H.E Dte. [Block-Khanakul-I]. | Assistant Engineer | Junior Engineer (Civill) | ORD/000378/2021-2022 | 609/Arg | 31/12/2021 | 30/01/2022 | SRIJAN ECOLOGICAL UPLIFTMENT PVT. LTD. | 3.67 | 0 | 0 | 100
2 | HOOGHLY |  | Hooghly Division | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPLY SCHEME FOR ATGHARA. | SM/09692 | Augmentation | Sinking of I (one) No Big dia tube well (250 mm X 150mm) with supply of PVC Pipe and strainer and having depth upto 150 M at 3rd TW site of Arandi W/S Scheme under Arambagh Sub-Division of Hooghly Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer (Civill) | ORD/000140/2022-2023 | 1411/HUG | 12/07/2022 | 11/08/2022 | OSMAN SEKH | 8.6 | 0 | 0 | 100
3 | HOOGHLY |  | Central Drilling | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPLY SCHEME FOR ATGHARA. | SM/09692 | Augmentation | SUPPLY & DELIVERY OF PEA SIZE GRAVELS FOR CONSTRUCTION OF TUBE WELL AT SOLEPUR DUTTAPUR (Z-II) PWSS, TARAKESWAR BLOCK, HOOGHLY DISTRICT UNDER CMSD-II (D), CDD, PHE DTE. | Driller In Charge | Junior Engineer | ORD/000272/2022-2023 | 530/CMSD-II | 01/12/2022 | 08/12/2022 | C.M. ENTERPRISE | 0.98 | 0 | 0 | 100
4 | HOOGHLY |  | Hooghly Division | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPLY SCHEME FOR ATGHARA. | SM/09692 | Augmentation | Sinking of 1 no 300 X200 mm dia Tube Well 180 mtr. Depth by D.R. Rig method using UPVC pipe (CD) and UPVC Deep Well Screen (RDS) at proposed Tube Well Site of ATGHARA W/S Scheme under ARAMBAG Sub-Division of Hooghly Division, P.H.E. Dte. | Assistant Engineer |  | ORD/000671/2022-2023 | 165/HUG | 16/01/2023 | 15/02/2023 | M/S EMON ENTERPRISE | 12.83 | 0 | 0 | 0
5 | HOOGHLY |  | Central Drilling | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPLY SCHEME FOR ATGHARA. | SM/09692 | Augmentation | SUPPLY & DELIVERY OF PEA SIZE GRAVELS FOR CONSTRUCTION OF TUBE WELL AT ATGHARA PWSS TW-III, HOOGHLY DISTRICT UNDER CMSD-II (D), CDD, PHE DTE. |  |  | ORD/000274/2022-2023 | 530/CMSD-II (D) | 01/12/2022 | 08/12/2022 | C.M. ENTERPRISE | 0.98 | 0 | 0 | 100
6 | HOOGHLY |  | Central Drilling | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPLY SCHEME FOR ATGHARA. | SM/09692 | Augmentation | PROVIDING DRILLING CREW AND OTHER ALLIED WORKS FOR CONSTRUCTION OF TUBE WELL (300MM X 200MM X 210 MTRS DEPTH) BY UTILIZING DEPARTMENTAL MACHINERIES FOR ATGHARA PWSS, TW-III, UNDER HOOGHLY DISTRICT, CDD, PHE DTE. | Driller In Charge | Junior Engineer | ORD/000273/2022-2023 | 1562/CDD | 08/12/2022 | 07/01/2023 | C.M. ENTERPRISE | 12.49 | 0 | 0 | 100
7 | HOOGHLY |  | Hooghly Division | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPLY SCHEME FOR ATGHARA. | SM/09692 | Augmentation | Augmentation of ATGHARA Water Supply Scheme with Laying Distribution System & Functional Household Tap Connection within Shrirampur, Kaiba & Atghara Mouza, Repairing of existing OHR at Khanakul-I Block under Arambag Sub-Division, PHE Dte. | Assistant Engineer | Junior Engineer (Civill) | ORD/000381/2022-2023 | 1181/HUG | 15/06/2022 | 14/08/2022 | RURAL CONSTRUCTION (MANIK CHANDRA ADAK) | 207.8 | 0 | 0 | 10
8 | HOOGHLY |  | Hooghly Division | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPLY SCHEME FOR ATGHARA. | SM/09692 | Augmentation | Construction of 1 No. switch room (5.40 m x 3.60 m) with sanitary arrangement At Proposed T.W Site OF ATGHARA Water Supply Scheme Under Arambagh Sub-Division Under Hooghly Division P.H.E Dte. | Assistant Engineer |  | ORD/000192/2023-2024 | 1775/HUG | 15/06/2023 | 30/07/2023 | SOUMYAJIT DUTTA | 7.34 | 0 | 0 | 100
9 | HOOGHLY |  | Hooghly Division | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPLY SCHEME FOR ATGHARA. | SM/09692 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000164/2021-2022 | 424/5/Hug | 07/03/2022 | 07/03/2022 | Resource Division | 36.05 | 0 | 0 | 0
10 | HOOGHLY |  | Hooghly Division | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPLY SCHEME FOR ATGHARA. | SM/09692 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000104/2022-2023 | 1773/38/Hug | 29/08/2022 | 29/08/2022 | Resource Division | 0.69 | 0 | 0 | 0
11 | HOOGHLY |  | Hooghly Division | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPLY SCHEME FOR ATGHARA. | SM/09692 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000146/2023-2024 | 1385/17/Hug | 15/05/2023 | 15/05/2023 | Resource Division | 5.48 | 0 | 0 | 0
12 | HOOGHLY |  | Hooghly Division | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPLY SCHEME FOR ATGHARA. | SM/09692 | Augmentation | WBSEDCL bill for Atghara PWSS |  |  | BILL/00408/2022-2023 | BP-2022-23-659 | 29/03/2023 | 29/03/2023 | EXECUTIVE ENGINEER, ELECTRICAL DIVISION, PHE DTE | 5.37 | 0 | 0 | 0
13 | HOOGHLY |  | Hooghly Division | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPLY SCHEME FOR ATGHARA. | SM/09692 | Augmentation | Augmentation of ATGHARA Water Supply Scheme with Laying Distribution System & Functional Household Tap Connection Within Sekendarpur & Helan Mouza, Repairing of Switch room, Boundary wall at Khanakul-I Block under Arambag Sub-Division, PHE Dte. | Assistant Engineer | Junior Engineer (Civill) | ORD/000382/2022-2023 | 1180/HUG | 15/06/2022 | 02/09/2024 | M/S R.K. CHOUDHURI | 139.82 | 0 | 0 | 80
14 | HOOGHLY |  | Hooghly Division | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPLY SCHEME FOR ATGHARA. | SM/09692 | Augmentation | Protection works and other allied works at 3rd TubeWell Sites of Dihibagnan & Atghara Water Supply Scheme under Arambagh Sub-Division of Hooghly Division P.H.E Dte. |  |  | ORD/000471/2024-2025 | 4051/HUG | 19/12/2024 | 19/03/2025 | GOURI ENTERPRISE | 15.53 | 0 | 0 | 0
15 | HOOGHLY |  | Electrical | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPLY SCHEME FOR ATGHARA. | SM/09692 | Augmentation | Supply, delivery & installation of submersible pumping machinery and other electrical / mechanical equipments etc. including allied works for Augmentation of Atghara water supply scheme TW No I Block Khanakul I District Hooghly under ED PHED. | Assistant Engineer 2 | Junior Engineer4 | ORD/000286/2022-2023 | 936/ED | 22/02/2023 | 01/09/2025 | OSMAN SEKH | 10.75 | 0 | 0 | 40
Total | [13 empty] | 468.38 | 0 | 0