## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | HOOGHLY |  | Hooghly Division | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR RAJHATO. | SM/09693 | Augmentation | Preparation of DPR for Augmentation of RAJHATO Piped Water Supply Scheme Under Arambagh Sub-Division of Hooghly Division P.H.E Dte. [Block-Khanakul-II]. | Assistant Engineer | Junior Engineer (Civill) | ORD/000382/2021-2022 | 613/Arg | 31/12/2021 | 30/01/2022 | SRIJAN ECOLOGICAL UPLIFTMENT PVT. LTD. | 3.79 | 3.78 | 99.61 | 100
2 | HOOGHLY |  | Central Drilling | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR RAJHATO. | SM/09693 | Augmentation | HIRING OF DIESEL DRIVEN MOTOR CAB (BS-III & ABOVE) (NON AC) HAVING CONTRACT CARRIAGE PERMIT ALONG WITH FOR THE OFFICE OF THE CALCUTTA MECHANICAL SUB DIVISION-I, PHE DTE. |  |  | ORD/000217/2021-2022 | 67/CMSD-I (D) | 22/03/2022 | 29/03/2022 | SUJATA BHOWMICK | 0.87 | 0 | 0 | 67
3 | HOOGHLY |  | Central Drilling | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR RAJHATO. | SM/09693 | Augmentation | SUPPLY AND DELIVERY OF TENT FOR DRILLING WORK AT RAJHATO PWSS UNDER CDD, PHE DTE. |  |  | ORD/000190/2022-2023 | 255/CMSD-I | 23/06/2022 | 08/07/2022 | M/S S.K.GHOSH & CO. | 4.56 | 0 | 0 | 100
4 | HOOGHLY |  | Central Drilling | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR RAJHATO. | SM/09693 | Augmentation | CONTINGENCY BILL |  |  | VCH/000151/2022-2023 | BP-2022-23-40 | 15/07/2022 | 15/07/2022 | SUJATA BHOWMICK | 0.14 | 0 | 0 | 0
5 | HOOGHLY |  | Central Drilling | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR RAJHATO. | SM/09693 | Augmentation | CONTINGENCY BILL |  |  | VCH/000150/2022-2023 | BP-2022-23-41 | 15/07/2022 | 15/07/2022 | ASHUTOSH PAL | 0.29 | 0 | 0 | 0
6 | HOOGHLY |  | Central Drilling | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR RAJHATO. | SM/09693 | Augmentation | HIRING OF DIESEL DRIVEN MOTOR CAB (BS-IV & ABOVE) HAVING CONTRACT CARRIAGE PERMIT ALONG WITH DRIVER FOR THE OFFICE OF THE DRILLER-IN-CHARGE, CMSD-II (D), CDD, PHE DTE. |  |  | ORD/000216/2021-2022 | 55/CMSD-II (D) | 31/01/2022 | 07/02/2022 | ASHUTOSH PAL | 0.86 | 0 | 0 | 64
7 | HOOGHLY |  | Central Drilling | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR RAJHATO. | SM/09693 | Augmentation | PROVIDING DRILLING CREW AND OTHER ALLIED WORKS FOR CONSTRUCTION OF TUBE WELL (250MM X 200MM X 240 MTRS DEPTH) BY UTILISING DEPARTMENTAL MACHINERIES FOR AUGMENTATION OF MIDNAPORE MEDICAL COLLEGE & HOSPITAL W/S SCHEME (TW0II) UNDER PASCHIM MIDNAPORE DISTRICT, CDD, PHE DTE. |  |  | ORD/000393/2022-2023 | 1077/CDD | 28/10/2022 | 27/11/2022 | PADMA ENGINEERING & CO. | 16.51 | 4.28 | 25.94 | 0
8 | HOOGHLY |  | Central Drilling | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR RAJHATO. | SM/09693 | Augmentation | MISCELLANEOUS REPAIRING OF MUD PUMP ATTACHED WITH RIG MACHINE NO. KORES/DR/1000 UNDER CMSD-II (D), CDD, PHE DTE. |  |  | ORD/000241/2021-2022 | 634/CMSD-II (D) | 23/12/2021 | 07/01/2022 | M/S B.P.TRADING CORPORATION | 3.28 | 3.22 | 98.03 | 100
9 | HOOGHLY |  | Hooghly Division | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR RAJHATO. | SM/09693 | Augmentation | Sinking of Two Nos Big Dia Tube Well (300 mm X 200 mm) with supply of UPVC pipes & Strainer having depth upto150 Mtr at RAJHATO PWSS of ARAMBAGH Sub-Division under Hooghly Division, PHE Dte. | Assistant Engineer | Junior Engineer (Civill) | ORD/000455/2022-2023 | 2506/HUG | 22/11/2022 | 06/01/2023 | OSMAN SEKH | 22.53 | 22.24 | 98.71 | 100
10 | HOOGHLY |  | Central Drilling | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR RAJHATO. | SM/09693 | Augmentation | Supply & Delivery of Tent for Drilling work at Rajhato PWSS, Dist Hooghly and other PWSS under CDD, PHE Dte. |  |  | ORD/000306/2022-2023 | 336/CMSD-I(D) | 18/07/2022 | 02/08/2022 | M/S S.K.GHOSH & CO. | 4.37 | 4.37 | 100 | 100
11 | HOOGHLY |  | Hooghly Division | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR RAJHATO. | SM/09693 | Augmentation | Supply of UPVC Pipe for TW-III of RAJHATO Water Supply Scheme under Arambagh Sub-Division, of Hooghly Division P.H.E. Dte. [Block-Khanakul-II] | Assistant Engineer |  | ORD/000910/2022-2023 | 209/Arg | 31/03/2023 | 15/04/2023 | OSMAN SEKH | 0.69 | 0.69 | 100 | 100
12 | HOOGHLY |  | Central Drilling | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR RAJHATO. | SM/09693 | Augmentation | Providing drilling crew and other allied works for construction of Tube Well (300mm x 200mm x 150mtrs Depth ) by utilising Departmental Machineries for Rajhato W/S Scheme ,Arambag Block under hooghly District ,CDD,PHE Dte. | Driller In Charge | Junior Engineer | ORD/000005/2023-2024 | 61/CDD | 06/04/2023 | 06/05/2023 | UNIVERSAL ENTERPRISES | 11.38 | 10.14 | 89.14 | 100
13 | HOOGHLY |  | Hooghly Division | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR RAJHATO. | SM/09693 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000161/2021-2022 | 424/2/Hug | 07/03/2022 | 07/03/2022 | Resource Division | 36.05 | 0 | 0 | 0
14 | HOOGHLY |  | Hooghly Division | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR RAJHATO. | SM/09693 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000045/2022-2023 | 1590/Hug | 03/08/2022 | 03/08/2022 | Resource Division | 24.64 | 0 | 0 | 0
15 | HOOGHLY |  | Hooghly Division | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR RAJHATO. | SM/09693 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000075/2022-2023 | 1773/9/Hug | 29/08/2022 | 29/08/2022 | Resource Division | 0.69 | 0 | 0 | 0
16 | HOOGHLY |  | Hooghly Division | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR RAJHATO. | SM/09693 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000142/2023-2024 | 1385/14/Hug | 15/05/2023 | 15/05/2023 | Resource Division | 0.2 | 0 | 0 | 0
17 | HOOGHLY |  | Hooghly Division | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR RAJHATO. | SM/09693 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000177/2022-2023 | 79/23/Hug | 06/01/2023 | 06/01/2023 | Resource Division | 26.55 | 0 | 0 | 0
18 | HOOGHLY |  | Electrical | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR RAJHATO. | SM/09693 | Augmentation | Quotation for New Service Connection of Rajhato(Aug) w/s Scheme, PH No-2 District-Hooghly Under Electrical division PHE Dte |  |  | BILL/01162/2023-2024 | 84 | 10/07/2023 | 10/07/2023 | WBSEDCL | 2.57 | 0 | 0 | 0
19 | HOOGHLY |  | Electrical | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR RAJHATO. | SM/09693 | Augmentation | Quotation bill for New Service connection of Rajhato w/s scheme,TW-I |  |  | BILL/00731/2023-2024 | 20 | 04/05/2023 | 04/05/2023 | WBSEDCL | 2.22 | 0 | 0 | 0
20 | HOOGHLY |  | Hooghly Division | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR RAJHATO. | SM/09693 | Augmentation | Sinking of 3 nos. 300 X200 mm dia Tube Well 210 mtr. Depth by D.R. Rig method using UPVC pipe (CD) and UPVC Deep Well Screen (RDS) For AUGMENTATION Of Gobindapur, Rajhato & Kamarpukur W/S Scheme under Arambagh Sub-Division of Hooghly Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer (Civill) | ORD/000226/2023-2024 | 2038/HUG | 13/07/2023 | 12/08/2023 | SPG ENTERPRISES | 48.51 | 13.73 | 28.31 | 70
21 | HOOGHLY |  | Hooghly Division | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR RAJHATO. | SM/09693 | Augmentation | Repair and Renovation Works of R.C.C. Elevated Reservoir, Boundary Wall of RAJHATO PWSS under Arambagh Sub-Division of Hooghly Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer (Civill) | ORD/000448/2024-2025 | 4083/HUG | 19/12/2024 | 19/03/2025 | M/S PRADYUT KUMAR HAZRA (PARTNERSHIP) | 21.43 | 0 | 0 | 0
22 | HOOGHLY |  | Electrical | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR RAJHATO. | SM/09693 | Augmentation | Supply, delivery & installation of submersible pumping machinery and other electrical/ mechanical equipments etc. including allied works for Augmentation of Rajhato water supply scheme, T.W. No.- I & II, Block: Khanakul-II, District- Hooghly under Electrical Division, PHE Dte. | Assistant Engineer 2 | Junior Engineer4 | ORD/000289/2022-2023 | 939/ED | 22/02/2023 | 23/05/2023 | MAA KALI ENTERPRISE | 21.48 | 21.31 | 99.25 | 60
23 | HOOGHLY |  | Hooghly Division | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR RAJHATO. | SM/09693 | Augmentation | Construction of 3.6 m X 3.0 m Switch Room with Sanitary and Water Supply & Sanitation arrangement , Boundary Wall in Proposed T.W Site,Laying rising main pipe for inter connection between T.W & Distribution For Augmentation of RAJHATO Piped Water Supply Scheme under Arambagh Sub-Division of Hooghly Division P.HE Dte. within Khanakul-II Block. | Assistant Engineer | Junior Engineer (Civill) | ORD/000124/2023-2024 | 1458/HUG | 18/05/2023 | 17/06/2023 | BENGAL TRADERS | 10.29 | 10.28 | 99.92 | 100
24 | HOOGHLY |  | Hooghly Division | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR RAJHATO. | SM/09693 | Augmentation | Augmentation of RAJHATO Water Supply Scheme with LDS, Switch room, Boundary wall,Rising Main,FHTC Work, of existing Switch Rooms& Boundary Wall at Khanakul-II Block. | Assistant Engineer | Junior Engineer (Civill) | ORD/000190/2022-2023 | 826//Hug | 20/04/2022 | 02/10/2025 | M/S PRADYUT KUMAR HAZRA | 404.28 | 365.14 | 90.32 | 80
Total | [13 empty] | 668.2 | 459.2 | 68.72