## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | HOOGHLY |  | Hooghly Division | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR RAJBALHAT. | SM/09694 | Augmentation | Preparation of DPR for Augmentation of Rajbalhat (Zone-I & II) Water Supply Scheme under Serampore Sub-Division of Hooghly Division, P.H.E. Dte. [Block-Jangipara] | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/000396/2021-2022 | 289/SER | 18/02/2022 | 10/03/2022 | SRIJAN ECHOLOGICAL UPLIFTMENT PVT. LTD. | 4.01 | 4.01 | 100 | 100
2 | HOOGHLY |  | Hooghly Division | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR RAJBALHAT. | SM/09694 | Augmentation | Preparation of DPR for Augmentation of Rajbalhat (Zone-III) Water Supply Scheme under Serampore Sub-Division of Hooghly Division, P.H.E. Dte. [Block-Jangipara] | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/000397/2021-2022 | 301/SER | 21/02/2022 | 13/03/2022 | SRIJAN ECHOLOGICAL UPLIFTMENT PVT. LTD. | 2.12 | 1.96 | 92.42 | 100
3 | HOOGHLY |  | Central Drilling | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR RAJBALHAT. | SM/09694 | Augmentation | PROVIDING DRILLING CREWS FOR CONSTRUCTION OF TUBE WELL (300MM X 200MM X 180 MTRS DEPTH) BY KORES RIG MACHINE FOR RAJBALHAT W/S SCHEME, JANGIPARA BLOCK UNDER HOOGHLY DISTRICT, CMSD-II (D), CDD, PHE DTE. | Driller In Charge | Junior Engineer | ORD/000101/2022-2023 | 231/CMSD-II (D) | 20/05/2022 | 04/06/2022 | M/S PRACHI ENGINEERING | 2.4 | 2.23 | 92.79 | 100
4 | HOOGHLY |  | Central Drilling | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR RAJBALHAT. | SM/09694 | Augmentation | SUPPLY & DELIVERY OF PEA SIZE GRAVELS AND BENTONITE POWDER SODIUM BASED AT SITE FOR CONSTRUCTION OF TUBE WELL AT RAJBALHAT W/S SCHEME IN HOOGHLY DISTRICT UNDER CMSD-II (D), CDD, PHE DTE. | Driller In Charge | Junior Engineer | ORD/000102/2022-2023 | 237/CMSD-II (D) | 20/05/2022 | 04/06/2022 | M/S SAIKAT ENTERPRISE | 2.08 | 1.9 | 91.33 | 100
5 | HOOGHLY |  | Central Drilling | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR RAJBALHAT. | SM/09694 | Augmentation | PROVIDING TUBE WELL MATERIALS OF 300 MM NOMINAL DIA CONFORMING TO IS: 12818:2010 WITH OTHER MATERIALS AT SITE FOR CONSTRUCTION OF TUBE WELL ATY RAJBALHAT W/S SCHEME UNDER HOOGHLY DISTRICT, CMSD-II (D), CDD, PHE DTE. | Driller In Charge | Junior Engineer | ORD/000100/2022-2023 | 233/CMSD-II (D) | 20/05/2022 | 04/06/2022 | M/S PRACHI ENGINEERING | 2.79 | 2.79 | 100 | 100
6 | HOOGHLY |  | Central Drilling | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR RAJBALHAT. | SM/09694 | Augmentation | PROVIDING TUBE WELL MATERISLS OF 200 MM NOMINAL DIA. CONFORMING TO IS: 12818:2010 WITH OTHER MATERIALS AT SITE FOR CONSTRUCTION OF TUBE WELL AT RAJBALHAT W/S SCHEME, UNDER HOOGHLY DISTRICT, CMSD-II (D), CDD, PHE DTE. | Driller In Charge | Junior Engineer | ORD/000099/2022-2023 | 234/CMSD-II (D) | 20/05/2022 | 04/06/2022 | M/S PRACHI ENGINEERING | 3.87 | 3.41 | 88.01 | 90
7 | HOOGHLY |  | Electrical | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR RAJBALHAT. | SM/09694 | Augmentation | Quatation Bill for New Service Connection of WBSEDCL at Aug. of Rajbalhat W/S. Sch. PH-III |  |  | BILL/00015/2022-2023 | BP-2022-23-114 | 14/12/2022 | 14/12/2022 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 8.48 | 0 | 0 | 0
8 | HOOGHLY |  | Hooghly Division | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR RAJBALHAT. | SM/09694 | Augmentation | Augmentation of RAJBALHAT Water Supply Scheme with Laying Distribution System, Rising Main, Construction of 3.6 M X3.00 M Switch Room, Boundary wall, Repairing of O.H.R, Bounday wall, Existing Switch Room & FHTC at Jangipara Block under Serampore Sub-Division of Hooghly Division, P.H.E. Dte., Dist. Hooghly. | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/000043/2022-2023 | 827/Hug | 20/04/2022 | 17/10/2022 | DIPTI TRADERS | 458.18 | 444.62 | 97.04 | 70
9 | HOOGHLY |  | Electrical | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR RAJBALHAT. | SM/09694 | Augmentation | Supply, delivery & installation of submersible pumping machinery and other electrical/ mechanical equipments etc. including allied works for Rajbalhat water supply scheme, T.W. No. IV, Block: Jangipara, District- Hooghly under Electrical Division, PHE Dte. | Assistant Engineer Howrah mechanical Sub Division | Junior Engineer2 | ORD/000061/2023-2024 | 1640/ED | 11/04/2023 | 10/07/2023 | SUDIKSHA CONSTRUCTION | 10.68 | 10.39 | 97.31 | 0
10 | HOOGHLY |  | Hooghly Division | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR RAJBALHAT. | SM/09694 | Augmentation | Sinking of One No Big Dia Tube Well (300 mm X 200 mm) with supply of UPVC pipes & Strainer having depth upto180 Mtr at RAJBALHAT ZONE-III PWSS of SERAMPORE Sub-Division under Hooghly Division, PHE Dte. | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/000446/2022-2023 | 2482/HUG | 21/11/2022 | 21/12/2022 | R CONSTRUCTION | 12.44 | 11.72 | 94.23 | 0
11 | HOOGHLY |  | Hooghly Division | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR RAJBALHAT. | SM/09694 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000158/2021-2022 | 422/3/Hug | 07/03/2022 | 07/03/2022 | Resource Division | 39.63 | 0 | 0 | 0
12 | HOOGHLY |  | Hooghly Division | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR RAJBALHAT. | SM/09694 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000009/2022-2023 | 1122/6/HUG | 06/06/2022 | 06/06/2022 | Resource Division | 12.32 | 0 | 0 | 0
13 | HOOGHLY |  | Hooghly Division | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR RAJBALHAT. | SM/09694 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000320/2023-2024 | 1384/17/Hug | 15/05/2023 | 15/05/2023 | Resource Division | 1.71 | 0 | 0 | 0
14 | HOOGHLY |  | Electrical | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR RAJBALHAT. | SM/09694 | Augmentation | Quoation bill for new service connection at Rajbalhat |  |  | BILL/00775/2022-2023 | 151 | 08/02/2023 | 08/02/2023 | WBSEDCL | 3.85 | 0 | 0 | 0
15 | HOOGHLY |  | Hooghly Division | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR RAJBALHAT. | SM/09694 | Augmentation | Repairing of Damaged Road due to FHTC Works at Northern zone of Rajbalhat W/S Scheme under Serampore Sub-Division of Hooghly Division P.H.E.Dte. | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/000202/2024-2025 | 547/SER | 19/09/2024 | 26/09/2024 | M/S SHIVAM UDYOG | 4.99 | 0 | 0 | 99
16 | HOOGHLY |  | Hooghly Division | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR RAJBALHAT. | SM/09694 | Augmentation | Repairing of Damaged Road due to FHTC Works at Southern zone of Rajbalhat W/S Scheme under Serampore Sub-Division of Hooghly Division P.H.E.Dte. | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/000207/2024-2025 | 552/SER | 19/09/2024 | 26/09/2024 | ARUN SEAL AND CO. | 4.99 | 0 | 0 | 99
17 | HOOGHLY |  | Hooghly Division | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR RAJBALHAT. | SM/09694 | Augmentation | Repairing of Damaged Road due to FHTC Works at Western zone of Rajbalhat W/S Scheme under Serampore Sub-Division of Hooghly Division P.H.E.Dte. | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/000209/2024-2025 | 554/SER | 19/09/2024 | 26/09/2024 | ARUN SEAL AND CO. | 4.97 | 0 | 0 | 99
18 | HOOGHLY |  | Hooghly Division | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR RAJBALHAT. | SM/09694 | Augmentation | Repairing of Damaged Road due to FHTC Works at Eastern zone of Rajbalhat W/S Scheme under Serampore Sub-Division of Hooghly Division P.H.E.Dte. | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/000193/2024-2025 | 536/SER | 17/09/2024 | 24/09/2024 | M/S SHIVAM UDYOG | 4.98 | 0 | 0 | 99
19 | HOOGHLY |  | Electrical | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR RAJBALHAT. | SM/09694 | Augmentation | Quotation money deposition for new service connection at Rajbalhat w/s scheme, T.W. No.-V, Dist.-Hooghly under PHE Dte. Application No- 5004123576 Reference ID- 503622497 SM Code- 09694 |  |  | BILL/01402/2024-2025 | 345 | 31/07/2024 | 31/07/2024 | WBSEDCL | 3.8 | 0 | 0 | 0
20 | HOOGHLY |  | Electrical | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR RAJBALHAT. | SM/09694 | Augmentation | Quotation money deposition for new service connection at Rajbalhat w/s scheme, T.W. No.-V, Dist.-Hooghly under PHE Dte. Application No- 100000118583 Reference ID- 860312463 SM Code- 09694 |  |  | BILL/01992/2024-2025 | 480 | 01/10/2024 | 01/10/2024 | WBSEDCL | 1.63 | 0 | 0 | 0
21 | HOOGHLY |  | Hooghly Division | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR RAJBALHAT. | SM/09694 | Augmentation | Providing 200 nos. FHTC of Rajbalhat and its Adjoining Mouzas Water Supply Scheme Under Serampore Sub-Division of Hooghly Division P.H.E Dte. [Block- Jangipara]. | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/000648/2023-2024 | 3479/HUG | 29/11/2023 | 30/09/2024 | SADHUKHAN ENTERPRISE | 21.58 | 16.02 | 74.23 | 99
22 | HOOGHLY |  | Hooghly Division | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR RAJBALHAT. | SM/09694 | Augmentation | Laying pipe line within Morhal & Rajbalhat Mouza in Rajbalhat W/S Scheme under Serampore Sub-Division of Hooghly Division, P.H.E. Dte. | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/001259/2024-2025 | 59/SER | 20/01/2025 | 27/01/2025 | ARUN SEAL AND CO. | 5 | 0 | 0 | 0
23 | HOOGHLY |  | Hooghly Division | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR RAJBALHAT. | SM/09694 | Augmentation | Shifting of existing water supply pipeline due to widening & strengthening of Box Culvert at neart Brindabon Chak, Badur Chak, Rajbalhat & Hariharpur, Block- Jangipara under Rajbalhat Water Supply Scheme Under Serampore Sub-Division of Hooghly Division P.H.E Dte . | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/001307/2024-2025 | 79/SER | 20/01/2025 | 30/01/2025 | ARUN SEAL AND CO. | 3.98 | 0 | 0 | 0
24 | HOOGHLY |  | Hooghly Division | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR RAJBALHAT. | SM/09694 | Augmentation | Sinking of 3rd tube-well by D.R. Rig method, Construction of 3.6 m X 3.0 m Switch Room with Sanitary and Water Supply arrangement, Construction of Boundary Wall, Laying rising main pipe for inter connection between Proposed T.W & Distribution of RAJBALHAT Piped Water Supply Scheme under SERAMPORE Sub-Division of Hooghly Division P.HE Dte. | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/000754/2023-2024 | 389/HUG | 08/02/2024 | 01/03/2025 | KAJAL DEY | 31.66 | 19.1 | 60.33 | 99
25 | HOOGHLY |  | Hooghly Division | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR RAJBALHAT. | SM/09694 | Augmentation | Construction of 2 nos. Boundary wall at existing 3rd & 4th tubewell sites. under RAJBALHAT PWSS under Serampore Sub-Division of Hooghly Division P.H.E. Dte. | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/000905/2023-2024 | 828/HUG | 11/03/2024 | 01/12/2024 | SUDIPTA SINHA | 13.7 | 8.64 | 63.03 | 99
26 | HOOGHLY |  | Electrical | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR RAJBALHAT. | SM/09694 | Augmentation | Supply, delivery & installation of submersible pumping machinery and other electrical/ mechanical equipments etc. including allied works for Rajbalhat water supply scheme, T.W. No. III, Block: Jangipara, District- Hooghly under Electrical Division, PHE Dte. | Assistant Engineer Howrah mechanical Sub Division | Junior Engineer2 | ORD/000168/2022-2023 | 3501/ED | 30/12/2022 | 10/09/2026 | MAA KALI ENTERPRISE | 10.68 | 10.39 | 97.31 | 100
27 | HOOGHLY |  | Electrical | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR RAJBALHAT. | SM/09694 | Augmentation | Supply, delivery & installation of submersible pumping machinery and other electrical / mechanical equipments etc. including allied works for RAJBALHAT PIPED W/S SCHEME, T.W. No. V, District - Hooghly under JJM Program under Electrical Division PHE Dte. | Assistant Engineer 1,Assistant Engineer Howrah mechanical Sub Division | Junior Engineer2 | ORD/002580/2023-2024 | 456/ED | 05/03/2024 | 24/05/2026 | D. K. ELECTRIC | 9.7 | 6.94 | 71.57 | 65
Total | [13 empty] | 686.21 | 544.11 | 79.29