## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | HOOGHLY |  | Hooghly Division | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR JANAI BLOCK: CHANDITALA-II | SM/09695 | Augmentation | Preparation of DPR for Augmentation of Janai (Zone-I) Water Supply Scheme under Serampore Sub-Division of Hooghly Division, P.H.E. Dte. [Block-Chanditala-II] | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/000398/2021-2022 | 302/SER | 21/02/2022 | 13/03/2022 | SRIJAN ECHOLOGICAL UPLIFTMENT PVT. LTD. | 2.59 | 2.59 | 100 | 100
2 | HOOGHLY |  | Hooghly Division | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR JANAI BLOCK: CHANDITALA-II | SM/09695 | Augmentation | Preparation of DPR for Augmentation of Janai (Zone-II) Water Supply Scheme under Serampore Sub-Division of Hooghly Division, P.H.E. Dte. [Block-Chanditala-II] | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/000399/2021-2022 | 303/SER | 21/02/2022 | 13/03/2022 | SRIJAN ECHOLOGICAL UPLIFTMENT PVT. LTD. | 1.77 | 1.62 | 91.57 | 100
3 | HOOGHLY |  | Hooghly Division | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR JANAI BLOCK: CHANDITALA-II | SM/09695 | Augmentation | Sinking of One No Big Dia Tube Well (300 mm X 200 mm) with supply of uPVC pipes & Strainer having depth upto150 Mtr at JANAI ZONE-II PWSS of SERAMPORE Sub-Division under Hooghly Division, PHE Dte. | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/000452/2022-2023 | 2502/HUG | 22/11/2022 | 22/12/2022 | DOULPHINE ENTERPRISE (RANJIT KHANRA) | 10.95 | 10.2 | 93.16 | 0
4 | HOOGHLY |  | Electrical | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR JANAI BLOCK: CHANDITALA-II | SM/09695 | Augmentation | Quatation Bill for New Service Connection of WBSEDCL at Janai W/S. Sch. |  |  | BILL/00537/2022-2023 | 131 | 16/01/2023 |  | WBSEDCL | 0.68 | 0 | 0 | 0
5 | HOOGHLY |  | Electrical | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR JANAI BLOCK: CHANDITALA-II | SM/09695 | Augmentation | Supply, delivery & installation of submersible pumping machinery and other electrical/ mechanical equipments etc. including allied works for Augmentation of Janai water supply scheme, T.W. No.- I, Block: Chanditala-II, District- Hooghly under Electrical Division, PHE Dte. | Assistant Engineer Howrah mechanical Sub Division | Junior Engineer2 | ORD/000102/2022-2023 | 648/ED | 02/02/2023 | 03/05/2023 | M/S BABUSONA ENTERPRISE | 10.74 | 10.47 | 97.41 | 100
6 | HOOGHLY |  | Hooghly Division | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR JANAI BLOCK: CHANDITALA-II | SM/09695 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000321/2023-2024 | 1384/18/Hug | 15/05/2023 |  | Resource Division | 9.36 | 0 | 0 | 0
7 | HOOGHLY |  | Hooghly Division | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR JANAI BLOCK: CHANDITALA-II | SM/09695 | Augmentation | Augmentation of Janai Zone-I Water Supply Scheme with Construction of 450 cum capacity RCC OHR with 20 mtr. staging height including Soil Investigation work including Laying Distribution System, Rising Main, FHTC, of existing Switch Room, Boundary Wall & at Chanditala-II Block under Serampore Sub-Division of Hooghly Division, P.H.E. Dte., Dist. Hooghly. | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/000191/2022-2023 | 868//hug | 27/04/2022 | 21/02/2023 | DOULPHINE ENTERPRISE (RANJIT KHANRA) | 378.23 | 343.15 | 90.72 | 100
8 | HOOGHLY |  | Electrical | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR JANAI BLOCK: CHANDITALA-II | SM/09695 | Augmentation | Adhoc Payment to WBSEDCL against Service Connection |  |  | BILL/01124/2023-2024 | null | 28/06/2023 |  | WBSEDCL | 89.37 | 0 | 0 | 0
9 | HOOGHLY |  | Hooghly Division | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR JANAI BLOCK: CHANDITALA-II | SM/09695 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000157/2021-2022 | 422/2/Hug | 07/03/2022 |  | Resource Division | 39.63 | 0 | 0 | 0
10 | HOOGHLY |  | Hooghly Division | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR JANAI BLOCK: CHANDITALA-II | SM/09695 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000007/2022-2023 | 1122/4/HUG | 06/06/2022 |  | Resource Division | 12.32 | 0 | 0 | 0
11 | HOOGHLY |  | Hooghly Division | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR JANAI BLOCK: CHANDITALA-II | SM/09695 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000059/2022-2023 | 1689/3/HUG | 22/08/2022 |  | Resource Division | 19.89 | 0 | 0 | 0
12 | HOOGHLY |  | Hooghly Division | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR JANAI BLOCK: CHANDITALA-II | SM/09695 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000044/2022-2023 | 1369/Hug | 06/07/2022 |  | Resource Division | 15.6 | 0 | 0 | 0
13 | HOOGHLY |  | Hooghly Division | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR JANAI BLOCK: CHANDITALA-II | SM/09695 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000123/2022-2023 | 2210/2/Hug | 30/09/2022 |  | Resource Division | 0.05 | 0 | 0 | 0
14 | HOOGHLY |  | Hooghly Division | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR JANAI BLOCK: CHANDITALA-II | SM/09695 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000035/2022-2023 | 1291/3/Hug | 24/06/2022 |  | Resource Division | 6.16 | 0 | 0 | 0
15 | HOOGHLY |  | Hooghly Division | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR JANAI BLOCK: CHANDITALA-II | SM/09695 | Augmentation | Extension of Laying Distribution System for proposed Augemntation of JANAI Zone-I & II Water Supply Scheme Under Serampore Sub-Division under Hooghly Division,P.H.E Dte | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/000231/2023-2024 | 2064/HUG | 17/07/2023 | 15/10/2023 | M/S SHIVAM UDYOG | 41.09 | 19.84 | 48.29 | 99
16 | HOOGHLY |  | Hooghly Division | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR JANAI BLOCK: CHANDITALA-II | SM/09695 | Augmentation | Augmentation of Janai Zone-II Water Supply Scheme with Laying Distribution System, Laying Rising Main, Providing FHTC and Construction of 3.6 M X 3.00 M Switch Room, Boundary wall at Chanditala-II Block under Serampore Sub-Division of Hooghly Division, P.H.E. Dte., Dist. Hooghly. | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/000050/2022-2023 | 834/Hug | 20/04/2022 | 19/07/2022 | M/S S.C CIVIL ENTERPRISE | 146.57 | 94.11 | 64.21 | 65
17 | HOOGHLY |  | Hooghly Division | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR JANAI BLOCK: CHANDITALA-II | SM/09695 | Augmentation | Additional works for laying of water supply pipeline by HDD process and Protection of Pipe Line along Pond embankment and road side at Zone II of JANAI Water Supply Scheme under Serampore SubDivision, P.H.E. Dte. |  |  | ORD/000869/2023-2024 | 744/HUG | 05/03/2024 | 04/04/2024 | S AND P CONSTRUCTION | 45.19 | 0 | 0 | 0
18 | HOOGHLY |  | Hooghly Division | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR JANAI BLOCK: CHANDITALA-II | SM/09695 | Augmentation | Designing making and erection of Display Board using logo and tag line of Jal Jeevan Mission to be placed at different work sites and HGJ villages for awareness generation among the people in the district of Hooghly under Serampore Sub Division under Hooghly Division PHE Dte. 1. Kapasharia PWSS 2. Janai PWSS 3. Begampur PWSS 4. Baksa PWSS 5. Chikrand PWSS 6. Kharsarai PWSS | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/000941/2023-2024 | 111/SER | 23/02/2024 | 01/03/2024 | AMBIAN INFRASTRUCTURE | 0.95 | 0.48 | 50 | 80
19 | HOOGHLY |  | Electrical | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR JANAI BLOCK: CHANDITALA-II | SM/09695 | Augmentation | Quotation money deposition for new service connection at Janai w/s scheme, Zone- II, T.W. No.-II, Dist.-Hooghly under PHE Dte. Application No- 5004099413 Reference ID- 503611354 SM Code- 09695 |  |  | BILL/00159/2024-2025 | 71 | 16/04/2024 |  | WBSEDCL | 4.56 | 0 | 0 | null
20 | HOOGHLY |  | Electrical | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR JANAI BLOCK: CHANDITALA-II | SM/09695 | Augmentation | Quotation money deposition for new service connection at Janai w/s scheme, Zone- II, T.W. No.-II, Dist.-Hooghly under PHE Dte. Application No- 5004099413 Reference ID- 503611354 SM Code- 09695 |  |  | BILL/00159/2024-2025 | 71 | 16/04/2024 |  | WBSEDCL | 4.56 | 0 | 0 | null
21 | HOOGHLY |  | Hooghly Division | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR JANAI BLOCK: CHANDITALA-II | SM/09695 | Augmentation | Sinking of Additional 300 X 200 mm dia Tubewell 180 mtr depth, Construction of Switch Room, Boundary wall and rising main with interconnection at Janai W/s Scheme (Zone-II), Chanditala-II Block under Hooghly Division PHE Dte. | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/000742/2023-2024 | 377/HUG | 08/02/2024 | 08/05/2024 | M/S SHIVAM UDYOG | 35 | 12.35 | 35.28 | 30
22 | HOOGHLY |  | Electrical | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR JANAI BLOCK: CHANDITALA-II | SM/09695 | Augmentation | Supply, delivery & installation of submersible pumping machinery and other electrical / mechanical equipments etc. including allied works for JANAI PIPED W/S SCHEME, Zone - II, T.W. No. II, Block: Chanditala - II, District - Hooghly under JJM Program under Electrical Division PHE Dte. | Assistant Engineer Howrah mechanical Sub Division | Junior Engineer2 | ORD/000171/2024-2025 | 1194/ED | 14/06/2024 | 12/09/2024 | DAS ENTERPRISE | 10.73 | 8.42 | 78.44 | 30
23 | HOOGHLY |  | Hooghly Division | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR JANAI BLOCK: CHANDITALA-II | SM/09695 | Augmentation | CONSTRUCTION OF 2NOS. TEMPORARY KIOSK FOR THE NECESSARY ARRANGEMENT OF ELECTRIFICATION OF TUBEWELL AT JANAI (ZONE-II) 2ND TW SITE AND CHANDITALA PWSS NEAR THERO AREA UNDER SERAMPORE SUB-DIVISION OF HOOGHLY DIVISION P.H.E DTE. | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/000142/2024-2025 | 428/SER | 31/07/2024 | 15/08/2024 | SRI KRISHNA ENTERPRISE | 0.68 | 0.33 | 48.58 | 95
Total | [13 empty] | 886.69 | 503.55 | 56.79