## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | HOOGHLY |  | Hooghly Division | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR ANUR. | SM/09698 | Augmentation | Preparation of DPR for Augmentation of ANUR Piped Water Supply Scheme Under Arambagh Sub-Division of Hooghly Division P.H.E Dte. [Block-Goghat-II]. | Assistant Engineer | Junior Engineer (Civill) | ORD/000379/2021-2022 | 610/Arg | 31/12/2021 | 30/01/2022 | SRIJAN ECOLOGICAL UPLIFTMENT PVT. LTD. | 3.48 | 0 | 0 | 100
2 | HOOGHLY |  | Hooghly Division | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR ANUR. | SM/09698 | Augmentation | Sinking of I (one) No Big dia tube well (250 mm X150mm) with supply of PVC Pipe and strainer and having depth upto 150 M at 4th TW site of Sabalsinghapur W/S Scheme under Arambagh Sub-Division of Hooghly Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer (Civill) | ORD/000143/2022-2023 | 1414/HUG | 12/07/2022 | 11/08/2022 | OSMAN SEKH | 8.6 | 0 | 0 | 100
3 | HOOGHLY |  | Hooghly Division | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR ANUR. | SM/09698 | Augmentation | Augmentation of ANUR (ZONE-I) Water Supply Scheme with Laying Distribution System & Functional Household Tap Connection, Repairing of Switch room, Boundary wall, existing OHR at GOGHAT-II Block under Arambag Sub-Division, PHE Dte. | Assistant Engineer | Junior Engineer (Civill) | ORD/000185/2022-2023 | 1600/Hug | 04/08/2022 | 18/10/2022 | SIBSANKAR CHOWDHURY | 200.45 | 0 | 0 | 40
4 | HOOGHLY |  | Electrical | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR ANUR. | SM/09698 | Augmentation | Supply, delivery & installation of submersible pumping machinery and other electrical/ mechanical equipments etc. including allied works for Augmentation of Anur water supply scheme, T.W. No.- I, Block: Goghat-II, District- Hooghly under Electrical Division, PHE Dte. |  |  | ORD/000194/2022-2023 | 820/ED | 14/02/2023 | 15/05/2023 | SUTRADHAR TRADERS | 10.78 | 0 | 0 | 0
5 | HOOGHLY |  | Hooghly Division | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR ANUR. | SM/09698 | Augmentation | Augmentation of ANUR (ZONE-II) Water Supply Scheme with Laying Distribution System & Functional Household Tap Connection, Construction of Switch Room, Boundary Wall of 3rd T.W. Site at GOGHAT-II Block under Arambag Sub-Division, PHE Dte. | Assistant Engineer | Junior Engineer (Civill) | ORD/000096/2022-2023 | 1087/Hug | 02/06/2022 | 12/07/2022 | M/S SHIVAM UDYOG | 81.78 | 0 | 0 | 100
6 | HOOGHLY |  | Hooghly Division | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR ANUR. | SM/09698 | Augmentation | Sinking of One No Big Dia Tube Well (300 mm X 200 mm) with supply of uPVC pipes & Strainer having depth upto180 Mtr at ANUR PWSS of ARAMBAGH Sub-Division under Hooghly Division, PHE Dte. | Assistant Engineer | Junior Engineer (Civill) | ORD/000453/2022-2023 | 2503/HUG | 22/11/2022 | 22/12/2022 | M/S SHIVAM UDYOG | 12.72 | 0 | 0 | 0
7 | HOOGHLY |  | Hooghly Division | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR ANUR. | SM/09698 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000160/2021-2022 | 424/1/Hug | 07/03/2022 | 07/03/2022 | Resource Division | 36.05 | 0 | 0 | 0
8 | HOOGHLY |  | Hooghly Division | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR ANUR. | SM/09698 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000089/2022-2023 | 1773/23/Hug | 29/08/2022 | 29/08/2022 | Resource Division | 0.69 | 0 | 0 | 0
9 | HOOGHLY |  | Hooghly Division | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR ANUR. | SM/09698 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000049/2022-2023 | 1590/4/Hug | 03/08/2022 | 03/08/2022 | Resource Division | 18.48 | 0 | 0 | 0
10 | HOOGHLY |  | Hooghly Division | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR ANUR. | SM/09698 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000149/2023-2024 | 1385/20/Hug | 15/05/2023 | 15/05/2023 | Resource Division | 2.3 | 0 | 0 | 0
11 | HOOGHLY |  | Electrical | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR ANUR. | SM/09698 | Augmentation | Quotation Bill for New Service Connection at Annur W/S. Sch. Z-II, PH-I |  |  | BILL/00912/2022-2023 | 186 | 13/03/2023 | 13/03/2023 | WBSEDCL | 4.44 | 0 | 0 | 0
12 | HOOGHLY |  | Hooghly Division | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR ANUR. | SM/09698 | Augmentation | Sinking of 2 nos 300 X200 mm dia Tube Well, 210 mtr. Depth by D.R. Rig method using UPVC pipe (CD) and UPVC Deep Well Screen (RDS) at Proposed Tube Well Siteof ANUR W/S Scheme under Arambagh Sub-Division of Hooghly Division, P.H.E. Dte. | Assistant Engineer |  | ORD/000172/2024-2025 | 3168/HUG | 10/09/2024 | 10/10/2024 | KALPATARU ENTERPRISE | 32.25 | 0 | 0 | 0
13 | HOOGHLY |  | Hooghly Division | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR ANUR. | SM/09698 | Augmentation | Repair and Renovation Works of R.C.C. Elevated Reservoir, Boundary Wall, Switch Room of ANUR PWSS under Arambagh Sub-Division of Hooghly Division, P.H.E. Dte. |  |  | ORD/000445/2024-2025 | 4086/HUG | 19/12/2024 | 19/03/2025 | DHIRENDRA ENGINEERING & CONSTRUCTION | 9.58 | 0 | 0 | 0
14 | HOOGHLY |  | Hooghly Division | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR ANUR. | SM/09698 | Augmentation | Designing making and erection of Display Board using logo and tag line of LAND DEMARCATION OF P.H.E. Dte. to the placed at different work sites and HGJ villages for awareness generation among the people in the district of Hooghly under ARAMBAGH Sub Division under Hooghly Division PHE Dte. (1) SAOTA PWSS- 3nos (2) ANUR PWSS- 3nos (3) Badanganj PWSS (Z- I)- 4nos (4) Badanganj PWSS (Z- II)-4nos | Assistant Engineer | Junior Engineer (Civill) | ORD/000416/2024-2025 | 808/Arg | 23/08/2024 | 31/12/2024 | DHIRENDRA ENGINEERING & CONSTRUCTION | 0.98 | 0 | 0 | 100
15 | HOOGHLY |  | Electrical | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR ANUR. | SM/09698 | Augmentation | Quotation money deposition for new service connection at kamarpukur,Anur w/s scheme, T.W. No.-III, Dist.-Hooghly under PHE Dte. Application No- 5004182874 Reference ID- 503645387 SM Code- 09698 |  |  | BILL/00484/2024-2025 | 147 | 22/05/2024 | 22/05/2024 | WBSEDCL | 5.57 | 0 | 0 | 0
Total | [13 empty] | 428.15 | 0 | 0