## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | HOOGHLY |  | Hooghly Division | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR ANUR. | SM/09698 | Augmentation | Preparation of DPR for Augmentation of ANUR Piped Water Supply Scheme Under Arambagh Sub-Division of Hooghly Division P.H.E Dte. [Block-Goghat-II]. | Assistant Engineer | Junior Engineer (Civill) | ORD/000379/2021-2022 | 610/Arg | 31/12/2021 | 30/01/2022 | SRIJAN ECOLOGICAL UPLIFTMENT PVT. LTD. | 3.48 | 3.48 | 100 | 100
2 | HOOGHLY |  | Hooghly Division | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR ANUR. | SM/09698 | Augmentation | Sinking of I (one) No Big dia tube well (250 mm X150mm) with supply of PVC Pipe and strainer and having depth upto 150 M at 4th TW site of Sabalsinghapur W/S Scheme under Arambagh Sub-Division of Hooghly Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer (Civill) | ORD/000143/2022-2023 | 1414/HUG | 12/07/2022 | 11/08/2022 | OSMAN SEKH | 8.6 | 8.44 | 98.1 | 100
3 | HOOGHLY |  | Hooghly Division | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR ANUR. | SM/09698 | Augmentation | Sinking of One No Big Dia Tube Well (300 mm X 200 mm) with supply of uPVC pipes & Strainer having depth upto180 Mtr at ANUR PWSS of ARAMBAGH Sub-Division under Hooghly Division, PHE Dte. | Assistant Engineer | Junior Engineer (Civill) | ORD/000453/2022-2023 | 2503/HUG | 22/11/2022 | 22/12/2022 | M/S SHIVAM UDYOG | 12.72 | 10.81 | 85.03 | 0
4 | HOOGHLY |  | Electrical | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR ANUR. | SM/09698 | Augmentation | Quotation Bill for New Service Connection at Annur W/S. Sch. Z-II, PH-I |  |  | BILL/00912/2022-2023 | 186 | 13/03/2023 |  | WBSEDCL | 4.44 | 0 | 0 | 0
5 | HOOGHLY |  | Hooghly Division | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR ANUR. | SM/09698 | Augmentation | Augmentation of ANUR (ZONE-I) Water Supply Scheme with Laying Distribution System & Functional Household Tap Connection, Repairing of Switch room, Boundary wall, existing OHR at GOGHAT-II Block under Arambag Sub-Division, PHE Dte. | Assistant Engineer | Junior Engineer (Civill) | ORD/000185/2022-2023 | 1600/Hug | 04/08/2022 | 18/10/2022 | SIBSANKAR CHOWDHURY | 200.45 | 127.81 | 63.76 | 40
6 | HOOGHLY |  | Hooghly Division | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR ANUR. | SM/09698 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000149/2023-2024 | 1385/20/Hug | 15/05/2023 |  | Resource Division | 2.3 | 0 | 0 | 0
7 | HOOGHLY |  | Electrical | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR ANUR. | SM/09698 | Augmentation | Supply, delivery & installation of submersible pumping machinery and other electrical/ mechanical equipments etc. including allied works for Augmentation of Anur water supply scheme, T.W. No.- I, Block: Goghat-II, District- Hooghly under Electrical Division, PHE Dte. |  |  | ORD/000194/2022-2023 | 820/ED | 14/02/2023 | 15/05/2023 | SUTRADHAR TRADERS | 10.78 | 10.75 | 99.77 | 0
8 | HOOGHLY |  | Hooghly Division | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR ANUR. | SM/09698 | Augmentation | Augmentation of ANUR (ZONE-II) Water Supply Scheme with Laying Distribution System & Functional Household Tap Connection, Construction of Switch Room, Boundary Wall of 3rd T.W. Site at GOGHAT-II Block under Arambag Sub-Division, PHE Dte. | Assistant Engineer | Junior Engineer (Civill) | ORD/000096/2022-2023 | 1087/Hug | 02/06/2022 | 12/07/2022 | M/S SHIVAM UDYOG | 81.78 | 69.32 | 84.77 | 100
9 | HOOGHLY |  | Hooghly Division | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR ANUR. | SM/09698 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000160/2021-2022 | 424/1/Hug | 07/03/2022 |  | Resource Division | 36.05 | 0 | 0 | 0
10 | HOOGHLY |  | Hooghly Division | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR ANUR. | SM/09698 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000089/2022-2023 | 1773/23/Hug | 29/08/2022 |  | Resource Division | 0.69 | 0 | 0 | 0
11 | HOOGHLY |  | Hooghly Division | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR ANUR. | SM/09698 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000049/2022-2023 | 1590/4/Hug | 03/08/2022 |  | Resource Division | 18.48 | 0 | 0 | 0
12 | HOOGHLY |  | Electrical | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR ANUR. | SM/09698 | Augmentation | Quotation money deposition for new service connection at kamarpukur,Anur w/s scheme, T.W. No.-III, Dist.-Hooghly under PHE Dte. Application No- 5004182874 Reference ID- 503645387 SM Code- 09698 |  |  | BILL/00484/2024-2025 | 147 | 22/05/2024 |  | WBSEDCL | 5.57 | 0 | 0 | null
13 | HOOGHLY |  | Hooghly Division | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR ANUR. | SM/09698 | Augmentation | Sinking of 2 nos 300 X200 mm dia Tube Well, 210 mtr. Depth by D.R. Rig method using UPVC pipe (CD) and UPVC Deep Well Screen (RDS) at Proposed Tube Well Siteof ANUR W/S Scheme under Arambagh Sub-Division of Hooghly Division, P.H.E. Dte. | Assistant Engineer |  | ORD/000172/2024-2025 | 3168/HUG | 10/09/2024 | 10/10/2024 | KALPATARU ENTERPRISE | 32.25 | 0 | 0 | 0
Total | [13 empty] | 417.58 | 230.63 | 55.23