## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | HOOGHLY |  | Hooghly Division | RETROFITTING WORKS FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) WITHIN THE COMMAND AREA OF RAJHAT WATER SUPPLY SCHEME UNDER POLBA-DADPUR BLOCK OF CHINSURHA SUB-DIVISION UNDER HOOGHLY DIVISION PHE DTE. | SM/09772 | Retrofitting | Providing 200 nos Functional Household Tap Connection (FHTC) within the command area of Rajhat Zone-I Water Supply Scheme Under Chinsurah Sub-Division of Hooghly Division P.H.E Dte. | Assistant Engineer (Civil) |  | ORD/000291/2021-2022 | 2202/Hug | 14/12/2021 | 03/01/2022 | GHOSH CONSTRUCTION | 13.02 | 13.02 | 100 | 0
2 | HOOGHLY |  | Hooghly Division | RETROFITTING WORKS FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) WITHIN THE COMMAND AREA OF RAJHAT WATER SUPPLY SCHEME UNDER POLBA-DADPUR BLOCK OF CHINSURHA SUB-DIVISION UNDER HOOGHLY DIVISION PHE DTE. | SM/09772 | Retrofitting | Providing 500 nos Functional Household Tap Connection (FHTC) within the command area of RAJHAT & HARAL ZONE-I Water Supply Scheme Under Chinsurah Sub-Division of Hooghly Division P.H.E Dte. | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/000438/2021-2022 | 456/Hug | 10/03/2022 | 09/04/2022 | M/S S.C CIVIL ENTERPRISE | 31.96 | 31.4 | 98.27 | 0
3 | HOOGHLY |  | Central Drilling | RETROFITTING WORKS FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) WITHIN THE COMMAND AREA OF RAJHAT WATER SUPPLY SCHEME UNDER POLBA-DADPUR BLOCK OF CHINSURHA SUB-DIVISION UNDER HOOGHLY DIVISION PHE DTE. | SM/09772 | Retrofitting | PROVIDING DRILLING CREW AND OTHER ALLIED WORKS FOR CONSTRUCTION OF TUBE WELL (300MM X 200MM X 250 MTRS DEPTH) BY UTILIZING DEPARTMENTAL MACHINERIES FOR RAJHAT W/S SCHEME (Z-II) POLBA DADPUR BLOCK UNDER HOOGHLY DISTRICT, CDD, PHE DTE. | Driller In Charge | Junior Engineer | ORD/000022/2022-2023 | 303/ CDD | 27/04/2022 | 27/05/2022 | C.M. ENTERPRISE | 14.67 | 2.21 | 15.06 | 0
4 | HOOGHLY |  | Central Drilling | RETROFITTING WORKS FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) WITHIN THE COMMAND AREA OF RAJHAT WATER SUPPLY SCHEME UNDER POLBA-DADPUR BLOCK OF CHINSURHA SUB-DIVISION UNDER HOOGHLY DIVISION PHE DTE. | SM/09772 | Retrofitting | REPAIRING OF PTO AND OTHER FOR RIG MACHINE JOHN/DR/1500-III UNDER CMSD-I (D), CDD, PHE DTE. |  |  | ORD/000251/2021-2022 | 214/CMSD-I(D) | 09/11/2021 | 24/11/2021 | PADMA ENGINEERING & CO. | 4.52 | 0.29 | 6.42 | 0
5 | HOOGHLY |  | Central Drilling | RETROFITTING WORKS FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) WITHIN THE COMMAND AREA OF RAJHAT WATER SUPPLY SCHEME UNDER POLBA-DADPUR BLOCK OF CHINSURHA SUB-DIVISION UNDER HOOGHLY DIVISION PHE DTE. | SM/09772 | Retrofitting | PROVIDING TUBE WELL MATERIALS OF 200MM NOMINAL DIA CONFORMING TO IS: 12818:2010 WITH OTHER MATERIALS AT SITE FOR CONSTRUCTION OF TUBE WELL IN POLBA DADPUR BLOCK AT RAJHAT (ZONE-II) W/S SCHEME UNDER CDD, PHE DTE. |  |  | ORD/000004/2022-2023 | 90/ CMSD-I (D) | 19/04/2022 | 04/05/2022 | C.M. ENTERPRISE | 5 | 4.07 | 81.45 | 0
6 | HOOGHLY |  | Central Drilling | RETROFITTING WORKS FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) WITHIN THE COMMAND AREA OF RAJHAT WATER SUPPLY SCHEME UNDER POLBA-DADPUR BLOCK OF CHINSURHA SUB-DIVISION UNDER HOOGHLY DIVISION PHE DTE. | SM/09772 | Retrofitting | PROVIDING TUBE WELL MATERIALS OF 300MM NOMINAL DIA CONFORMING TO IS: 12818:2010 WITH OTHER MATERIALS AT SITE FOR CONSTRUCTION OF TUBE WELL IN POLBA DADPUR BLOCK AT RAJHAT (ZONE-I) W/S SCHEME UNDER CDD, PHE DTE. |  |  | ORD/000006/2022-2023 | 87/CMSD-I (D) | 18/04/2022 | 03/05/2022 | C.M. ENTERPRISE | 4.99 | 4.55 | 91.04 | 0
7 | HOOGHLY |  | Central Drilling | RETROFITTING WORKS FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) WITHIN THE COMMAND AREA OF RAJHAT WATER SUPPLY SCHEME UNDER POLBA-DADPUR BLOCK OF CHINSURHA SUB-DIVISION UNDER HOOGHLY DIVISION PHE DTE. | SM/09772 | Retrofitting | PROVIDING DRILLING CREW AND OTHER ALLIED WORKS FOR CONSTRUCTION OF TUBE WELL (300 MM X 200 MM X 250 MTRS DEPTH) BY UTILIZING DEPARTMENTAL MACHINERIES FOR RAJHAT W/S SCH (Z-II), POLBA DADPUR BLOCK UNDER HOOGHLY DISTRICT, CDD, PHE DTE. | Driller In Charge | Junior Engineer | ORD/000009/2022-2023 | 303/CDD | 27/04/2022 | 27/05/2022 | C.M. ENTERPRISE | 14.67 | 3.45 | 23.53 | 0
8 | HOOGHLY |  | Central Drilling | RETROFITTING WORKS FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) WITHIN THE COMMAND AREA OF RAJHAT WATER SUPPLY SCHEME UNDER POLBA-DADPUR BLOCK OF CHINSURHA SUB-DIVISION UNDER HOOGHLY DIVISION PHE DTE. | SM/09772 | Retrofitting | PROVIDING TUBE WELL MATERIALS OF 300MM NOMINAL DIA CONFORMING TO IS: 12818:2010 WITH OTHER MATERIALS AT SITE FOR CONSTRUCTION OF TUBE WELL IN POLBA DADPUR BLOCK AT RAJHAT (ZONE-II) W/S SCHEME UNDER CDD, PHE DTE. |  |  | ORD/000002/2022-2023 | 89/CMSD-I (D) | 19/04/2022 | 04/05/2022 | C.M. ENTERPRISE | 4.99 | 4.99 | 100 | 0
9 | HOOGHLY |  | Central Drilling | RETROFITTING WORKS FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) WITHIN THE COMMAND AREA OF RAJHAT WATER SUPPLY SCHEME UNDER POLBA-DADPUR BLOCK OF CHINSURHA SUB-DIVISION UNDER HOOGHLY DIVISION PHE DTE. | SM/09772 | Retrofitting | PROVIDING TUBE WELL MATERIALS OF 200MM NOMINAL DIA CONFORMING TO IS: 12818:2010 WITH OTHER MATERIALS AT SITE FOR CONSTRUCTION OF TUBE WELLIN POLBA DADPUR BLOCK AT RAJHAT (ZONE-I) W/S SCHEME UNDER CDD, PHE DTE. |  |  | ORD/000005/2022-2023 | 88/CMSD-I (D) | 18/04/2022 | 03/05/2022 | C.M. ENTERPRISE | 5 | 4.69 | 93.82 | 0
10 | HOOGHLY |  | Central Drilling | RETROFITTING WORKS FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) WITHIN THE COMMAND AREA OF RAJHAT WATER SUPPLY SCHEME UNDER POLBA-DADPUR BLOCK OF CHINSURHA SUB-DIVISION UNDER HOOGHLY DIVISION PHE DTE. | SM/09772 | Retrofitting | PROVIDING TUBE WELL MATERIALS, (300MM DIA) CONFORMING TO IS: 12818:2010 AND OTHER WORKS AT SITE FOR CONSTRUCTION OF TUBE WELL AT RAJHAT (Z-I) PWSS, POLBA DADPUR BLOCK, HOOGHLY DISTRICT UNDER CDD, PHE DTE. | Driller In Charge | Junior Engineer | ORD/000213/2022-2023 | 476/CMSD-II | 11/10/2022 | 18/10/2022 | TAMAL ENTERPRISE | 0.53 | 0.51 | 94.86 | 0
11 | HOOGHLY |  | Central Drilling | RETROFITTING WORKS FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) WITHIN THE COMMAND AREA OF RAJHAT WATER SUPPLY SCHEME UNDER POLBA-DADPUR BLOCK OF CHINSURHA SUB-DIVISION UNDER HOOGHLY DIVISION PHE DTE. | SM/09772 | Retrofitting | PROVIDING TUBE WELL MATERIALS, CONFORMING TO IS: 12818:2010 WITH OTHER MATERIALS AT SITE FOR CONSTRUCTION OF TUBE WELL AT RAJHAT (Z-I), POLBA DADPUR BLOCK, HOOGHLY DISTRICT UNDER CDD, PHE DTE. |  |  | ORD/000149/2022-2023 | 138/S&WSD | 12/08/2022 | 27/08/2022 | TAMAL ENTERPRISE | 5 | 4.55 | 91 | 0
12 | HOOGHLY |  | Central Drilling | RETROFITTING WORKS FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) WITHIN THE COMMAND AREA OF RAJHAT WATER SUPPLY SCHEME UNDER POLBA-DADPUR BLOCK OF CHINSURHA SUB-DIVISION UNDER HOOGHLY DIVISION PHE DTE. | SM/09772 | Retrofitting | SUPPLY & DELIVERY OF CONSUMABLES AND OTHERS WORKS AT SITE FOR CONSTRUCTION OF TUBE WELL AT RAJHAT (Z-I) PWSS, POLBA DADPUR BLOCK, HOOGHLY DISTRICT UNDER CDD, PHE DTE. |  |  | ORD/000150/2022-2023 | 139/S&WSD | 12/08/2022 | 27/08/2022 | DEY ENTERPRISE | 4.99 | 2.83 | 56.77 | 0
13 | HOOGHLY |  | Central Drilling | RETROFITTING WORKS FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) WITHIN THE COMMAND AREA OF RAJHAT WATER SUPPLY SCHEME UNDER POLBA-DADPUR BLOCK OF CHINSURHA SUB-DIVISION UNDER HOOGHLY DIVISION PHE DTE. | SM/09772 | Retrofitting | PROVIDING DRILLING CREWS FOR CONSTRUCTION OF TUBE WELL BY DEPARTMENTAL RIG MACHINE AT RAJHAT (Z-I) PWSS, POLBA DADPUR BLOCK, HOOGHLY DISTRICT UNDER CDD, PHE DTE. |  |  | ORD/000151/2022-2023 | 137/S&WSD | 12/08/2022 | 27/08/2022 | TAMAL ENTERPRISE | 3.92 | 3.74 | 95.53 | 0
14 | HOOGHLY |  | Central Drilling | RETROFITTING WORKS FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) WITHIN THE COMMAND AREA OF RAJHAT WATER SUPPLY SCHEME UNDER POLBA-DADPUR BLOCK OF CHINSURHA SUB-DIVISION UNDER HOOGHLY DIVISION PHE DTE. | SM/09772 | Retrofitting | SUPPLY & DELIVERY OF CONSUMBLES AND OTHERS WORKS AT SITE FOR CONSTRUCTION OF TUBE WELL AT RAJHAT (Z-II) PWSS, POLBA DADPUR BLOCK, HOOGHLT DISTRICT UNDER CDD, PHE DTE. |  |  | ORD/000205/2022-2023 | 141/S&WSD | 12/08/2022 | 27/08/2022 | M/S P P ELECTRICALS | 4.98 | 3.69 | 73.99 | 0
15 | HOOGHLY |  | Central Drilling | RETROFITTING WORKS FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) WITHIN THE COMMAND AREA OF RAJHAT WATER SUPPLY SCHEME UNDER POLBA-DADPUR BLOCK OF CHINSURHA SUB-DIVISION UNDER HOOGHLY DIVISION PHE DTE. | SM/09772 | Retrofitting | PROVIDING DRILLING CREWS FOR CONSTRUCTION OF TUBE WELL BY DEPARTMENTAL RIG MACHINE AT RAJHAT (Z-II) PWSS, POLBA DADPUR BLOCK, HOOGHLY DISTRICT UNDER CDD, PHE DTE. |  |  | ORD/000206/2022-2023 | 140/S&WSD | 12/08/2022 | 27/08/2022 | M/S P P ELECTRICALS | 3.91 | 3.8 | 97.16 | 0
16 | HOOGHLY |  | Central Drilling | RETROFITTING WORKS FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) WITHIN THE COMMAND AREA OF RAJHAT WATER SUPPLY SCHEME UNDER POLBA-DADPUR BLOCK OF CHINSURHA SUB-DIVISION UNDER HOOGHLY DIVISION PHE DTE. | SM/09772 | Retrofitting | PROCVIDING TUBE WELL MATERIALS, CONFORMING TO IS: 12818:2010 WITH OTHER MATERIALS AT SITE FOR CONSTRUCTION OF TUBE WELL AT RAJHAT (Z-II) PWSS, POLBA DADPUR BLOCK, HOOGHLY DISTRICT UNDER CDD, PHE DTE. |  |  | ORD/000204/2022-2023 | 142/S&WSD | 12/08/2022 | 27/08/2022 | M/S P P ELECTRICALS | 5 | 4.78 | 95.68 | 0
17 | HOOGHLY |  | Central Drilling | RETROFITTING WORKS FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) WITHIN THE COMMAND AREA OF RAJHAT WATER SUPPLY SCHEME UNDER POLBA-DADPUR BLOCK OF CHINSURHA SUB-DIVISION UNDER HOOGHLY DIVISION PHE DTE. | SM/09772 | Retrofitting | PROVIDING DRILLING CREWS AND OTHER ALLIED WORKS FOR CONSTRUCTION OF TUBE WELL (300MM X 200MM X 250 MTRS. DEPTH) BY UTILISING DEPARTMENTAL MACHINERIES FOR RAJHAT W/S SCHEME (Z-I) POLBA DADPUR BLOCK HOOGHLY DISTRICT, CDD, PHE DTE. | Driller In Charge | Junior Engineer | ORD/000001/2022-2023 | 301/CDD | 27/04/2022 | 27/05/2022 | C.M. ENTERPRISE | 14.67 | 5.74 | 39.16 | 0
18 | HOOGHLY |  | Hooghly Division | RETROFITTING WORKS FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) WITHIN THE COMMAND AREA OF RAJHAT WATER SUPPLY SCHEME UNDER POLBA-DADPUR BLOCK OF CHINSURHA SUB-DIVISION UNDER HOOGHLY DIVISION PHE DTE. | SM/09772 | Retrofitting | Providing 1480 nos Functional Household Tap Connection (FHTC) within the command area of Rajhat (Zone-II) Water Supply Scheme Under Chinsurah Sub-Division of Hooghly Division P.H.E Dte | Assistant Engineer (Civil) |  | ORD/000207/2021-2022 | 1676/Hug | 13/09/2021 | 23/10/2021 | M/S BUILDWELL | 59.06 | 27.65 | 46.81 | 0
19 | HOOGHLY |  | Hooghly Division | RETROFITTING WORKS FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) WITHIN THE COMMAND AREA OF RAJHAT WATER SUPPLY SCHEME UNDER POLBA-DADPUR BLOCK OF CHINSURHA SUB-DIVISION UNDER HOOGHLY DIVISION PHE DTE. | SM/09772 | Retrofitting | Providing 1480 nos Functional Household Tap Connection (FHTC) within the command area of Rajhat (Zone-II) Water Supply Scheme Under Chinsurah Sub-Division of Hooghly Division P.H.E Dte | Assistant Engineer (Civil) |  | ORD/000546/2021-2022 | 1676/HUG | 13/09/2021 | 23/10/2021 | M/S BUILDWELL | 59.06 | 31.4 | 53.17 | 100
20 | HOOGHLY |  | Hooghly Division | RETROFITTING WORKS FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) WITHIN THE COMMAND AREA OF RAJHAT WATER SUPPLY SCHEME UNDER POLBA-DADPUR BLOCK OF CHINSURHA SUB-DIVISION UNDER HOOGHLY DIVISION PHE DTE. | SM/09772 | Retrofitting | Construction of Boundary Wall & Pathway Development of Rajhat(Z-I) at H/W Site W/S Scheme under Chinsurah Sub-Division P.H.E. Dte. | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/000122/2022-2023 | 462/CH | 31/05/2022 | 10/07/2022 | S. G. ENTERPRISE | 3.36 | 0 | 0 | 0
21 | HOOGHLY |  | Central Drilling | RETROFITTING WORKS FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) WITHIN THE COMMAND AREA OF RAJHAT WATER SUPPLY SCHEME UNDER POLBA-DADPUR BLOCK OF CHINSURHA SUB-DIVISION UNDER HOOGHLY DIVISION PHE DTE. | SM/09772 | Retrofitting | HIRING OF DIESEL DRIVEN MOTOR CAB (BS-III & ABOVE) (NON AC) HIVING CONTRACT CARRIAGE PERMIT ALONG WITH DRIVER FOR THE OFFICE OF THE CALCUTTA MECHANICAL SUB DIVISION -I (D), PHE DTE. |  |  | ORD/000173/2022-2023 | 483/CMSD-I | 23/09/2022 | 03/10/2022 | SUJATA BHOWMICK | 0.86 | 1.69 | 195.94 | 0
22 | HOOGHLY |  | Central Drilling | RETROFITTING WORKS FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) WITHIN THE COMMAND AREA OF RAJHAT WATER SUPPLY SCHEME UNDER POLBA-DADPUR BLOCK OF CHINSURHA SUB-DIVISION UNDER HOOGHLY DIVISION PHE DTE. | SM/09772 | Retrofitting | HIRING OF DIESEL DRIVEN MOTOR CAB (BS-III & ABOVE) (NON AC) HIVING CONTRACT CARRIAGE PERMIT ALONG WITH DRIVER FOR THE OFFICE OF THE CALCUTTA MECHANICAL SUB DIVISION -I (D), PHE DTE. |  |  | ORD/000356/2022-2023 | 483/CMSD-I (RA-VI & F) | 23/09/2022 | 08/10/2022 | SUJATA BHOWMICK | 0.39 | 0.39 | 100 | 0
23 | HOOGHLY |  | Hooghly Division | RETROFITTING WORKS FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) WITHIN THE COMMAND AREA OF RAJHAT WATER SUPPLY SCHEME UNDER POLBA-DADPUR BLOCK OF CHINSURHA SUB-DIVISION UNDER HOOGHLY DIVISION PHE DTE. | SM/09772 | Retrofitting | Providing Functional Household Tap Connection (FHTC) within the command area (left out portion) of RAJHAT Water Supply Scheme Under Chinsurah Sub-Division of Hooghly Division P.H.E Dte. | Assistant Engineer (Civil) |  | ORD/000889/2022-2023 | 1509/Hug | 22/07/2022 | 11/08/2022 | GHOSH CONSTRUCTION | 20.38 | 19.74 | 96.85 | 100
24 | HOOGHLY |  | Hooghly Division | RETROFITTING WORKS FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) WITHIN THE COMMAND AREA OF RAJHAT WATER SUPPLY SCHEME UNDER POLBA-DADPUR BLOCK OF CHINSURHA SUB-DIVISION UNDER HOOGHLY DIVISION PHE DTE. | SM/09772 | Retrofitting | Providing Functional Household Tap Connection (FHTC) under JJM within left out Mouzas / Habitations of different PWSS under POLBA-DADPUR Block of CHINSURAH Sub-Division of Hooghly Division P.H.E Dte. | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/000341/2023-2024 | 2431/HUG | 11/08/2023 | 10/09/2023 | DILIP KUMAR GHOSH | 42.76 | 41.91 | 98.01 | 95
Total | [13 empty] | 327.7 | 221.1 | 67.47