## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | HOOGHLY |  | Hooghly Division | RETROFITTING WORKS FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) WITHIN THE COMMAND AREA OF MORHAL WATER SUPPLY SCHEME UNDER JANGIPARA BLOCK OF SERAMPORE SUB-DIVISION UNDER HOOGHLY DIVISION PHE DTE. | SM/09773 | Retrofitting | Providing additional 20 nos FHTC in Morhal PWSS | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/000508/2021-2022 | 165/SER. | 26/10/2021 | 30/11/2021 | TOTON MONDAL | 1.35 | 0 | 0 | 0
2 | HOOGHLY |  | Hooghly Division | RETROFITTING WORKS FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) WITHIN THE COMMAND AREA OF MORHAL WATER SUPPLY SCHEME UNDER JANGIPARA BLOCK OF SERAMPORE SUB-DIVISION UNDER HOOGHLY DIVISION PHE DTE. | SM/09773 | Retrofitting | Providing Add. 90 nos FHTC within the Morhal PWSS | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/000505/2021-2022 | 164/Ser | 26/10/2021 | 25/11/2021 | ARUN SEAL AND CO. | 3.78 | 0 | 0 | 0
3 | HOOGHLY |  | Hooghly Division | RETROFITTING WORKS FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) WITHIN THE COMMAND AREA OF MORHAL WATER SUPPLY SCHEME UNDER JANGIPARA BLOCK OF SERAMPORE SUB-DIVISION UNDER HOOGHLY DIVISION PHE DTE. | SM/09773 | Retrofitting | Providing additional 800 nos Functional Household Tap Connection (FHTC) within the command area of Morhal Water Supply Scheme Under Serampore Sub-Division of Hooghly Division P.H.E Dte. [Block-Jangipara] | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/000358/2020-2021 | 470/Hug | 26/02/2021 | 28/03/2021 | M/S SHIVAM UDYOG | 29.36 | 0 | 0 | 0
4 | HOOGHLY |  | Hooghly Division | RETROFITTING WORKS FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) WITHIN THE COMMAND AREA OF MORHAL WATER SUPPLY SCHEME UNDER JANGIPARA BLOCK OF SERAMPORE SUB-DIVISION UNDER HOOGHLY DIVISION PHE DTE. | SM/09773 | Retrofitting | Construction of 3.6 m. X 3.0 m. Switch Room without sanitary and water supply arrangement at 3rd tube well site of Morhal W/S Scheme under Serampore Sub-Division of Hooghly Division, P. H. E. Directorate. | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/000391/2021-2022 | 297/SER | 21/02/2022 | 23/03/2022 | BAKSHI ENTERPRISE | 3.32 | 0 | 0 | 0
5 | HOOGHLY |  | Hooghly Division | RETROFITTING WORKS FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) WITHIN THE COMMAND AREA OF MORHAL WATER SUPPLY SCHEME UNDER JANGIPARA BLOCK OF SERAMPORE SUB-DIVISION UNDER HOOGHLY DIVISION PHE DTE. | SM/09773 | Retrofitting | Providing 150 nos Functional Household Tap Connection (FHTC) within the command area of RADHABALLAVPUR Water Supply Scheme Under ARAMBAG Sub-Division of Hooghly Division P.H.E Dte | Assistant Engineer,Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/000313/2021-2022 | 2232/Hug | 15/12/2021 | 04/01/2022 | DREAM INFRASTRUCTURE | 4.92 | 0 | 0 | 100
6 | HOOGHLY |  | Hooghly Division | RETROFITTING WORKS FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) WITHIN THE COMMAND AREA OF MORHAL WATER SUPPLY SCHEME UNDER JANGIPARA BLOCK OF SERAMPORE SUB-DIVISION UNDER HOOGHLY DIVISION PHE DTE. | SM/09773 | Retrofitting | Providing 250 nos Functional Household Tap Connection (FHTC) within the command area of Morhal Water Supply Scheme Under Serampore Sub-Division of Hooghly Division P.H.E Dte | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/000295/2021-2022 | 2206/Hug | 14/12/2021 | 03/01/2022 | ARUN SEAL AND CO. | 13.6 | 0 | 0 | 100
7 | HOOGHLY |  | Hooghly Division | RETROFITTING WORKS FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) WITHIN THE COMMAND AREA OF MORHAL WATER SUPPLY SCHEME UNDER JANGIPARA BLOCK OF SERAMPORE SUB-DIVISION UNDER HOOGHLY DIVISION PHE DTE. | SM/09773 | Retrofitting | Additional Work for Laying HDPE pipes & specials for connection with Main pipe line of Morhal Water Supply Scheme from Shaw para Kali Mandir to House of Harimohan Shaw under Serampore Sub-Division of Hooghly Division, P.H.E. Dte. | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/000739/2023-2024 | 309/SER | 29/12/2023 | 28/01/2024 | MA TARA CONSTRUCTION (SATYAJIT BANIK) | 1 | 0 | 0 | 100
8 | HOOGHLY |  | Hooghly Division | RETROFITTING WORKS FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) WITHIN THE COMMAND AREA OF MORHAL WATER SUPPLY SCHEME UNDER JANGIPARA BLOCK OF SERAMPORE SUB-DIVISION UNDER HOOGHLY DIVISION PHE DTE. | SM/09773 | Retrofitting | Additional Work for Laying HDPE pipes & specials for connection with Main pipe line of Morhal Water Supply Scheme from House of Harimohan Shaw to Jora Culvert under Serampore Sub-Division of Hooghly Division, P.H.E. Dte. | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/000738/2023-2024 | 308/SER | 29/12/2023 | 28/01/2024 | MA TARA CONSTRUCTION (SATYAJIT BANIK) | 1 | 0 | 0 | 100
9 | HOOGHLY |  | Hooghly Division | RETROFITTING WORKS FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) WITHIN THE COMMAND AREA OF MORHAL WATER SUPPLY SCHEME UNDER JANGIPARA BLOCK OF SERAMPORE SUB-DIVISION UNDER HOOGHLY DIVISION PHE DTE. | SM/09773 | Retrofitting | Designing making and erection of Display Board using logo and tag line of Jal Jeevan Mission to be placed at different work sites and HGJ villages for awareness generation among the people in the district of Hooghly under Serampore Sub Division under Hooghly Division PHE Dte. 1. Kotalpur PWSS 2. Morhal PWSS 3. Borhal PWSS 4. Antpur PWSS 5. Rajbalhat PWSS 6. Gopalpur-I PWSS | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/000943/2023-2024 | 113/SER | 23/02/2024 | 01/03/2024 | AMBIAN INFRASTRUCTURE | 0.95 | 0 | 0 | 80
10 | HOOGHLY |  | Hooghly Division | RETROFITTING WORKS FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) WITHIN THE COMMAND AREA OF MORHAL WATER SUPPLY SCHEME UNDER JANGIPARA BLOCK OF SERAMPORE SUB-DIVISION UNDER HOOGHLY DIVISION PHE DTE. | SM/09773 | Retrofitting | Repairing of Damaged Road due to FHTC Works at Western zone of Morhal W/S Scheme under Serampore Sub-Division of Hooghly Division P.H.E.Dte. | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/000208/2024-2025 | 553/SER | 19/09/2024 | 26/09/2024 | TOTON MONDAL | 4.97 | 0 | 0 | 98
11 | HOOGHLY |  | Hooghly Division | RETROFITTING WORKS FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) WITHIN THE COMMAND AREA OF MORHAL WATER SUPPLY SCHEME UNDER JANGIPARA BLOCK OF SERAMPORE SUB-DIVISION UNDER HOOGHLY DIVISION PHE DTE. | SM/09773 | Retrofitting | Laying CI/DI pipes & specials for connection with Main pipe line & T.W. No.-3 and interconnection including allied work with laying distribution system for Development of Morhal Water Supply Scheme under Serampore Sub-Division of Hooghly Division, P.H.E. Dte. SL NO - 08 | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/000376/2022-2023 | 2089/Hug | 21/09/2022 | 21/10/2022 | MA TARA CONSTRUCTION (SATYAJIT BANIK) | 14.32 | 0 | 0 | 99
12 | HOOGHLY |  | Hooghly Division | RETROFITTING WORKS FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) WITHIN THE COMMAND AREA OF MORHAL WATER SUPPLY SCHEME UNDER JANGIPARA BLOCK OF SERAMPORE SUB-DIVISION UNDER HOOGHLY DIVISION PHE DTE. | SM/09773 | Retrofitting | Sinking of 3rd tube-well by D.R. Rig method, Construction of 3.6 m X 3.0 m Switch Room with Sanitary and Water Supply arrangement, Construction of Boundary Wall, Laying rising main pipe for inter connection between Proposed T.W & Distribution of MORHAL Piped Water Supply Scheme under SERAMPORE Sub-Division of Hooghly Division P.HE Dte. | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/000755/2023-2024 | 390/HUG | 08/02/2024 | 08/04/2024 | BANSBERIA CONSTRUCTION CO. | 31.57 | 0 | 0 | 75
13 | HOOGHLY |  | Hooghly Division | RETROFITTING WORKS FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) WITHIN THE COMMAND AREA OF MORHAL WATER SUPPLY SCHEME UNDER JANGIPARA BLOCK OF SERAMPORE SUB-DIVISION UNDER HOOGHLY DIVISION PHE DTE. | SM/09773 | Retrofitting | Repairing of Switch Room & Boundary Wall at existing TW sites, and Construction of Boundary wall at 3rdT.W Site of MORHAL Water Supply Scheme under Serampore Sub-Division of Hooghly Division P.H.E. Dte. | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/000904/2023-2024 | 827/HUG | 11/03/2024 | 10/04/2024 | BAKSHI ENTERPRISE | 13.28 | 0 | 0 | 60
Total | [13 empty] | 123.45 | 0 | 0