## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | HOOGHLY |  | Hooghly Division | RETROFITTING WORKS FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) WITHIN THE COMMAND AREA OF DHAMAITIKAR WATER SUPPLY SCHEME UNDER DHANIAKHALI BLOCK OF CHINSURHA SUB-DIVISION UNDER HOOGHLY DIVISION PHE DTE. | SM/09774 | Retrofitting | Providing 502 nos F.H.T.C. in Dhamaitikar village of Dhamaitikar and its Adjoining Mouzas Water Supply Scheme Under Chinsurah Sub-Division of Hooghly Division P.H.E Dte. [Block-Dhaniakhali](Part-A) | Assistant Engineer (Civil) |  | ORD/000909/2020-2021 | 1337/HUG | 29/09/2020 | 29/10/2020 | SOUMYADIP DE | 19.04 | 0.44 | 2.32 | 100
2 | HOOGHLY |  | Hooghly Division | RETROFITTING WORKS FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) WITHIN THE COMMAND AREA OF DHAMAITIKAR WATER SUPPLY SCHEME UNDER DHANIAKHALI BLOCK OF CHINSURHA SUB-DIVISION UNDER HOOGHLY DIVISION PHE DTE. | SM/09774 | Retrofitting | Withdrawal & Re-Laying of DHAMAITIKAR and its Adjoining Mouzas Water Supply Scheme Under Chinsurah Sub-Division,P.H.E Dte. [Block - Dhaniakhali] | Assistant Engineer (Civil) |  | ORD/000264/2022-2023 | 719/CH | 23/08/2022 | 07/09/2022 | SUDIPTA SINHA | 4.86 | 4.85 | 99.78 | 0
3 | HOOGHLY |  | Hooghly Division | RETROFITTING WORKS FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) WITHIN THE COMMAND AREA OF DHAMAITIKAR WATER SUPPLY SCHEME UNDER DHANIAKHALI BLOCK OF CHINSURHA SUB-DIVISION UNDER HOOGHLY DIVISION PHE DTE. | SM/09774 | Retrofitting | Providing FHTC at the left out portions of Dhamatikar PWSS udner Bhanderhati-II Gram Panchayet of Dhaniakhali Block of Chinsurah Sub-Division, PHE Dte. | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/000056/2024-2025 | 2366/HUG | 21/06/2024 | 24/04/2025 | MUKHERJEE AND CO | 44.64 | 4.36 | 9.78 | 95
Total | [13 empty] | 68.53 | 9.65 | 14.09