## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | HOOGHLY |  | Hooghly Division | RETROFITTING WORKS FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) WITHIN THE COMMAND AREA OF KOLA WATER SUPPLY SCHEME UNDER CHINSURAH-MOGRA BLOCK OF CHINSURHA SUB-DIVISION UNDER HOOGHLY DIVISION PHE DTE. | SM/09775 | Retrofitting | Providing 1200 nos Functional Household Tap Connection (FHTC) within the command area of KOLA Water Supply Scheme Under Chinsurah Sub-Division of Hooghly Division P.H.E Dte | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/000358/2021-2022 | 119/Hug | 19/01/2022 | 20/03/2022 | GHOSH ENTERPRISE (SOUMEN GHOSH) | 67.95 | 63.78 | 93.85 | 0
2 | HOOGHLY |  | Hooghly Division | RETROFITTING WORKS FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) WITHIN THE COMMAND AREA OF KOLA WATER SUPPLY SCHEME UNDER CHINSURAH-MOGRA BLOCK OF CHINSURHA SUB-DIVISION UNDER HOOGHLY DIVISION PHE DTE. | SM/09775 | Retrofitting | Providing 350 nos Functional Household Tap Connection (FHTC) within the command area of KOLA & HARAL ZONE-II Water Supply Scheme Under Chinsurah Sub-Division of Hooghly Division P.H.E Dte | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/000439/2021-2022 | 457/Hug | 10/03/2022 | 30/03/2022 | ARATI ENGINEERING | 19.29 | 18.63 | 96.6 | 0
3 | HOOGHLY |  | Central Drilling | RETROFITTING WORKS FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) WITHIN THE COMMAND AREA OF KOLA WATER SUPPLY SCHEME UNDER CHINSURAH-MOGRA BLOCK OF CHINSURHA SUB-DIVISION UNDER HOOGHLY DIVISION PHE DTE. | SM/09775 | Retrofitting | PROVIDING TUBE WELL MATERIALS, CONFORMING TO IS: 12818:2010 WITH OTHER MATERIALS AT RAGHUNATHPUR W/S SCHEME TW-I, POLBA DADPUR BLOCK, HOOGHLY DIOSTRICT UNDER CDD, PHE DTE | Driller In Charge | Junior Engineer | ORD/000121/2022-2023 | 289/CMSD-II (D) | 01/06/2022 | 16/06/2022 | C.M. ENTERPRISE | 4.99 | 0 | 0 | 0
4 | HOOGHLY |  | Hooghly Division | RETROFITTING WORKS FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) WITHIN THE COMMAND AREA OF KOLA WATER SUPPLY SCHEME UNDER CHINSURAH-MOGRA BLOCK OF CHINSURHA SUB-DIVISION UNDER HOOGHLY DIVISION PHE DTE. | SM/09775 | Retrofitting | Providing 800 nos F.H.T.C. in Kola and its Adjoining Mouzas Water Supply Scheme UnderChinsurah Sub-Division of Hooghly Division P.H.E Dte. [Block-Chinsurah-Mogra] | Assistant Engineer (Civil) |  | ORD/000009/2021-2022 | 940/Hug | 06/05/2021 | 05/06/2021 | PRASUN ENTERPRISE (PRASUN BISWAS) | 39.21 | 6.16 | 15.72 | 0
5 | HOOGHLY |  | Hooghly Division | RETROFITTING WORKS FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) WITHIN THE COMMAND AREA OF KOLA WATER SUPPLY SCHEME UNDER CHINSURAH-MOGRA BLOCK OF CHINSURHA SUB-DIVISION UNDER HOOGHLY DIVISION PHE DTE. | SM/09775 | Retrofitting | Providing Functional Household Tap Connection (FHTC) under JJM within left out portion of KOLA PWSS under Chinsurah Sub-Division of Hooghly Division P.H.E Dte. | Assistant Engineer (Civil) | Junior Engineer (Civill) | ORD/000033/2023-2024 | 1133/HUG | 19/04/2023 | 19/05/2023 | ROY ENTERPRISE | 33.33 | 32.86 | 98.59 | 100
Total | [13 empty] | 164.77 | 121.43 | 73.7